## Slide 1
BPA Milestones – 3B Decision
  Public Process - BPA customer review and input prior to decision
  Consider lessons from NBFS and program/ governance design
  Present FS submittal results
  Evaluate ability to meet BPA’s WRAP Participation Principles
Decision on Binding Phase (Fall/Winter 2022) and BPA Customer Engagement
  Complete program and governance design
  Submit data for detailed modeling to establish Resource Adequacy value and PRM
  Compile FS data
    Winter 2022/23
    Summer 2023
  Refine design/modeling requirements based on continued learnings
  Continue engagement with BPA customers/ stakeholders
Non-Binding Forward Showing
Winter (2022/23) and Summer (2023)
  Sept 29, 2021 - Final letter to the region with decision on participation in NBFS phase of WRAP program
Decision on Non-Binding Forward Showing
  July 29, 2021 – Share BPA perspective on program details and implementation issues
  Aug 20, 2021 – Publish draft letter to the region (Aug 20-Sep 3)
  Aug 25, 2021 – Public meeting to provide clarification on issues in draft letter
BPA Customer Engagement
  BPA staff/executive resources participate in WRAP workgroups
  Finalize Phase 2B deliverables
  Develop implementation plan for Phase 3A
  WPP hires Program Operator
Close Out Phase 2B/
Phase 3A Implementation Planning (2020/2021)
NBFS = Non-Binding Forward Showing