## Open Items
ID# | Submitter | Topic/Theme | Question/Consideration | Planned Stakeholder Discussion Timing | Resolution Venue | Dependencies | Original Question/Consideration | Outcome | Resolved
12 | PPC | Decision Process | What are the risks (operational, cost exposure, regulatory, legal) of BPA’s participation and how will BPA mitigate them? What are the risks of not participating? | Fall 2022 | Business Case Elements/CloseOut Letter | Forward Showing Results. Finalized governance structure.
99 | AWEC | Program Impacts | Request for BPA to clarify its thinking if BPA is considering limits, given NLSL determinations are made annually, to a customer’s ability to make new elections each forward showing season and what those limits may be. | Fall 2022 | Formal Decision Process
100 | AWEC | BPA Products and Services | If a consumer load meets the exclusion requirements under WRAP, but their load does not meet the NLSL designation by BPA, would BPA prevent them from requesting the exclusion for the load? | Fall 2022 | Formal Decision Process |  | Seeks further discussion around how customers may exclude NLSL and treat PF-served portion separately when the customer has grandfathered PF-serving load and NLSL at the same site
102 | UEC | Decision Process | Encourage BPA to develop its analysis [for the formal decision] with consideration of at least two timeframes: (1) the benefits and risks to customers during the Regional Dialogue contract term, and (2) the benefits and risks to customers thereafter. This analysis will permit BPA’s customers like UEC to make informed decisions regarding the participation of the loads they serve currently, and in the future. | Fall 2022 | Formal Decision Process

## Resolved Items
ID# | Submitter | Topic/Theme | Question/Consideration | Planned Stakeholder Discussion Timing | Resolution Venue | Dependencies | Original Question/Consideration | Outcome | Resolved
1 | AWEC | Cost Allocation/Rates | BPA needs to determine how costs (and benefits) will impact NLSLs prior to making a 3B decision | Sept 2022 | Formal Decision Process | BPA NLSL operational treatment |  | BPA provided a response in the Sept 29 2022 decision meeting. Treatment and associated credit process would be part of standard rate setting and include BPA's rates to be implemented for the binding season elected if BPA decides to join WRAP. | X
11 | PPC | Decision Process | What are the objectives of participating in WRAP and how does WRAP participation compare with other approaches to meeting those objectives? | Sept 2022 | Formal Decision Process |  | What is the value proposition for BPA in the formation of a WRAP compared to other alternatives that would aim to address the agency’s resource adequacy concerns? | BPA provided a response in the Sept 29 2022 decision meeting. BPA referenced the introduction known as the "island" slide at the beginning of the meeting. | X
13 | PPC | Decision Process | What are the anticipated costs of participating in the program? How will those costs be recovered? | Sept 2022 | Business Case Elements/CloseOut Letter | Forward Showing Results. Phase 3A design refinements. | What is the business case for 1) the binding forward showing aspect of the program and 2) the operational aspect of the program? How does the business case change under different assumptions of BPA load obligations? | BPA provided a response in the Sept 29 2022 decision meeting. BPA provided the "Business Case for WRAP" presentation to describe anticipated costs. BPA provided "WRAP Participation Interaction with other BPA Initiatives" presentation to describe cost recovery. | X
15 | PPC | Decision Process | What are the anticipated benefits of participating in the program? Who are the recipients of those benefits? | Sept 2022 | Business Case Elements/CloseOut Letter | Forward Showing Results. | What additional costs/benefits does BPA anticipate for its customers if the agency participates? How does this differ by product? | BPA provided a response in the Sept 29 2022 decision meeting. BPA provided the "Business Case for WRAP" presentation to describe anticipated costs. | X
16 | PPC | BPA Products and Services | Does BPA believe that participation will improve the competitiveness of its products and services? If so, how? | Sept 2022 | Formal Decision Process |  |  | BPA provided a response in the Sept 29 2022 decision meeting. Any full requirements product offering by BPA would continue to place full planning responsibility on BPA, specific features and services included with future contract products have not yet been designed. | X
17 | PPC | BPA Products and Services | Is BPA expected to need to make additional capacity purchases to be compliant with the program? How does this expectation change over time? How could this expectation be impacted by customers' decisions on post-2028 contracts? | Sept 2022 | Formal Decision Process | Forward Showing Results. |  | BPA provided a response in the Sept 29 2022 decision meeting. BPA does not see a requirement to purchase additional capacity at this time. If BPA joins WRAP, clear evaluation of WRAP would be part of product design and implementation for Provider of Choice. | X
21 | PPC | BPA Products and Services | How does the development of post-2028 product options impact BPA’s participation in the RA program? | Sept 2022 | RA Engagement Workshop / Provider of Choice |  |  | BPA provided a response in the Sept 29 2022 decision meeting. If BPA joins WRAP, BPA will work with customers to develop and design products for post-2028. | X
23 | PPC | Cost Allocation/Rates | Consider rate impacts to BPA's power products | Sept 2022 | Business Case Elements/CloseOut Letter |  |  | BPA provided a response in the Sept 29 2022 decision meeting. BPA treatment of costs and benefits - BPA staffing/system costs will be applied to Composite cost pool; WPP assessed fees/charges and other costs/benefits will be applied to the Non-Slice cost pool. | X
24 | PPC | Cost Allocation/Rates | What is the anticipated rate treatment of program costs/benefits? Does this change if BPA's anticipated position (long vs. short) changes in the program? | Sept 2022 | Formal Decision Process |  |  | BPA provided a response in the Sept 29 2022 decision meeting. BPA treatment of costs and benefits - BPA staffing/system costs will be applied to Composite cost pool; WPP assessed fees/charges and other costs/benefits will be applied to the Non-Slice cost pool. | X
25 | PPC | Cost Allocation/Rates | How will BPA recover the costs associated with capacity held out to cover NLSLs? | Sept 2022 | Formal Decision Process |  |  | BPA provided a response in the Sept 29 2022 decision meeting. Treatment and associated credit process would be part of standard rate setting and include BPA's rates to be implemented for the binding season elected if BPA decides to join WRAP. | X
51 | WPAG | Decision Process | BPA has indicated that the forward showing requirement under the RA program is unlikely to be a binding constraint on how BPA plans to meet its load obligations. To the extent BPA does not plan to change its planning process, it cannot say that the lower Planning Reserve Margin (“PRM”) gained by participating in the program ultimately leads to benefits for its customers because BPA will still incur the planning costs of its higher planning standard. How will this be factored into BPA’s business case for joining the binding phase of the program? | Sept 2022 | Formal Decision Process | Forward Showing Results & PO Evaluation Results. |  | BPA provided a response in the Sept 29 2022 decision meeting. BPA has an energy constrained system and will continue to plan based on its energy planning methodologies. The business case does not take into account a benefit from the reduced PRM value. | X
69 | PPC | BPA Products and Services | Item #20: In response to PPC’s request that BPA conduct a business case sensitivity assuming all preference customers choose to have BPA serve their net requirements post-2028, BPA stated that it has a broad mandate which directs the agency to meet “its firm power customer needs, which is impartial to the product type chosen by preference customers.” PPC does not disagree with this statement; however, in this context BPA is specifically differentiating the treatment of preference customers in the RA program based on their chosen product. Based on BPA’s interpretation of customers’ existing contracts, selection of a different power product would impact the agency’s obligations under the RA program. Thus, there is the potential that customers selecting different power products could impact BPA’s business case for participating in WRAP. A scenario assuming that BPA is responsible for all preference customer obligations post-2028 would provide a helpful datapoint since customers have the right to place those obligations on BPA. Regardless of whether this specific sensitivity is analyzed, some assessment of how varying levels of obligation under the program effect BPA’s business case for participation should be conducted. | Sept 2022 | Formal Decision Process |  |  | BPA provided a response in the Sept 29 2022 decision meeting. BPA's statute requires it to meet meet net requirements load, not planning reserve margin. BPA has responsibiityfor RA planning for LF customers but not Block or Slice/Block. | X
86 | UEC | Program impacts | Please provide the attestation that BPA will require of a customer, coordinating with BPA, to exclude all or a portion of an NLSL load from BPA WRAP coverage? | Sept 2022 | Formal Decision Process |  |  | BPA provided a response in the Sept 29 2022 decision meeting. The attestation is a WRAP attestation and WRAP requirement. BPA to share once WRAP develops it. | X
90 | UEC | BPA Products and Services | Will BPA allow changes to the purchase period election Exhibits of the Regional Dialogue contracts in order to update specified and unspecified resource amount elections, Tier 2 elections, RSS elections, etc.? Are there any other changes to election rights or deadlines anticipated as a result of BPA’s participation in the WRAP? Please explain. | Sept 2022 | Formal Decision Process |  |  | BPA provided a response in the Sept 29 2022 decision meeting. Under Regional Dialogue, the election deadlines are outlined in existing contracts and are not expected to change. | X
98 | AWEC | Program Impacts | Whether and how BPA will consider any type of limit on the amount of eligible NLSL load that can be excluded, and whether the consideration for that limit would be a BPA decision, or whether BPA views that as a determination made at the WRAP level. | Sept 2022 | Formal Decision Process |  |  | BPA provided a response at the Sept 29 2022 decision meeting. Load exclusion process is WRAP's and applies to single line discrete loads which NLSL meets the requirement. Load exclusion is subject to a mutually signed attestation (yet to be developed by WRAP). An LRE cannot choose on its own to exclude any load or portion. | X
101 | UEC | Decision Process | Request for BPA to clearly articulate the potential costs and benefits to UEC’s members of WRAP participation. | Sept 2022 | Formal Decision Process |  |  | BPA referenced responses to 13 and 15 in the Sept 29 2022 decision meeting. | X
103 | UEC | Cost Allocation/Rates | Concerned that BPA is requiring customers who signed Regional Dialogue contracts which remain in force until 2028 to discuss and resolve credits/penalties in the BP-24 rate case setting (covering Fiscal Years 2024-25) for services and obligations that were never a part of the contract, but now are “required” due to BPA’s potential and entirely elective participation in a voluntary Resource Adequacy program. The disconnect between current contract rates, terms and conditions and the WRAP has not been adequately considered or articulated. | Sept 2022 | Formal Decision Process |  |  | BPA provided a response in the Sept 29 2022 decision meeting. BPA's authority to participate in WRAP arises under section 11(b)(6)(i) of the Transmission System Act of 1974. WRAP is another tool to meet firm contractual obligations. | X
104 | UEC | Cost Allocation/Rates | Disconnect between BPA having sufficient QCC on a planning basis, but then asserting a risk of unidentified cost-shifts as the basis for creating and allocating to BPA customers credits and penalties needs far better articulation - including the contractual basis for doing so in the current contract period. Respectfully, there cannot be a “credit” for NLSL WRAP participation without an accompanying cost, and it is reasonable to characterize that cost which will be allocated in BP-24 to some or all of BPA’s preference customers as a “penalty”. | Sept 2022 | Formal Decision Process |  |  | BPA provided a response in the Sept 29 2022 decision meeting. BPA outlines a solution in order to address cost shift, placing the capacity responsibility and costs back on the correct specific customer. In order to account for the opportunity costs of capacity, the proposed BP-24 RA incentives included in the proposals are based on BPA's embedded cost of capacity. | X
105 | UEC | Program Impacts | Provide more details regarding how loads served with unspecified resources will impose costs on the customers of the Federal power system, whether Tier 1 or Tier 2 (or other resource pools). | Sept 2022 | Formal Decision Process |  |  | BPA provided a response at the Sept 29 2022 decision meeting. BPA would purchase power to cover amount of customer(s) unspecified resource(s) that do not meet the program. At this time, BPA does not believe it can quantify the opportunity cost. See also 106 and 107. | X
106 | UEC | Program Impacts | Identify the benefits, by way of avoided costs, that BPA anticipates will be realized by Tier 2 customers as a result of some preference customers choosing to serve these loads with unspecified resources. | Sept 2022 | Formal Decision Process |  |  | BPA provided a response at the Sept 29 2022 decision meeting. Based on WRAP rules, costs and benefits to customers with AHWM load served with firm power at appliable PF Tier 2 rate isn't relevent. all AHWM load regardless of how it is served is part of the program load. See also 105 | X
107 | UEC | Program Impacts | Explain why BPA is not allowing the exclusion of A-RHWM load. Identify the costs and benefits that would be realized by Tier 2 customers as a result of some customers serving AHWM loads with unspecified resources. | Sept 2022 | Formal Decision Process |  |  | BPA provided a response at the Sept 29 2022 decision meeting. Based on WRAP rules, costs and benefits to customers with AHWM load served with firm power at appliable PF Tier 2 rate isn't relevent. all AHWM load regardless of how it is served is part of the program load. See also 105 | X
108 | UEC | BPA Products and Services | Request to elaborate on what new planning requirements, accounting and application(s) are being contemplated for the post-2028 contracts. | Sept 2022 | Formal Decision Process |  |  | BPA provided a response at the Sept 29 2022 decision meeting. Clarity on requirements, accounting, and application should be provided in the Provider of Choice process and prior to customers signing final contracts in late 2025. | X
109 | UEC | BPA Products and Services | Appears to be a conflict in messages between BPA’s intent to encourage resource development under Provider of Choice discussions and the policies related to WRAP for unspecified resources. Has BPA considered allowing a specified portion of load to be served with unspecified resources? | Sept 2022 | Formal Decision Process |  |  | BPA provided a response at the Sept 29 2022 decision meeting. If BPA joins WRAP, it may need to reassess the resource requirements and costs associated with difference resource types for future contracts. | X
87 | UEC | Cost Allocation/Rates | What is the anticipated cost-basis for assessing a charge or penalty for NLSL load that is NOT excluded from BPA’s WRAP coverage, but still served with unspecified resources – for example, if documentation for known/existing resources to serve unspecified obligations is NOT submitted? How is the application of a new charge consistent with the RD PSA terms and conditions? | July 2022 / Sept 2022 | RA Engagement Workshop |  |  | BPA provided a response in the July 26 2022 workshop and an updated response in the Sept 29 2022 decision meeting. Resource adequacy incentives would be included in the 2024 Power Rates Scedules and GRSPs with applicable billing determinant amounts. | X
88 | UEC | Cost Allocation/Rates | What is the anticipated cost-basis for credits awarded to customers using known/existing resources rather than unspecified resources for serving A-RHWM loads? How is the application of this credit consistent with the RD PSA terms and conditions? | July 2022 / Sept 2022 | RA Engagement Workshop |  |  | BPA provided a response in the July 26 2022 workshop and an updated response in the Sept 29 2022 decision meeting. Resource adequacy incentives would be included in the 2024 Power Rates Scedules and GRSPs with applicable billing determinant amounts. | X
97 | NRU | Cost Allocation/Rates | Suggest BPA review rate or cost structures for redundancies if BPA enters binding phase (would UAIs be redundant with penalties BPA may incur for same excess demand) and suggest rates and costs be addressed in BP-24 process. | July 2022 / Sept 2022 | RA Engagement Workshop |  |  | BPA provided a response in the July 26 2022 workshop and an updated response in the Sept 29 2022 decision meeting. Resource adequacy incentives would be included in the 2024 Power Rates Scedules and GRSPs with applicable billing determinant amounts. | X
77 | AWEC | Program Impacts | Substantial concerns given the unknowns regarding unspecified resource amounts and NLSLs and projected timeline of Fall 2022 for Phase 3B decision. | July 2022 | RA Engagement Workshop |  |  | BPA provided a response in the July 26, 2022 workhop. BPA’s proposals do not conflict with Regional Dialogue contracts and the customers’ ability to use Unspecified Resources, while balancing the capacity requirements of the WRAP, and creating a fair and equal treatment for those [BPA customers and other WRAP participants] who serve loads with specified resources. While it is true that BPA will evaluate whether to participate in the next phase of the WRAP in the Fall of 2022, the program design was done to allow for multiple non-binding seasons before participation becomes “binding." | X
78 | AWEC | Program Impacts | Suggests standing up a working group comprised of BPA, utilities that serve NLSLs, AWEC and any other organization with similar interests, and individual end-use consumers to resolve NLSL issues with a report out on possible options to the broader stakeholder group. | July 2022 | RA Engagement Workshop |  |  | BPA provided a response in the July 26 2022 workshop. BPA met with NLSL customers and AWEC prior to developing proposals to address the concerns around NLSL and AHWM loads using unspecified resources. At the June 13, 2022 workshop, BPA provided solution concepts on NLSL and AHWM loads using unspecified resources. BPA plans to continue working with customers the flesh out the proposals and how each option affects individual LF customers. | X
79 | AWEC | Program Impacts | Request for planning scenarios, similar to the April 13, 2022 workshop, for utilities serving above rate period high mark ("RHWM") loads and NLSLs with nonfederal, unspecified resource amounts to understand WRAP impacts on BPA's current processes. | July 2022 | RA Engagement Workshop |  |  | BPA provided a response in the July 26 2022 workshop. BPA will work with affected customers individually to identify specific requirements and needs associated with them. | X
80 | UEC | Program impacts | Does the FCRPS have adequate Qualifying Capacity Contribution during the Capacity Critical Hours for all of its LRE obligations including NLSL loads through the end of the Regional Dialogue Power Sales Agreement (RD PSA) term? Would you please provide this analysis? | July 2022 | RA Engagement Workshop |  |  | BPA provided a response in the July 26 2022 workshop. Initial indicative results show BPA has capacity to meet the projected need through the end of the RD contract period. BPA plans on sharing a summary of the values for the Winter Forward Showing 2022/23 data submittal at an upcoming public meeting. | X
81 | UEC | Program impacts | Can a customer choose to exclude only a portion of an NLSL load from BPA’s WRAP coverage? Are there specific criteria that must be met to exclude a portion of an NLSL load? | July 2022 | RA Engagement Workshop |  |  | BPA provided a response in the July 26, 2022 workshop. The concept of excluding a single discrete load is a WRAP concept, not within BPA’s discretion. The exclusion process is intended for individual discrete loads. For a NLSL to fit this description it would have to be the full discrete load. | X
82 | UEC | Program impacts | If an NLSL load is excluded from the BPA WRAP coverage, does the customer have any obligation(s) under the WRAP (e.g., to secure resources to support a share of Planning Reserve Margin for that excluded NLSL load or demonstrate transmission arrangements for load service, etc.)? | July 2022 | RA Engagement Workshop |  |  | BPA provided a response in the July 26 2022 workshop. Excluded load does not have WRAP resource QCC, PRM, transmission demonstration, or any other WRAP requirements. | X
83 | UEC | BPA Products and Services | If an NLSL load is excluded from the BPA WRAP coverage, will transmission curtailments and load excursions continue to be treated as they are currently by BPA (e.g., with NR ESS, TCMS, UAI penalties, etc.)? Will BPA’s participation in the WRAP change in any way the application or calculation of NR ESS, TCMS, UAI penalties, etc. If so, please explain. | July 2022 | RA Engagement Workshop |  |  | BPA provided a response in the July 26 2022 workshop. Best to our knowledge treatment and coverage of NLSL would not have any changes. | X
84 | UEC | BPA Products and Services | Is BPA contemplating a separate or different UAI charge for loads excluded from BPA’s WRAP coverage? If so, please explain. | July 2022 | RA Engagement Workshop |  |  | BPA provided a response in the July 26 2022 workshop. UAI charges would not change. | X
85 | UEC | Program impacts | If a customer chooses to exclude an NLSL load (or part of an NLSL load) from BPA WRAP coverage, can that decision be changed? If so, can this be done every rate case period? What would be the deadline for this decision? What are the conditions for these elections? | July 2022 | RA Engagement Workshop |  |  | BPA provided a response in the July 26 2022 workshop. The WRAP calculation cycle starts with the Advanced Assessment which is completed two years ahead of each season, the choice to exclude a load must be completed prior to that assessment, and cannot be changed for the specific binding season once modeled. | X
89 | UEC | Program impacts | Will BPA consider allowing NLSL and A-RHWM loads that are included in the BPA WRAP coverage to be served with unspecified resources without charges, credits, or lack of credits, at least through the term of the RD PSA? | July 2022 | RA Engagement Workshop |  |  | BPA provided a response in the July 26, 2022 workshop. Customers have the option of how they serve NLSL and AHWM loads. Customers who have chosen to secure firm physical resource to meet those needs should not be penalized (incurring additional costs) to support those who have made a decision to not acquire firm physical resource in advance. | X
91 | AWEC | Program impacts | On slide 37, BPA states that “[l]oads served by a single [load serving entity (“LSE”)] may not be partially excluded.” At this time, it is unclear from this statement what partial exclusion means. For example, if a customer has both NLSL and AHWM load, does the customer make a single determination on whether to include or exclude its entire load served by Unspecified Resource Amounts (regardless of whether NLSL or AHWM load)? Or can a customer choose to exclude NLSL, but include AWHM load (or vice versa)? If a customer were to have more than one NLSL, can it make a determination on an NLSL-by-NLSL basis, or is it an “all or nothing” decision (i.e., all in or all out)? Does BPA view itself as having discretion to make these determinations, or are these within the purview of WRAP design? | July 2022 | RA Engagement Workshop |  |  | BPA provided a response in the July 26, 2022 workshop. Only single line discrete loads can be excluded from WRAP's load exclusion process. By definition, a NLSL meets this requirement because it is an individually metered load that is specific and discrete. AHMM does not meet this. Load exclusion is subject to a mutally agreed upon attestion, yet to be developed by the WRAP. | X
92 | AWEC | Program impacts | Assuming that the above prohibition on partial exclusion would not prevent a customer from designating a subset of its load as excluded, it is unclear how a subset of load would be delineated. Is excluded load determined on a meter-by-meter basis? An end-user by end-user basis, regardless of whether some load may be NLSL and some AHWM? Would BPA make a determination on this issue, or would it be at the discretion of the customer? And similar to AWEC’s question above, does BPA view itself as having discretion to make these determinations, or are these within the purview of WRAP design? | July 2022 | RA Engagement Workshop |  |  | BPA provided a response in the July 26, 2022 workshop. Only single line discrete loads can be excluded from WRAP's load exclusion process. By definition, a NLSL meets this requirement because it is an individually metered load that is specific and discrete. AHMM does not meet this. Load exclusion is subject to a mutally agreed upon attestion, yet to be developed by the WRAP. | X
93 | AWEC | Program impacts | Could a customer exclude load for purposes of BPA's WRAP participation but participate in the WRAP for excluded loads on it's own? Implications with BPA, particularly related to credits or charges that could be associated with this decision? | July 2022 | RA Engagement Workshop |  |  | BPA provided a response in the July 26, 2022 workshop. Excluding a load is an exclusion of the load in WRAP. If the desire is for the load to be covered by WRAP, it should not be excluded and resource information needs to be provided for the Forward Showing data submital. | X
94 | NRU | Program impacts | Requests additional information regarding the approach and the impacts of customer's decision on customer options to include or exclude NLSLs as part of the load for which BPA is responsible under the WRAP. How would the choice related to treatment of the NLSL impact the future ability of customers to directly join in the WRAP for those specific loads? What other impacts does BPA see that may be important for customers to understand? | July 2022 | RA Engagement Workshop |  |  | BPA provided a response in the July 26, 2022 workshop. Excluding a load is an exclusion of the load in WRAP. If the desire is for the load to be covered by WRAP, it should not be excluded and resource information needs to be provided for the Forward Showing data submital. | X
95 | NRU | Program impacts | Determination of NLSL responsibility for the WRAP Planning Reserve Margin (“PRM”) must consider actual load characteristics which will likely lead to a smaller PRM obligation in comparison to other load types. (Context: NLSLs that are data centers typically have a very high load factor and are served with blocks of energy that exceed the actual demand with a small margin (e.g. 1-2 MWs). In contrast, most of the non-NLSL loads have diurnal shapes exhibiting high peaks and low load factors – weather dependency is highly correlated to these loads.) | July 2022 | RA Engagement Workshop |  |  | BPA provided a response in the July 26 2022 workshop. Specific load characteristics do not carry a specific PRM value. PRM calculated through WRAP. | X
96 | NRU | Program impacts | Seeks more information about how demand response resources (i.e., WRAP’s “Load Modification” and “Capacity Resources”) may factor into meeting BPA’s WRAP obligation. How BPA would utilize Load Modification and Capacity Resources during such events to meet its reliability requirements and support the region? | July 2022 | RA Engagement Workshop |  |  | BPA provided a response in the July 26 2022 workshop. WRAP spells out specifics on how demand response is counted in the WRAP. How resources would be deployed by BPA are yet to be determined but would need to follow defined rules for how they operate and be consisent with existing RD contracts. | X
76 | AWEC | Program Impacts | Regional Dialogue contract conflict with the WRAP Forward Showing requirements because known sources do not need to be identified until pre-schedule. Concerned WRAP will create potential capacity costs that will get passed to the NLSL. | June 2022 / July 2022 | RA Engagement Workshop |  |  | BPA developed presentations and provided a response in the June 13, 2022 and July 26, 2022 workhops. BPA shared soluton concepts to address the conflicintg requirements while honoring the Regional Dialogue contracts. | X
4 | AWEC | Program Impacts | IPPs should be allowed to meet the requirements for the NLSLs they serve if a COU has contracted with them to meet the NLSL energy needs, rather than service from BPA at an NR Rate | June 2022 | RA Engagement Workshop | BPA NLSL operational treatment |  | BPA provided a response in the June 13 2022 workshop. BPA agrees. Under WRAP, resources serving load must be a physical resource or a power supply contract (traceable to a physical resource) and be provided during the FS timeframe. | X
18 | PPC | BPA Products and Services | Will BPA be providing new products to help facilitate the program? | June 2022 | RA Engagement Workshop |  |  | BPA provided a response in the June 13 2022 workshop. Customers are encouraged to interface with the marketplace for products. BPA is not considering new RD products. If BPA joins binding phase, future product offerings would be addressed through the Provider of Choice process. | X
37 | PPC | Program Impacts - Transmission | What type of reporting will be made available on the use of BPA’s transmission related to the WRAP? | June 2022 | RA Engagement Workshop |  |  | BPA provided a response in the June 13 2022 workshop. WPP will not be issuing any reports. | X
57 | WPAG | Program Impacts - Transmission | What impact will the seven month forward showing have on the reservation and scheduling deadlines that the region currently relies upon? | June 2022 | RA Engagement Workshop |  |  | BPA provided a response in the June 13 2022 workshop. No expected changes to BPA's Tariff and Business Practices. | X
58 | WPAG | Program Impacts - Transmission | Will BPA’s NT customers be allowed to identify the centroid point of receipt as a Designated Network Resource for purposes of receiving RA program provided energy when they are deficient? What if, as is likely, an NT customer cannot identify the control area(s) from which such power will originate at the time of the attempted designation (which was the downfall of BPA’s short-lived seller’s choice option for NT customers)? Does the answer to this question depend on whether the transmission customer is also a BPA power customer and/or, specifically, a load following or slice/block customer of BPA? | June 2022 | RA Engagement Workshop | Transmission questions should be worked through before addressing this |  | BPA provided a response in the June 13 2022 workshop. NT customers who are participating in WRAP and are deficit may use 6NN from the Centroid/Hub to their load to receive energy deployment and PTP customers may use PTP transmission to move their energy deployment from the Centroid/Hub or directly from another Participant. | X
59 | WPAG | Program Impacts - Transmission | Will BPA’s NT customers participating in the RA program be able to identify the centroid point of delivery as a Designated Network Load for purposes of meeting its energy delivery obligations under the program when it is surplus and another program participant is deficient? Or, will such a customer be required to use point-to-point transmission for such purposes? | June 2022 | RA Engagement Workshop | Transmission questions should be worked through before addressing this |  | BPA provided a response in the June 13 2022 workshop. An NT customer who is participating in WRAP must use PTP to deliver surplus under the program. | X
63 | WPAG | Program Implementation - Transmission | Does BPA expect to have short-term preemption and competition fully implemented (including in the hourly and daily timeframes) prior to the first operational season under the program? Will BPA respect and continue to implement such preemption rights during RA sharing events once the program goes live? | June 2022 | RA Engagement Workshop | PCM implementation timeline for hourly implementation. |  | BPA provided a response in the June 13 2022 workshop. To date, BPA has implemented PCM for all short-term products except hourly, including redirects. BPA is currently working to implement PCM for hourly firm products and it will be implemented by WRAP’s first operational season. | X
66 | PPC | Program Impacts - Transmission | How will new long-term transmission requests intended to support the program be studied since they would be going to Mid-C (given current restrictions on hubbing requests in long-term studies)? | June 2022 | RA Engagement Workshop |  |  | BPA provided a response in the June 13 2022 workshop. There are no changes expected to BPA’s Tariff and Business Practices, including our NT policies and procedures. | X
67 | PPC | Program Impacts - Transmission | What will the process be for entities redirecting their existing transmission rights to the centroid? | June 2022 | RA Engagement Workshop |  |  | BPA provided a response in the June 13 2022 workshop. No expected changes to BPA's Tariff and Business Practices. | X
68 | PPC | Program Impacts - Transmission | Will the centroid be used for all transmission rights used to demonstrate adequacy under the program? Or only for generation that is made available to others during the operational showing period? | June 2022 | RA Engagement Workshop |  |  | BPA provided a response in the June 13 2022 workshop. The centroid hub is only designed for delivery of the holdback obligation. Participants can continue under bilateral arrangements today to faciliate delivery. | X
7 | NWEC | Program Impacts | 7-month deadline for FS may not be able to accommodate the variability of hydro availability | April 2022 / June 2022 | RA Engagement Workshop |  |  | BPA provided a response in the April 13 and June 13 2022 workshops. WRAP's QCC methodology for storage hydro takes into account the unique characteristics of storage hydro. | X
8 | PPC | Program Impacts | How do the reserves that BPA is currently holding out for its products compare to the Planning Reserve Margin that is required under the RA program? Will this difference result in any changes to the amount of capacity that BPA holds as reserves? | April 2022 / June 2022 | RA Engagement Workshop |  |  | BPA provided a response in the April 13 and June 13 2022 workshops. BR and CR required of BA are different from the PRM required for participants in WRAP. WRAP does not change the capacity BPA BAA holds for both BR and CR. | X
19 | PPC | BPA Products and Services | How will the requirement to “hold out” capacity for others in the program impact BPA’s ability to make secondary sales? How is this mitigated through payments from the WRAP? | April 2022 / June 2022 | RA Engagement Workshop, Closeout letter | Understanding of BPA Planning with WRAP |  | BPA provided a response in the April 13 and June 13 2022 workshops. Premature to answer impact to secondary sales. BPA provided "BPA Planning with WRAP" and "Planning Scenarios and Preference Rights" presentations to WRAP obligations. | X
36 | PPC | Program Impacts | Wants to explore with BPA “what would happen today” vs. “in the RA program” under various scenarios | April 2022 / June 2022 | RA Engagement Workshop | Understanding of BPA Planning with WRAP (including scenarios) |  | BPA provided a response in the April 13 and June 13 2022 workshops. At the April 13 2022 workshop, BPA provided "BPA Planning with WRAP" presentation and "Planning Scenarios and Preference Rights" presentations to explain BPA's planning process and how it may or may not be impacted by WRAP. | X
41 | PPC | Legal | What specific contract language provides BPA the authority to participate in the RA program? | April 2022 / June 2022 | RA Engagement Workshop |  |  | BPA provided a response in the April 13 and June 13 2022 workshops. BPA’s authority to participate in the WRAP arises under section 11(b)(6)(i) of the Transmission System Act of 1974, which grants the Administrator authority to acquire power on a short-term basis (5 years and less). WRAP is another tool for helping to assure the Administrator has an adequate and reliable supply of power to meet his firm contractual obligations. | X
45 | SNO | Program Impacts | Needs common understanding of how BPA plans on a forward basis to meet its peak loads today, including the reserve margin BPA applies to the forecasted peaks. (baseline to allow customers to judge if RA program is an improvement over BPA status quo) | April 2022 / June 2022 | RA Engagement Workshop | BPA Planning with WRAP (including scenarios) |  | BPA provided a response in the April 13 and June 13 2022 workshops. At the April 13 2022 workshop, BPA provided "BPA Planning with WRAP" presentation and "Planning Scenarios and Preference Rights" presentations to explain BPA's planning process and how it may or may not be impacted by WRAP. | X
47 | WPAG | Program Impacts | Would BPA (and its load-following customers) be better off if BPA simply sold excess capacity to others in the RA program without being a load-responsible entity itself? Would this be a better business case for BPA given that (i) it does not plan on changing its own planning criteria and (ii) it would allow BPA to avoid the risk of penalties but still reap capacity sales revenues? | April 2022 / June 2022 | RA Engagement Workshop | BPA Planning with WRAP (including scenarios) |  | BPA provided a response in the April 13 and June 13 2022 workshops. WRAP would be another tool in the "toolbox" to meet BPA's long-term sales contract obligations. WRAP participation does not create incremental MWs to the FCRPS. BPA must understand current or expected, fuel constraints to evaluate its marketing situation. | X
53 | WPAG | Program Impacts | What happens if there simply is not sufficient physical capacity in the region to meet the forward showing obligations of all RA participants when the binding phase of the RA program begins? Would the RA program still impose penalties even though it is not possible to comply? Would BPA still pay them? | April 2022 / June 2022 | RA Engagement Workshop | Finalized program design. May be language in the design doc on this. CONE Penalty proposal (posted) |  | BPA provided a response in the April 13 and June 13 2022 workshops. WRAP must be workable for all participants and not intended to set up participants to fail. CONE charge is adopted only under certain conditions, including ability to procure capacity to pass the Forward Showing. | X
54 | WPAG | Program Impacts | The RA program’s PRM is based on a coincident peak, yet the program then applies that PRM to each individual entity’s non-coincident peak. Is this a standard design among similar programs? If not, does it reduce the purported benefits of a region-wide RA construct? | April 2022 / June 2022 | RA Engagement Workshop | Explanation in Design Document (Section 2.2.2 and Appendix C) |  | BPA provided a response in the April 13 and June 13 2022 workshops. WRAP methodology maintains and unlocks diversity from the full footprint and established the regional capacity requirement needed to meet the reliability metric. Other programs use a variety of approaches but include some relationship between them in order to maximize diversity and allocate it to individual participants. | X
56 | WPAG | Legal | How will BPA preserve the rights and obligations of both BPA and its customers under the Regional Dialogue contracts when such rights and/or obligations may conflict with the requirements of the RA program? | April 2022 / June 2022 | RA Engagement Workshop | BPA Planning with WRAP (including scenarios) |  | BPA provided a response in the April 13 and June 13 2022 workshops. BPA will continue to meet its existing contractual obligations. | X
70 | WPAG | Program Impacts | Requests that BPA explore through a public forum the relationship between program-qualified capacity and the capacity needed to meet its P10 Heavy Load Hour planning criteria | April 2022 / June 2022 | RA Engagement Workshop | BPA Planning in Wrap (Scenarios) |  | BPA provided a response in the April 13 and June 13 2022 workshops. At the April 13 2022 workshop, BPA provided "BPA Planning with WRAP" presentation and "Planning Scenarios and Preference Rights" presentations to explain BPA's planning process and how it may or may not be impacted by WRAP. | X
71 | WPAG | Program Impacts | Assuming BPA does not become a load responsible entity in the WRAP, how much excess capacity could BPA potentially sell to other load responsible entities in the WRAP while still meeting its current planning criteria? | April 2022 / June 2022 | RA Engagement Workshop | BPA Planning with WRAP (including scenarios) |  | BPA provided a response in the April 13 and June 13 2022 workshops. WRAP would be another tool in the "toolbox" to meet BPA's long-term sales contract obligations. WRAP participation does not create incremental MWs to the FCRPS. BPA must understand current or expected, fuel constraints to evaluate its marketing situation. | X
72 | WPAG | Program Impacts | Assuming BPA does become a load responsible entity in the WRAP, does BPA plan to relax its current planning criteria to reduce capacity planning charges or create excess capacity to sell to other load responsible entities in the WRAP? | April 2022 / June 2022 | RA Engagement Workshop, Closeout letter | Tied to item #73 BPA Planning with WRAP (including scenarios) |  | BPA provided a response in the April 13 and June 13 2022 workshops. Premature to answer impact to secondary sales. BPA provided "BPA Planning with WRAP" and "Planning Scenarios and Preference Rights" presentations to WRAP obligations. | X
73 | WPAG | Program Impacts | How much can BPA reliably relax its current planning criteria and how much excess capacity would this create for BPA to sell (subject to its preference obligations) to load responsible entities in the WRAP? How much net revenue would result? | April 2022 / June 2022 | RA Engagement Workshop, Closeout letter | Tied to item #72 BPA Planning with WRAP (including scenarios) |  | BPA provided a response in the April 13 and June 13 2022 workshops. Premature to answer impact to secondary sales. BPA provided "BPA Planning with WRAP" and "Planning Scenarios and Preference Rights" presentations to WRAP obligations. | X
74 | WPAG | Program Impacts | Assuming BPA does become a load responsible entity and does not plan to relax its existing planning criteria, how much WRAP qualified capacity does BPA anticipate it will have in excess of program requirements that it will not need to meet its other planning criteria? | April 2022 / June 2022 | RA Engagement Workshop | BPA Planning with WRAP (including scenarios) |  | BPA provided a response in the April 13 and June 13 2022 workshops. At the April 13 2022 workshop, BPA provided "BPA Planning with WRAP" presentation and "Planning Scenarios and Preference Rights" presentations to explain a decision to join the WRAP would not change the way in which BPA conducts marketing activities. | X
75 | WPAG | Program Impacts | How will BPA’s methodology and timeline(s) for making surplus capacity and energy available first to preference customers interact with the forward showing and operational timelines and requirements under the program? | April 2022 / June 2022 | RA Engagement Workshop | BPA Planning with WRAP (including scenarios) |  | BPA provided a response in the April 13 and June 13 2022 workshops. At the April 13 2022 workshop, BPA provided "BPA Planning with WRAP" presentation and "Planning Scenarios and Preference Rights" presentations to explain a decision to join the WRAP would not change the way in which BPA conducts marketing activities. | X
64 | WPAG | Legal | How will BPA respect statutory preference rights in both the forward and operational timeframes while simultaneously meeting its commitments in the program? | January 2022 / April 2022 / June 2022 | RA Engagement Workshop | BPA Planning with WRAP (including scenarios) |  | BPA provided a response at the January 27, April 13, and June 13 2022 workshops. BPA does not need to change its current process to statutory preference rights. | X
9 | NWEC | Program Implementation | Consider how customer-side resources (energy efficiency, demand response, distributed generation, storage) can contribute to the program | January 2022 | RA Engagement Workshop |  |  | BPA provided a response in the Jan 27 2022 workshop. WRAP allows customer resources to participate. See WRAP detailed design document. | X
40 | PPC | Legal | Would participation in a FERC jurisdictional program expand FERC’s jurisdiction over any existing BPA rates or products? What are some of the key considerations for BPA in determining whether a FERC jurisdictional program would work for the agency? | January 2022 | RA Engagement Workshop |  |  | BPA provided a response in the Jan 27 2022 workshop. BPA firm power sales and rates (both power and transmission) set by process set in the NW Power Act. FERC has limited authority review of BPA rates. Changes to Tariff governed by tariff proceeding meeting requirements in Section 9 of BPA OATT. | X
65 | PPC | Program Implementation | Seeking Clarification on BPA's response to item #32: Can BPA please clarify what is meant by the statement "BPA does not represent any additional parties" [on slide 18 of Nov. 19 presentation regarding RAPC participation]? In addition to BPA itself? In addition to BPA's preference or load following customers? | N/A | WRAP Public Considerations Tracking Spreadsheet |  |  | BPA’s interest in participation is based on BPA’s obligation to supply power (energy and capacity). BPA does not represent or act on behalf of any other legal entity. | X
10 | SNO | Cost Allocation/Rates | Cost allocation should be equitable to all customers and any rate construct limitations should be clearly discussed and understood what would be needed to resolve them | November 2021 | RA Engagement Workshop |  |  | BPA provided a response in the Nov 19 2021 workshop. BPA follows applicable rate directives. | X
14 | PPC | Program Impacts | What is the problem statement for the WRAP? | November 2021 | RA Engagement Workshop |  |  | BPA provided direction on where to locate the WRAP problem statement in the Nov 19 2021 workshop. | X
22 | PPC | BPA Products and Services - Transmission | How will use of transmission in the program impact existing BPA transmission contracts? | November 2021 | RA Engagement Workshop |  |  | BPA provided a response in the Nov 19 2021 workshop. The program will not impact existing contracts. | X
26 | PPC | Stakeholder Engagement | Public stakeholder process needs to occur as new information becomes available, and should begin now. Work with public to address concerns upfront in the program design. | November 2021 | RA Engagement Workshop |  |  | BPA proposed a public engagement process in the Nov 19 2021 workshop which aligns with the timing of information availability. | X
27 | PPC | Stakeholder Engagement | Where would BPA capture its commitment to participation and associated responsibilities? | November 2021 | RA Engagement Workshop |  |  | BPA stated in the Nov 19 2021 workshop that information will be captured through workshops/materials, this tracking sheet, and/or 3B participation decision document. | X
28 | PPC | Stakeholder Engagement | How will BPA keep customers apprised of costs/benefits of the RA program on an ongoing basis? | November 2021 | RA Engagement Workshop |  |  | BPA proposed a public engagement process in the Nov 19 2021 workshop which includes ongoing engagement. | X
30 | NWEC | Program Implementation | Alignment of WRAP with other regional initiatives | November 2021 | RA Engagement Workshop |  |  | BPA provided a response in the Nov 19 2021 workshop. Alignment depends on the other initiatives, and BPA engages with the intent of pursuing alignment. | X
31 | PPC | Stakeholder Engagement | Request for “Customer Impact Summary” similar to EIM engagement plan. | November 2021 | RA Engagement Workshop |  |  | BPA proposed a public engagement process in the Nov 19 2021 workshop which includes mechanisms for impact transparency, including this tracking sheet. | X
32 | PPC | Program Implementation | How does BPA see its role as a member of the RA Participants Committee (RAPC) and what constituencies is BPA representing in this role? What process will BPA have for representing these constituencies on the RAPC? | November 2021 | RA Engagement Workshop |  |  | BPA provided a response in the Nov 19 2021 workshop. BPA does not represent any additional parties; BPA will evaluate whether the WRAP may, if implemented, assist BPA in meeting BPA’s existing and future obligations to supply power. | X
38 | PPC | Program Impacts - Transmission | Demonstrate that there are no negative impacts to the quality of transmission service it provides its customers | November 2021 | RA Engagement Workshop |  |  | BPA provided a response in the Nov 19 2021 workshop. The program does not change BPA's commitment and obligation to operate a reliable transmission system. | X
42 | PPC | Transmission Planning | How will use of transmission in the program impact BPA’s transmission planning and operations - particularly if a trading hub or node is used to schedule capacity available to the program? Does this differ on a day-ahead and real-time basis from impacts on a long-term basis? | November 2021 | RA Engagement Workshop |  |  | BPA provided a response in the Nov 19 2021 workshop. The program will provide situational awareness. | X
43 | PPC | Transmission Planning | Is the use of transmission to facilitate the program expected to trigger new transmission builds? How will costs be allocated if this occurs? | November 2021 | RA Engagement Workshop |  |  | BPA provided a response in the Nov 19 2021 workshop. Data on seasonality has the potential to be a tool to help with mid-term and long-term regional planning. | X
44 | NWEC | Legal | Program participation should be compatible with BPA's existing power and transmission contractual requirements and also with statutory obligations including protection of fish and wildlife. | November 2021 | RA Engagement Workshop and Closeout Letter | Finalized program design |  | BPA provided a response in the Nov 19 2021 workshop. This is a foundational principle for BPA participation in the program. | X
48 | WPAG | Stakeholder Engagement | BPA should scope with customers immediately following 3A implementation agreement signing questions needing to be addressed and scheduling workshops | November 2021 | RA Engagement Workshop |  |  | BPA proposed a public engagement process in the Nov 19 2021 workshop which addresses initial scoping and the plan for ongoing scoping of topics. | X
49 | WPAG | Stakeholder Engagement | BPA should include a draft scope for stakeholder engagement, and include all open questions raised by customers in this process | November 2021 | RA Engagement Workshop |  |  | BPA proposed a public engagement process in the Nov 19 2021 workshop which addresses initial scoping. All submitted comments can be located on BPA's resource adequacy website. | X
60 | WPAG | Program Impacts - Transmission | Will BPA’s existing transmission customers see increased congestion, curtailment, and NT Redispatch risk and/or costs arising from the location of the RA centroid at Mid-C? | November 2021 | RA Engagement Workshop |  |  | BPA provided a response in the Nov 19 2021 workshop. These impacts are not expected to occur as designed. | X
61 | WPAG | Program Impacts - Transmission | What impact will the location of the RA centroid at Mid-C have on BPA’s implementation of limited hourly firm under the TC-20 Settlement Agreement? | November 2021 | RA Engagement Workshop |  |  | BPA provided a response in the Nov 19 2021 workshop. The program does not change current scheduling practices, reservation rights in place, or TC-20 settlement obligations. | X
62 | WPAG | Program Impacts - Transmission | Does BPA anticipate that it will need to expand the capacity of its transmission system, or relax the current operating limits placed on the existing system, to ensure the success of the RA program and/or meet increased demand placed on the system due to the program? | November 2021 | RA Engagement Workshop |  |  | BPA provided a response in the Nov 19 2021 workshop. The program will not change how transmission is provided, operated, or how operating limits are set. | X
2 | AWEC | Logistics | Proposed timing of 3B decision and implementation is concerning without a rate case to flesh out rate impacts/cost allocation | Fall 2021 | 3A Final Decision Letter |  |  | BPA addressed in response to comments section (#9) in the final decision document. Rate case prior to 3B decision should not be needed. | X
3 | AWEC | Logistics | BPA should commit to potentially conducting a mini-7(i) process during BP-22 rate period prior to issuing a final decision on Phase 3B participation. | Fall 2021 | 3A Final Decision Letter |  |  | BPA addressed in response to comments (#8) in the final decision document. BPA is not conducting mini-7(i) process. | X
5 | NRU | Cost Allocation/Rates | All initial program costs and benefits should accrue to LF customers. Non-slice cost pool may be the appropriate place in the near term. Consider cost and benefit pool for LF customers only for post-2028. | Fall 2021 | 3A Final Decision Letter |  |  | BPA addressed in response to comments section (#7) in the final decision document. BPA agrees with the statement made. | X
6 | NRU | Program Implementation | Governance structure should be refined so that BPA Load Following customers have a guaranteed voice (within the Program Review Committee) to state their interests in program operation (as they cannot adequately be represented by any other entity, including BPA | Fall 2021 | 3A Final Decision Letter |  |  | BPA provided a response to comment (#5) on governance participation - final governance structure is not within BPA's control | X
20 | PPC | BPA Products and Services | Has BPA studied the impacts of participating in the program post 2028? Would BPA have sufficient capacity to cover its obligations under the program if all customers change to the load-following product? | Fall 2021 | 3A Final Decision Letter |  |  | BPA addressed this in comments (#11) section of the final decision document. Bonneville has a very broad power marketing mandate that directs Bonneville to meet its firm power customer needs, which is impartial to the product type chosen by preference customers. | X
29 | PPC | Logistics | BPA should take a strategic approach to evaluating markets and regional programs by evaluating all against developed principles and philosophies (PPC’s were included) | Fall 2021 | 3A Final Decision Letter |  |  | BPA addressed in response to comments section (#2) in the final decision document. BPA reiterated principles for program evaluation | X
33 | PPC | Program Impacts | BPA participating in 3A as a means to gain more information about design and implementation, and impacts to BPA customers, contracts, products, and rates. | Fall 2021 | 3A Final Decision Letter |  |  | BPA agreed with this statement in the final decision letter | X
34 | PPC | Program Impacts | BPA must commit to working with customers to resolve these questions in advance of taking on any binding obligations related to the program | Fall 2021 | 3A Final Decision Letter |  |  | BPA explictly responded to this request in comment (#1) in the final decision document. We will not commit to resolving specific questions. | X
35 | PPC | Program Impacts | Are there any circumstances, either in the planning or operational stages, where, by virtue of participating in the RA program, a non-preference customer would have access to the Federal system capacity before a preference customer, or would be allocated a share of that capacity pro rata? Why or why not? | Fall 2021 | 3A Final Decision Letter |  |  | BPA addressed in response to comments (#4) in the final decision document. Order of preference will not be impacted by the program | X
39 | PPC | Program Implementation | Does BPA have the legal authority to pay penalties or fines associated with its participation in WRAP and would it require any waiver of sovereign immunity? | Fall 2021 | 3A Final Decision Letter |  |  | BPA addressed in response to comments (#12) in the final decision document. BPA cannot pay penalties, so any penalty structure would need a BPA waiver | X
46 | SNO | Legal | Understand how BPA is meeting its statutory and contractual obligations by participating, including preference rights of customers to energy and capacity | Fall 2021 | 3A Final Decision Letter |  |  | BPA addressed in response to comments (#10) in the final decision document. | X
50 | WPAG | Logistics | Timeline for final decision on binding phase 3B by fall/winter 2022 may prove difficult to meet | Fall 2021 | 3A Final Decision Letter |  |  | BPA addressed in response to comments (#9) in the final decision document. Bound by WRAP timelines | X
52 | WPAG | Program Implementation | Make explicit that BPA fully reserves the right to not join the binding program in the event it determines doing so will not meet BPA’s RA principles | Fall 2021 | 3A Final Decision Letter |  |  | BPA made this statement in 3A decision letter | X
55 | WPAG | Program Implementation | Does BPA have the legal authority to agree by contract to pay a penalty when deemed deficient by the RA Program Operator or would such an agreement be an unlawful waiver of the federal government’s sovereign immunity? See, e.g., Southwestern Power Administration vs. F.E.R.C., 763 F.3d 27 (D.C. Circuit 2014) (holding that the Federal Power Act did not effect an unequivocal waiver of federal government’s sovereign immunity from monetary penalties). | Fall 2021 | 3A Final Decision Letter |  |  | BPA addressed in response to comments (#12) in the final decision document. BPA cannot pay penalties, so any penalty structure would need a BPA waiver | X