## Request List
Row | Request# | CAISO# | Start | End | Main Element Impacted | Path Affected
1 | 21-01711 | 9741845 | 02/03/2021 09:00 | 02/28/2023 17:00 | -USBR- GRAND COULEE 287/230KV TRANSFORMER KX-17-A (OLYMPIA-GRAND COULEE NO 1 287KV LINE OPERATING AT 230KV) | NOEL, PA, RP, SOC, WOCN, IROL, NOH, OKLA
2 | 21-01577 |  | 02/28/2021 06:00 | 09/02/2022 16:00 | -AVA- NORTH LEWISTON: 230/115KV TRANSFORMER
3 | 21-01581 |  | 04/30/2021 16:15 | 03/31/2023 18:00 | BCH - BURRARD SYNCHRONOUS CONDENSER STATION G2 | BCHT, BCHW, NI
4 | 21-01767 | 10359382 | 06/30/2021 10:00 | 02/03/2023 16:00 | PAUL: 4805 TERMINAL OF PAUL-PSE TONO NO 1 500KV LINE | LOAD, RP, SIG, PA
5 | 21-01781 | 10627274 | 08/25/2021 12:00 | 08/31/2022 23:59 | SATSOP: 500/230KV TRANSFORMER 1 (DERATED) | PA, RP, LOAD
6 | 21-01779 | 10627252 | 08/25/2021 12:00 | 08/31/2022 23:59 | CUSTER: 500/230KV TRANSFORMER 2 (DERATED) | NOEL, SIG, SOC, NI
7 | 21-01784 | 11699929 | 08/25/2021 12:00 | 12/31/2022 23:59 | GARRISON: 500/230KV TRANSFORMER 1 (DERATED) | MT-NW
8 | 21-01773 | 10627358 | 08/25/2021 12:00 | 09/29/2022 23:59 | MAPLE VALLEY: 500/230KV TRANSFORMER 2 (DERATED) | IROL, NOEL, SIG, SOC, WOCN
9 | 21-01797 | 10627354 | 08/25/2021 12:00 | 09/29/2022 23:59 | MCNARY: 500/230KV TRANSFORMER 2 (DERATED) | COI, PDCI, SIG, WOJD, WOM, NWACI
10 | 22-03687 |  | 01/25/2022 19:08 | 01/31/2023 23:59 | AVA MOSCOW 230/115KV TRANSFORMER OOS
11 | 22-06746 | 11593785 | 04/06/2022 06:30 | 12/30/2022 15:00 | CONKELLEY: LBD A-1575 INCLUDING 230KV CAP GROUP 2 SECTION 1 | MT-NW
12 | 22-06836 | 11597875 | 04/06/2022 12:25 | 12/31/2022 15:00 | OSTRANDER-TROUTDALE 1 500KV LINE INCLUDING TROUTDALE: 500/230KV TRANSFORMER BANK 8 | SIG, SOA, WOCS, SIG, WOCS, SOA
13 | 22-08527 | 11756807 | 06/01/2022 00:00 | 10/31/2022 23:59 | HAT ROCK TAP TO MCNARY-PACW WALLULA NO 1 230KV LINE | WOM
14 | 22-09321 | 11837919 | 06/01/2022 00:00 | 10/31/2022 23:59 | SACHEEN-DAY MT SPOKANE SECTION OF SACHEEN-BELL NO 1 230KV LINE, DAY MT SPOKANE-BELL SECTION OF SACHEEN-BELL NO 1 230KV LINE, (DERATED) | SOB, SOB
15 | 22-09334 | 11838131 | 06/01/2022 00:00 | 10/31/2022 23:59 | BIG EDDY-MAUPIN NO 1 230KV LINE, (DERATE)
16 | 22-09335 | 11838145 | 06/01/2022 00:00 | 10/31/2022 23:59 | MAUPIN-REDMOND NO 1 230KV LINE, (DERATE)
17 | 22-08395 | 11739865 | 06/01/2022 00:00 | 10/31/2022 23:59 | BOUNDARY-SACHEEN NO 1 230KV LINE
18 | 22-01027 | 11164008 | 06/01/2022 00:01 | 10/31/2022 23:59 | RIVERGATE-KEELER NO 1&2 230KV LINE (SUMMER DERATE) | SOA
19 | 22-07562 | 11662150 | 06/01/2022 00:01 | 10/31/2022 23:59 | COVINGTON: 500/230KV TRANSFORMER 5, DERATED | NOEL, RP, SIG, SOC, NI, WOCN
20 | 22-07563 | 11662212 | 06/01/2022 00:01 | 10/31/2022 23:59 | COVINGTON: 500/230KV TRANSFORMER 4, DERATED | NOEL, RP, SIG, SOC, NI, WOCN
21 | 22-00990 | 11156884 | 06/27/2022 18:00 | 08/18/2022 07:00 | HANFORD: PCB 4089 INCLUDING MODS 4088 & 4090 | NOH, NWACI, PDCI, COI, WOM, WOS
22 | 22-02600 | 11058752 | 07/05/2022 05:30 | 10/28/2022 15:00 | -USBR- HUNGRY HORSE PH: PCB 2382, PCB 2282 | WOH, WOH
23 | 22-06144 | 9826915 | 07/05/2022 09:00 | 09/02/2022 15:30 | PAC- MERIDIAN 500KV SERIES CAP GROUP 1 | COI, NWACI/PDCI
24 | 22-10319 | 11976164 | 07/11/2022 08:00 | 12/31/2022 15:00 | B-1518 TERMINAL OF THE UNDERWOOD TAP TO BONNEVILLE PH1-ALCOA NO 1&2 115 KV LINE
25 | 22-02718 | 11176154 | 07/15/2022 07:30 | 11/17/2022 12:00 | HILLS CREEK-OAKRIDGE SECTION OF HILLS CREEK-LOOKOUT POINT NO 1 115KV LINE
26 | 22-09999 | 11976188 | 07/18/2022 08:00 | 08/12/2022 15:00 | -COWLITZ- MEEKER-NORTH WOODLAND 115KV LINE | LOAD, SOA
27 | 22-04985 | 11412504 | 07/18/2022 15:00 | 08/05/2022 17:00 | BONNEVILLE PH 2-NORTH BONNEVILLE NO 3 230KV LINE | GEN, FCRPS, WOCS, WOCS
28 | 22-04983 | 11428362 | 07/25/2022 07:00 | 08/04/2022 16:00 | JOHN DAY: 4165/4166 TERMINAL OF JOHN DAY PH-JOHN DAY NO 3 500KV LINE | GEN, NWACI, COI, FCRPS, PDCI, SIG, WOJD
29 | 22-02401 | 11100119 | 07/25/2022 08:00 | 08/04/2022 16:30 | TAHKENITCH-REEDSPORT NO 1 115KV LINE | SWORE, LOAD
30 | 22-01038 | 11300476 | 07/25/2022 09:30 | 08/04/2022 14:00 | CAPTAIN JACK: PCB 4998 INCLUDING 500KV REACTOR 1 | COI, NWACI, PDCI, COI, NWACI, PDCI
31 | 22-02794 | 11120751 | 08/01/2022 03:00 | 08/05/2022 17:00 | GRAND COULEE: PCB 2392 | GEN, NOH, WOCN, COI, NWACI, PDCI
32 | 22-07858 | 11837353 | 08/01/2022 06:30 | 08/04/2022 16:30 | MCNARY: 230/115KV BANK # 9 INCLUDING PCB'S A-440, B-978 AND PCB 1W | WOM
33 | 22-00845 | 11131003 | 08/01/2022 07:00 | 08/12/2022 16:00 | ADDY-BOUNDARY SECTION OF BELL-BOUNDARY NO 3 230KV LINE | SOB, GEN, SOB, SOB
34 | 22-00846 | 11131005 | 08/01/2022 07:00 | 08/12/2022 16:00 | COLVILLE-SPIRIT SECTION OF COLVILLE-BOUNDARY NO 1 115KV LINE | SOB
35 | 22-01911 | 10699638 | 08/01/2022 07:00 | 09/16/2022 15:30 | MCNARY-ROSS NO 1 345KV LINE, MCNARY: 345/230KV TRANSFORMER 8, ROSS: 345/230KV TRANSFORMER 4 | SOA, WOCS, WOM, GEN, SOA, WOCS, WOM, SIG, SOA, WOCS, WOM, SOA, WOCS, WOM, SOA, WOCS
36 | 22-04056 | 11369332 | 08/01/2022 07:00 | 08/02/2022 16:00 | RAVER: PCB 4858 | NOEL, RP, SOC
37 | 22-02654 | 11108507 | 08/01/2022 07:00 | 08/02/2022 16:00 | GARRISON: PCB 4457 INCLUDING 500KV REACTOR 4 | MT-NW, MT-NW
38 | 22-02126 | 11080923 | 08/01/2022 07:00 | 08/11/2022 12:00 | MCNARY: 500/230KV TRANSFORMER 1 | COI, GEN, PDCI, SIG, WOJD, WOM, NWACI
39 | 22-00841 | 11136698 | 08/01/2022 07:00 | 08/03/2022 15:00 | CHIEF JOSEPH: PCB 4588 | BCHT, BCHW, GEN, NOH, NWACI, PDCI, WOCN, COI
40 | 22-03061 | 11210987 | 08/01/2022 07:30 | 08/21/2022 16:00 | COVINGTON-BETTAS ROAD 1 230KV LINE, COVINGTON-BETTAS ROAD NO 1 230KV LINE | NOEL, SOC, WOCN, IROL
41 | 22-02472 | 11025107 | 08/01/2022 07:30 | 08/02/2022 15:00 | RAVER: PCB 4914 | NOEL, RP, SOC
42 | 22-02605 | 11059907 | 08/01/2022 07:30 | 08/21/2022 16:00 | OLYMPIA-GRAND COULEE NO 1 287KV LINE, OLYMPIA: 287/230KV TRANSFORMER 3 | NOEL, NOH, RP, SOC, WOCN, IROL, NOEL, PA, RP, SOC, WOCN, IROL
43 | 22-07312 | 11976192 | 08/01/2022 07:30 | 08/25/2022 17:00 | LONGVIEW: 115KV M/B SECTION BETWEEN B-392 AND B-394 DISCONNECTS INCLUDING PCB B-330 AND THE 115KV A/B
44 | 22-08771 | 11791066 | 08/01/2022 08:00 | 08/04/2022 17:00 | PARKDALE-TROUTDALE SECTION OF BIG EDDY-TROUTDALE NO 1 230KV LINE | WOCS, WOJD
45 | 22-01289 | 11976192 | 08/01/2022 08:00 | 08/25/2022 17:00 | WREN-TOLEDO SECTION OF SANTIAM-TOLEDO NO 1 230KV LINE INCLUDING TOLEDO: PCB A-1472 | SWORE, LOAD, LOAD
46 | 22-02403 | 11013345 | 08/01/2022 08:00 | 08/04/2022 16:30 | NORWAY-MORRISON SECTION OF FAIRVIEW-BANDON NO 1 115KV LINE | SWORE
47 | 22-09106 | 11821598 | 08/01/2022 08:00 | 08/04/2022 16:00 | ADDY: 115KV NORTH MAIN BUS AND SOUTH MAIN BUS | SOB, SOB, SOB
48 | 22-08299 | 11798575 | 08/01/2022 08:00 | 08/04/2022 15:00 | CELILO: BIG EDDY 1 500KV LINE CAP GROUP 3 (PCB 5511) | PDCI
49 | 22-01169 | 9309407 | 08/01/2022 08:00 | 08/05/2022 16:00 | LEXINGTON: 230/115KV TRANSFORMER 1 INCLUDING 230KV MAIN BUS, 115 AUX BUS, & PCB B-1465 | PA, SOA, LOAD, PA, SOA, LOAD, LOAD, PA, RP, SOA, SOA, GEN, LOAD, SOA
50 | 22-04064 | 11337305 | 08/01/2022 08:00 | 08/01/2022 10:00 | CHIEF JOSEPH-SNOHOMISH NO 4 345KV LINE, CHIEF JOSEPH: 345/230KV TRANSFORMER 2, SNOHOMISH: 345/230KV TRANSFORMER 6 | NOEL, NOH, SOC, WOCN, FCRPS, NI, NOEL, SOC, WOCN, GEN, IROL, NOH, GEN, IROL, NOEL, NOH, SOC, WOCN
51 | 22-04066 | 11337303 | 08/01/2022 08:00 | 08/26/2022 07:00 | CHIEF JOSEPH: 345/230KV TRANSFORMER 2, (CHIEF JOSEPH-SNOHOMISH 4 LINE OPERATED AT 230KV) | NOEL, NOH, SOC, WOCN, FCRPS, NI, NOEL, SOC, WOCN, GEN, IROL, NOH
52 | 22-03271 | 11936489 | 08/01/2022 08:00 | 08/13/2022 16:00 | CARLTON-TILLAMOOK NO 1 230KV LINE | LOAD, SOA, COI, NWACI, PDCI
53 | 22-10000 | 11969393 | 08/01/2022 08:00 | 08/02/2022 15:00 | -COWLITZ- OLIVE WAY 115KV BUS | LOAD, LOAD, LOAD
54 | 22-03791 | 11300176 | 08/01/2022 08:00 | 08/01/2022 15:00 | LOWER GRANITE: PCB 4772 | GEN, MT-NW, WOH, WOLM
55 | 22-09985 | 11912517 | 08/01/2022 08:00 | 08/04/2022 17:00 | JOHN DAY: 230 WEST BUS, INCLUDING PCB'S A-1734, A-1735, AND A-1736 AND 230KV CAP GROUP 2 SECT'S 1,2, & 3 | COI, PDCI, WOJD, NWACI, COI, JDAY, PDCI, WOJD, NWACI, COI, JDAY, PDCI, WOJD, NWACI
56 | 22-09266 | 11911308 | 08/01/2022 08:00 | 08/02/2022 15:00 | BIG EDDY: BIG EDDY-MAUPIN NO 1 230KV LINE INCLUDING REDMOND: PCB A-814 AND 230KV A/B SECTION 2 | COI, NWACI, PDCI, WOJD, COI, NWACI, PDCI, WOJD
57 | 22-01954 | 10755121 | 08/01/2022 08:00 | 08/01/2022 16:00 | SIFTON: 230/115KV TRANSFORMER 1 INCLUDING 13.8KV STATION SERVICE TRANSFORMERS
58 | 22-02802 | 11103514 | 08/01/2022 08:00 | 09/01/2022 16:00 | SACHEEN: 230/115KV TRANSFORMER 1
59 | 22-06834 | 11637568 | 08/01/2022 08:00 | 08/04/2022 15:00 | MARTIN CREEK-DRAIN NO 1 115KV LINE
60 | 22-01281 | 9801605 | 08/01/2022 08:30 | 08/31/2022 12:00 | ROGUE: 230/115KV TRANSFORMER 1 | SWORE, LOAD, SWORE, SIG
61 | 22-09616 | 11877152 | 08/01/2022 14:00 | 08/14/2022 06:00 | LITTLE GOOSE: 4349/4351 TERMINAL OF , LITTLE GOOSE PH-LITTLE GOOSE NO 1 500KV LINE | GEN, WOLM
62 | 22-04058 | 11603998 | 08/02/2022 07:00 | 08/02/2022 16:00 | SCHULTZ: PCB 5148 BFR
63 | 22-02119 | 10888978 | 08/02/2022 08:00 | 08/02/2022 16:00 | PEARL: PCB 4280 | SOA
64 | 22-03851 | 11313527 | 08/02/2022 08:00 | 08/03/2022 14:30 | HATWAI: PCB 4710 | GEN, MT-NW, NOH, WOH, WOLM
65 | 22-03520 | 11282975 | 08/02/2022 08:15 | 08/02/2022 08:45 | GRAND COULEE: PCB 1996, PCB 1992 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI
66 | 22-03676 | 11350846 | 08/02/2022 08:30 | 08/03/2022 15:00 | NAPAVINE: 500KV PCB 5232 BFR | PA
67 | 22-03521 | 11282977 | 08/02/2022 09:15 | 08/02/2022 09:45 | GRAND COULEE: PCB 2096, PCB 2092 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI
68 | 22-03522 | 11282978 | 08/02/2022 10:15 | 08/02/2022 10:45 | GRAND COULEE: PCB 2296, PCB 2292 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI
69 | 22-03523 | 11282979 | 08/02/2022 11:15 | 08/02/2022 11:45 | GRAND COULEE: PCB 2396, PCB 2392 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI
70 | 22-03524 | 11282981 | 08/02/2022 12:45 | 08/02/2022 13:15 | GRAND COULEE: PCB 2492, PCB 2496 | GEN, NOH, COI, NWACI, PDCI, GEN, WOCN, COI, NOH, NWACI, PDCI
71 | 22-02662 | 11120732 | 08/03/2022 07:00 | 08/04/2022 16:00 | GARRISON: BROADVIEW 2 500KV LINE SERIES CAP GROUP 2 INCL PCB 4468 | MT-NW, MT-NW
72 | 22-04059 | 11604030 | 08/03/2022 07:00 | 08/03/2022 16:00 | SCHULTZ: PCB 5151 BFR
73 | 22-08506 | 11802723 | 08/03/2022 08:00 | 08/04/2022 16:30 | SOUTH TACOMA-WHITE RIVER NO. 1 230KV LINE INCLUDING PCB A-1098, A-1095 | RP, NOEL, SOC, GEN, RP, NOEL, SOC, NOEL, RP, SOC, WOCN
74 | 22-05367 |  | 08/03/2022 22:00 | 08/14/2022 06:00 | -PACW- MCKENZIE-DIAMOND HILL SECTION OF ALVEY-DIAMOND HILL NO 3 230KV LINE | NWACI, PDCI, COI
75 | 22-05366 |  | 08/03/2022 22:00 | 08/14/2022 06:00 | -EWEB- MCKENZIE EWEB: 1M33 TERMINAL OF THE DIAMOND HILL SECTION OF ALVEY-DIAMOND HILL NO 3 230KV LINE INCLUDING
76 | 22-02516 | 11035687 | 08/04/2022 08:00 | 08/04/2022 12:00 | OSTRANDER: PCB 4450 | WOCS
77 | 22-02517 | 11035700 | 08/04/2022 12:00 | 08/04/2022 16:00 | OSTRANDER: PCB 5134 | WOCS
78 | 22-09679 | 11890986 | 08/05/2022 07:30 | 08/08/2022 07:30 | LOOKOUT POINT-ALVEY NO.2 115KV LINE INCLUDING: MT. VERNON TAP (UNGROUNDED) | GEN, GEN, GEN
79 | 22-02347 | 10955957 | 08/05/2022 22:30 | 08/05/2022 23:00 | GRAND COULEE: PCB 2196, PCB 2192 | GEN, NOH, WOCN, GEN, NOH, WOCN
80 | 22-09812 |  | 08/06/2022 07:00 | 08/08/2022 19:00 | SCL - DIABLO-BOTHELL 1 & 2 230 KV LINE (D1 & D2) | SOC/NOEL
81 | 22-02715 | 11176227 | 08/06/2022 22:30 | 08/07/2022 08:00 | OAKRIDGE: LBD B-367, LANE ELEC COOP 115KV FEEDER 1, OAKRIDGE: LANE ELEC COOP 115KV FEEDER 1, OAKRIDGE-LOOKOUT POINT SECTION OF HILLS CREEK-LOOKOUT POINT NO 1 115KV LINE
82 | 22-08099 | 11719653 | 08/07/2022 00:00 | 08/07/2022 08:00 | SHELTON: MASON PUD #3 FEEDER NO 1 INCLUDING SHELTON PCB B-1128 AND THE 115KV AUX BUS
83 | 22-02795 | 11120752 | 08/08/2022 03:00 | 08/12/2022 17:00 | GRAND COULEE: PCB 2396 | GEN, NOH, WOCN, COI, NWACI, PDCI
84 | 22-02820 | 11232537 | 08/08/2022 06:00 | 08/11/2022 16:00 | GARRISON: 500KV REACTOR #3 RELAY SETS 1 & 2 (REACTOR 3 OUT OF SERVICE) | MT-NW
85 | 22-01869 | 10670162 | 08/08/2022 06:00 | 08/08/2022 18:00 | LOWER GRANITE: 4771/4773 TERMINAL OF LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE (UNGROUNDED) | GEN, MT-NW, NOH, WOH, WOLM, GEN, MT-NW, WOH, WOLM, GEN
86 | 22-02656 | 11108932 | 08/08/2022 07:00 | 08/11/2022 16:00 | GARRISON: PCB 4415 | MT-NW
87 | 22-04062 | 11604109 | 08/08/2022 07:00 | 08/08/2022 16:00 | SCHULTZ: PCB 5170 BFR
88 | 22-00830 | 11129593 | 08/08/2022 07:30 | 08/12/2022 16:00 | LAPINE: BUS TIE PCB A-1498, LAPINE: 230/115KV TRANSFORMER 2
89 | 22-09640 | 11976441 | 08/08/2022 07:30 | 08/14/2022 16:00 | -CLARK PUD- PIONEER SUBSTATION: PCB #1
90 | 22-08778 | 11790926 | 08/08/2022 08:00 | 08/11/2022 17:00 | BIG EDDY-CHEMAWA NO 1 230KV LINE | NWACI, PDCI, WOCS, COI, WOJD, WOCS, COI, NWACI, PDCI, WOJD
91 | 22-09696 | 11931622 | 08/08/2022 08:00 | 08/08/2022 11:00 | RAVER: PCB 4849, BFR | NOEL, RP, SOC
92 | 22-02093 | 10884869 | 08/08/2022 08:00 | 08/11/2022 15:00 | ECHO LAKE: PCB 5075 BFR | BCHT, BCHW, NOEL, SOC, WOCN, NI
93 | 22-00785 | 11125539 | 08/08/2022 08:00 | 08/18/2022 14:30 | ROGUE-GOLD BEACH NO 1 115KV LINE
94 | 22-09051 | 11808802 | 08/08/2022 08:00 | 08/26/2022 14:00 | CARDWELL: B-1542 TERMINAL OF THE CARDWELL-COWLITZ PUD #1 115KV LINE
95 | 22-09810 |  | 08/08/2022 08:00 | 08/26/2022 18:00 | SCL - DUWAMISH-DELRIDGE 230KV LINE
96 | 22-07773 | 11832586 | 08/08/2022 08:30 | 08/11/2022 18:00 | AIRPORT-LEBANON SECTION OF ALBANY-LEBANON NO 1 115KV LINE | SLAL, SLAL
97 | 22-02109 | 10912330 | 08/08/2022 09:00 | 08/11/2022 16:00 | MARION: PCB 4371 | NWACI, PDCI, WOCS, COI
98 | 22-09697 | 11931632 | 08/08/2022 12:00 | 08/08/2022 15:00 | RAVER: PCB 4314, BFR | NOEL, RP, SOC
99 | 22-02102 | 10879232 | 08/08/2022 22:00 | 08/08/2022 22:30 | GRAND COULEE: PCB 1996, PCB 1992 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI
100 | 22-01865 | 10670164 | 08/09/2022 06:00 | 08/09/2022 18:00 | LOWER GRANITE: 4771/4773 TERMINAL OF LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE (UNGROUNDED) | GEN, MT-NW, NOH, WOH, WOLM, GEN, MT-NW, WOH, WOLM, GEN
101 | 22-09401 | 11895665 | 08/09/2022 07:00 | 08/09/2022 15:00 | DWORSHAK-TAFT NO 1 500KV LINE | MT-NW, WOH, WOLM, MT-NW, NOH, WOH, WOLM, FCRPS, MT-NW, WOH, SLAL, WOLM, GEN, MT-NW, NOH, WOH, MT-NW, NOH, WOH
102 | 22-04060 | 11604087 | 08/09/2022 07:00 | 08/09/2022 16:00 | SCHULTZ: PCB 5154 BFR
103 | 22-01222 | 11019540 | 08/09/2022 07:30 | 08/09/2022 15:00 | PILOT BUTTE-LAPINE NO 1 230KV LINE INCLUDING LAPINE: PCB A-1552 AND THE 230KV AUX BUS | COI, PDCI, NWACI, NWACI, PDCI, COI, COR
104 | 22-09701 | 11931799 | 08/09/2022 08:00 | 08/09/2022 11:00 | RAVER: PCB 4921, BFR | NOEL, RP, SOC
105 | 22-07408 | 11695624 | 08/09/2022 08:00 | 08/09/2022 15:00 | Sno-King: PCB B-1560 including B-1560 BFR
106 | 22-09703 | 11931782 | 08/09/2022 12:00 | 08/09/2022 15:00 | RAVER: PCB 4876, BFR | NOEL, RP, SOC
107 | 22-00464 | 9692912 | 08/09/2022 16:30 | 08/09/2022 17:00 | GRAND COULEE: PCB 1992, PCB 1996 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI
108 | 22-01866 | 10670167 | 08/10/2022 06:00 | 08/10/2022 18:00 | LOWER GRANITE: 4771/4773 TERMINAL OF LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE (UNGROUNDED) | GEN, MT-NW, NOH, WOH, WOLM, GEN, MT-NW, WOH, WOLM, GEN
109 | 22-04061 | 11604104 | 08/10/2022 07:00 | 08/10/2022 16:00 | SCHULTZ: PCB 5157 BFR
110 | 22-01867 | 10670169 | 08/11/2022 06:00 | 08/11/2022 18:00 | LOWER GRANITE: 4771/4773 TERMINAL OF LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE (UNGROUNDED) | GEN, MT-NW, NOH, WOH, WOLM, GEN, MT-NW, WOH, WOLM, GEN
111 | 22-09230 | 11890282 | 08/11/2022 07:30 | 08/11/2022 17:00 | ALLSTON: PCB 4470 | PA, SOA
112 | 22-10384 | 11976448 | 08/11/2022 08:00 | 08/11/2022 15:00 | REDMOND: 230/115KV TRANSFORMER 5, REDMOND: PCB A-254, REDMOND: PCB B-1559 | COR
113 | 22-05554 | 11487778 | 08/11/2022 09:00 | 08/11/2022 12:00 | LITTLE GOOSE: PCB 4632 | WOLM
114 | 22-05171 | 11487829 | 08/11/2022 09:00 | 08/11/2022 12:00 | CENTRAL FERRY: PCB 5415 | MT-NW, WOH, WOLM, SIG
115 | 22-03141 | 11976749 | 08/11/2022 09:00 | 08/11/2022 15:00 | SACHEEN: 230/115KV TRANSFORMER 1 RELAYS, PCB A-1903, PCB A-1906, PCB B-323
116 | 22-05553 | 11487758 | 08/11/2022 12:00 | 08/11/2022 15:00 | LITTLE GOOSE: PCB 4350 | WOLM
117 | 22-05453 | 11487838 | 08/11/2022 12:00 | 08/11/2022 15:00 | CENTRAL FERRY: PCB 5418 | MT-NW, WOH, WOLM
118 | 22-01868 | 10670184 | 08/12/2022 06:00 | 08/12/2022 18:00 | LOWER GRANITE: 4771/4773 TERMINAL OF LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE (UNGROUNDED) | GEN, MT-NW, NOH, WOH, WOLM, GEN, MT-NW, WOH, WOLM, GEN
119 | 22-02716 | 11176235 | 08/13/2022 22:30 | 08/14/2022 08:00 | OAKRIDGE: LBD B-367, LANE ELEC COOP 115KV FEEDER 1, OAKRIDGE: LANE ELEC COOP 115KV FEEDER 1, OAKRIDGE-LOOKOUT POINT SECTION OF HILLS CREEK-LOOKOUT POINT NO 1 115KV LINE
120 | 22-03667 | 11289872 | 08/14/2022 22:00 | 08/14/2022 22:30 | GRAND COULEE: PCB 2196, PCB 2192 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI
121 | 22-09751 | 11902887 | 08/14/2022 22:00 | 09/02/2022 19:00 | GRAND COULEE: PCB 7382
122 | 22-03716 | 11309791 | 08/15/2022 06:00 | 08/31/2022 16:00 | GRAND COULEE-CHIEF JOSEPH NO 1 230KV LINE (UNGROUNDED) | GEN, NOH, FCRPS
123 | 22-02122 | 11314580 | 08/15/2022 07:00 | 08/25/2022 15:00 | MCNARY: 230/115/13.2KV TRANSFORMER #9, MCNARY: 230/115KV TRANSFORMER 9 | WOM
124 | 22-08317 | 11734507 | 08/15/2022 07:00 | 08/15/2022 15:00 | OLYMPIA: 230KV CAP GROUP 2 SECTIONS 1&2 INCLUDING LBD'S A-223, A-225 AND THE 230KV CAP GROUP 2 REACTIVE BUS | NOEL, SOC, WOCN, NOEL, SOC, WOCN
125 | 22-02660 | 11155950 | 08/15/2022 07:00 | 08/18/2022 16:00 | GARRISON: TAFT 2 500KV LINE SERIES CAP GROUP 2 INCLUDING PCB 4458 | MT-NW, MT-NW
126 | 22-06190 | 11587844 | 08/15/2022 07:00 | 09/09/2022 15:00 | COLVILLE: ADDY-COLVILLE NO 1 115KV LINE INCLUDING PCB B-1770 AND THE 115KV AUX BUS
127 | 22-01922 | 10951925 | 08/15/2022 07:30 | 08/18/2022 16:30 | ALLSTON: 500/230KV TRANSFORMER 1 | SIG, SOA, PA, SOA, PA, SOA
128 | 22-03584 | 11300194 | 08/15/2022 07:30 | 08/17/2022 15:00 | MALIN: PCB 4064 | NWACI, PDCI, COI
129 | 22-09244 | 11838282 | 08/15/2022 07:30 | 08/25/2022 16:00 | ALVEY: ALVEY-PACW GOSHEN SECTION OF THE ALVEY-MARTIN CREEK NO 1 115KV LINE INCLUDING: PCB B-588 AND THE 115KV NORTH AUX. | LOAD
130 | 22-09641 | 11976758 | 08/15/2022 07:30 | 08/21/2022 16:00 | -CLARK PUD- PIONEER SUBSTATION: PCB #2
131 | 22-02121 | 10888980 | 08/15/2022 08:00 | 08/15/2022 16:00 | PEARL: PCB 5458 | SOA
132 | 22-10001 | 11976761 | 08/15/2022 08:00 | 08/16/2022 14:00 | -COWLITZ- BAKER'S CORNER SUB STATION | LOAD
133 | 22-04757 | 11427923 | 08/15/2022 08:00 | 08/26/2022 16:00 | PLEASANT HILL-ALVEY SECTION OF LOOKOUT POINT-ALVEY NO 1 115KV LINE (UNGROUNDED) | GEN
134 | 22-02095 | 10884879 | 08/15/2022 08:00 | 08/18/2022 15:00 | ECHO LAKE: PCB 5078 | BCHT, BCHW, NOEL, SOC, WOCN, NI
135 | 22-04759 |  | 08/15/2022 08:00 | 08/25/2022 19:00 | ALVEY: S.U.B. 10TH STREET #1 115KV LINE , ALVEY: SPRNGFLD UTIL BRD 115KV FEEDER 1 TO 10TH STREET
136 | 22-06187 | 11587862 | 08/15/2022 08:30 | 09/09/2022 15:00 | ADDY-BOUNDARY SECTION OF BELL-BOUNDARY NO 3 230KV LINE | SOB, GEN, BCHT, GEN, MT-NW, SOB
137 | 22-04762 | 11427971 | 08/16/2022 07:00 | 08/18/2022 16:00 | ALVEY-CURRIN 115KV LINE | NWACI, PDCI, COI
138 | 22-04763 | 11427977 | 08/16/2022 07:00 | 08/19/2022 09:00 | HIDEAWAY-ALVEY SECTION OF HAWKINS-ALVEY NO 1 115KV LINE
139 | 22-03329 | 11407260 | 08/16/2022 07:00 | 08/20/2022 16:00 | FARGO-CHEMAWA SECTION OF OREGON CITY-CHEMAWA NO 2 115KV LINE
140 | 22-01995 | 11699449 | 08/16/2022 08:00 | 08/16/2022 15:00 | GRIZZLY: PCB 5040 | NWACI, WOJD, COI
141 | 22-04916 | 11382303 | 08/16/2022 08:15 | 08/16/2022 08:45 | GRAND COULEE: PCB 1992, PCB 1996 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI
142 | 22-04917 | 11382304 | 08/16/2022 09:15 | 08/16/2022 09:45 | GRAND COULEE: PCB 2092, PCB 2096 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI
143 | 22-04918 | 11382305 | 08/16/2022 10:15 | 08/16/2022 10:45 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 | GEN, NOH, WOCN
144 | 22-04919 | 11382306 | 08/16/2022 11:15 | 08/16/2022 11:45 | GRAND COULEE: PCB 2392, PCB 2396 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI
145 | 22-04920 | 11382308 | 08/16/2022 12:45 | 08/16/2022 13:15 | GRAND COULEE: PCB 2496, PCB 2492 | GEN, WOCN, COI, NOH, NWACI, PDCI, GEN, NOH, COI, NWACI, PDCI
146 | 22-02796 | 11120755 | 08/16/2022 22:00 | 08/29/2022 17:00 | GRAND COULEE: PCB 9292 | GEN, NOH, WOCN, COI, NWACI, PDCI
147 | 22-08313 | 11830418 | 08/17/2022 07:00 | 08/18/2022 16:00 | CHEHALIS: PCB A-52 | PA
148 | 22-01827 | 10857571 | 08/17/2022 09:00 | 08/25/2022 14:00 | SUMMER LAKE: PCB 4959 | NWACI, PDCI, COI
149 | 22-05293 | 11354146 | 08/17/2022 09:00 | 08/17/2022 21:00 | CELILO: PACIFIC HVDC OSCILLATION PROBE TEST (ALTERNATE DATE ) | NOH, NWACI, PDCI, COI, SIG
150 | 22-00992 | 11156894 | 08/18/2022 07:00 | 08/18/2022 16:00 | GRAND COULEE-HANFORD NO 1 500KV LINE INCLUDING HANFORD PCB 4089 | NOH, NWACI, PDCI, COI, WOM, WOS, BCHT, BCHW, GEN, NI, NOH, SIG, COI, NWACI, PDCI, WOCN
151 | 22-04671 | 11345434 | 08/18/2022 07:30 | 08/18/2022 11:00 | SCHULTZ: PCB 5154 | WOCN
152 | 22-04672 | 11345435 | 08/18/2022 11:00 | 08/18/2022 15:00 | SCHULTZ: PCB 5157 | WOCN
153 | 22-00993 | 11156982 | 08/18/2022 16:00 | 08/19/2022 07:00 | HANFORD: PCB 4089 | NOH, NWACI, PDCI, COI, WOM, WOS
154 | 22-00994 | 11156902 | 08/19/2022 07:00 | 08/19/2022 16:00 | HANFORD: 500KV NORTH BUS INCLUDING PCB 4089 | COI, NOH, NWACI, PDCI, WOM, WOS, NOH, NWACI, PDCI, COI, WOM, WOS
155 | 22-04766 | 11976767 | 08/19/2022 07:00 | 08/21/2022 16:00 | ALVEY: 115KV AUX BUS
156 | 22-03327 | 11596696 | 08/21/2022 07:00 | 08/22/2022 17:00 | OREGON CITY-FARGO SECTION OF THE OREGON CITY-CHEMAWA #2 115KV LINE
157 | 22-02186 | 10907902 | 08/22/2022 04:30 | 09/09/2022 15:00 | LIBBY: A-1587 TERMINAL OF THE LIBBY PH-LIBBY NO 2 230KV LINE | GEN, FCRPS, MT-NW
158 | 22-07762 | 11699069 | 2022-08-22 05:00 | 2022-08-22 18:00 | TACOMA: 230KV NORTH MAIN BUS INCLUDING TACOMA-TPWR NORTHEAST 2 230KV LINE AND 230KV NORTH AUX BUS | IROL, NOEL, RP, SOC, WOCN, NOEL, RP, SIG, SOC, IROL, WOCN, NOEL, RP, SOC, WOCN, NOEL, RP, SOC, WOCN, NOEL, RP, SOC
159 | 22-02657 | 11120690 | 08/22/2022 07:00 | 08/25/2022 16:00 | GARRISON: PCB 4360 | MT-NW
160 | 22-03123 | 11215567 | 08/22/2022 07:00 | 08/26/2022 15:00 | CHEHALIS: 230/115KV TRANSFORMER 2 | LOAD, PA, LOAD
161 | 22-04702 | 11337200 | 08/22/2022 07:00 | 08/22/2022 09:00 | LOWER MONUMENTAL: 4318 TERMINAL OF LOWER MONUMENTAL PH-LOWER MONUMENTAL NO 1 500KV LINE | GEN
162 | 22-01290 | 9878455 | 08/22/2022 07:30 | 09/16/2022 16:00 | SANTIAM-WREN SECTION OF SANTIAM-TOLEDO NO 1 230KV LINE INCLUDING SANTIAM: PCB A-524 AND 230KV AUX BUS | SWORE, LOAD, COI, PDCI, NWACI
163 | 22-02338 | 11131096 | 08/22/2022 07:30 | 08/25/2022 16:00 | ALLSTON: 230/115KV TRANSFORMER 3 | SOA, LOAD, SOA
164 | 22-03585 | 11300199 | 08/22/2022 07:30 | 08/24/2022 15:00 | MALIN: PCB 4186 | NWACI, PDCI, RATS, COI
165 | 22-03783 | 11350854 | 08/22/2022 07:30 | 08/25/2022 16:00 | NAPAVINE: 500KV PCB 5229 BFR AND PCB DIFF RELAY | GEN, NWACI, PA, PDCI, COI
166 | 22-09643 | 11976788 | 08/22/2022 07:30 | 08/27/2022 16:00 | -CLARK PUD- PIONEER SUBSTATION: PCB #3
167 | 22-03771 | 11228834 | 08/22/2022 08:00 | 08/26/2022 15:00 | CENTRAL FERRY: 500/230KV TRANSFORMER 1 INCLUDING SPARE PHASE, PCB'S A-1762 & A-1766 | WOLM, WOLM, GEN, WOLM, GEN, WOLM, WOH, WOLM
168 | 22-07625 | 11695701 | 08/22/2022 08:00 | 08/22/2022 15:00 | HANFORD: PCB 4007 | NOH, NWACI, PDCI, COI, WOM, WOS
169 | 22-05597 | 11493040 | 08/22/2022 08:00 | 11/18/2022 15:00 | BETTAS ROAD-COLUMBIA NO 1 230KV LINE INCLUDING BETTAS ROAD 230KV EAST BUS AND PCB A-3046 | NOEL, SOC, WOCN, WOCN, CI, NOEL, NOH, SOC, WOCN, IROL, NOEL, SOC, WOCN, NOEL, SOC, WOCN
170 | 22-02448 | 11025102 | 08/22/2022 08:00 | 08/23/2022 16:00 | RAVER: PCB 4311 BFR | NOEL, RP, SOC, WOCN
171 | 22-02406 | 11175525 | 08/22/2022 08:00 | 09/08/2022 16:30 | HAUSER-GLASGOW SECTION OF REEDSPORT-FAIRVIEW NO 1 115KV LINE | LOAD, SWORE
172 | 22-08986 | 11798909 | 08/22/2022 08:00 | 08/23/2022 16:30 | KITSAP: 115KV CAP GRP 1 SECTIONS 1&3 INCLUDING PCB B-949 AND LBD B-998
173 | 22-02603 | 11059981 | 2022-08-23 06:00 | 2022-08-27 18:00 | COVINGTON: 230KV MAIN BUS SECTION 1 INCLUDING PCB A-692 AND RAVER-COVINGTON NO 3 230KV LINE | NOEL, SOC, WOCN, NOEL, SOC, BCHT, BCHW, NOEL, RP, SOC, NOEL, SOC, NOEL, SOC, NOEL, RP, SOC, PA, RP, NOEL, RP, SOC, NOEL, SOC, NOEL, SOC, NOEL, SOC, BCHT, BCHW, RP, NOEL, SOC, NOEL, SOC, NOEL, RP, SOC, WOCN, NOEL, SOC, NOEL, SOC
174 | 22-03330 | 11407257 | 08/23/2022 07:00 | 08/26/2022 16:00 | FARGO-CHEMAWA SECTION OF OREGON CITY-CHEMAWA NO 2 115KV LINE
175 | 22-07627 | 11695712 | 08/23/2022 07:30 | 08/23/2022 16:00 | HANFORD: PCB 4095 | GEN, NWACI, PDCI, WOLM, COI, NOH, WOM, WOS
176 | 22-07787 | 11699215 | 08/23/2022 18:00 | 08/24/2022 16:30 | TACOMA-TPWR NORTHEAST NO 2 230KV LINE
177 | 22-04784 | 11345414 | 08/24/2022 08:00 | 08/24/2022 15:30 | BETTAS ROAD: PCB A-3043 BFR | NOEL, SOC, WOCN
178 | 22-02118 | 10910752 | 08/24/2022 08:30 | 08/24/2022 16:00 | SANTIAM: 230KV REACTIVE GROUP 1 CAP SECTION 1 INCLUDING PCB A-502 | COI, PDCI, NWACI, COI, NWACI, PDCI
179 | 22-08649 | 11803114 | 08/25/2022 08:00 | 08/25/2022 15:00 | CENTRAL FERRY: PCB 5388 | GEN, WOLM
180 | 22-02111 | 10912339 | 08/25/2022 09:00 | 08/25/2022 16:00 | MARION: 500KV REACTOR 1 INCLUDING PCB 4012 | COI
181 | 22-09514 | 11890365 | 08/25/2022 15:00 | 08/25/2022 15:30 | NAPAVINE: PCB 5226 | NOH, NWACI, PDCI, COI, SOA
182 | 22-04065 | 11337308 | 08/26/2022 07:00 | 08/26/2022 09:00 | CHIEF JOSEPH-SNOHOMISH NO 4 345KV LINE, CHIEF JOSEPH: 345/230KV TRANSFORMER 2, SNOHOMISH: 345/230KV TRANSFORMER 6 | NOEL, NOH, SOC, WOCN, FCRPS, NI, NOEL, SOC, WOCN, GEN, IROL, NOH, GEN, IROL, NOEL, NOH, SOC, WOCN
183 | 22-09765 |  | 08/27/2022 08:00 | 08/28/2022 18:00 | SCL- BOTHELL-CANAL 115KV LINE AND BOTHELL-SHORELINE 1 115KV LINE | SOC/NOEL
184 | 22-09769 |  | 08/27/2022 08:00 | 08/31/2022 18:00 | SCL-BOTHELL-CANAL 115KV LINE | SOC/NOEL
185 | 22-06137 | 11802878 | 08/29/2022 05:00 | 08/29/2022 18:00 | TACOMA-TPWR NORTHEAST NO 3 230KV LINE INCLUDING TACOMA 230KV SOUTH MAIN AND AUX BUS SECTION | NOEL, RP, SOC, WOCN, SIG, PA
186 | 22-02505 | 11017829 | 08/29/2022 06:30 | 08/29/2022 07:00 | MCNARY: PCB A-420 OF THE PH-MCNARY NO 3&4 230KV LINE , MCNARY PH-MCNARY NO 3&4 230KV LINE | GEN, WOM
187 | 22-00920 | 11237846 | 08/29/2022 06:30 | 08/29/2022 17:00 | LOWER MONUMENTAL-HANFORD NO 1 500KV LINE INCLUDING HANFORD 500KV NORTH BUS AND PCB 4095 | COI, NOH, NWACI, PDCI, WOM, WOS, NOH, NWACI, PDCI, SIG, WOLM, COI, GEN, NWACI, PDCI, WOLM, COI, NOH, WOM, WOS, GEN, NWACI, PDCI, WOLM, COI, NOH, WOM, WOS
188 | 22-02658 | 11120714 | 08/29/2022 07:00 | 09/01/2022 16:00 | GARRISON: PCB 4418 | MT-NW
189 | 22-02476 | 11369588 | 08/29/2022 07:30 | 08/30/2022 09:00 | RAVER: PCB 4917 BFR | NOEL, RP, SOC, IROL, WOCN, NOEL, RP, SOC
190 | 22-09644 | 11976817 | 08/29/2022 07:30 | 09/03/2022 16:00 | -CLARK PUD- PIONEER SUBSTATION: PCB #4
191 | 22-08685 | 11769222 | 08/29/2022 08:00 | 09/15/2022 16:00 | NORTH BONNEVILLE: A-11 TERMINAL OF THE BONNEVILLE PH-NORTH BONNEVILLE NO 4 230KV LINE | WOCS, GEN, FCRPS, WOCS
192 | 22-04802 | 11350615 | 08/29/2022 08:00 | 09/09/2022 16:00 | ELLENSBURG-CLYMER SECTION OF ELLENSBURG-MOXEE NO 1 115KV LINE | TCLA
193 | 22-08238 | 11767832 | 08/29/2022 08:00 | 09/08/2022 16:00 | ALLSTON-CLATSOP NO 1 230KV LINE INCLUDING DRISCOLL TAP AND CLATSOP: 230KV AUX BUS, A-1256 LINE DISCONNECT, AND 230/115/13.8KV TRANSFORMER 1 | SOA, SOA, LOAD, SOA, LOAD, PA, SOA, LOAD, SOA
194 | 22-00817 | 11135857 | 08/29/2022 08:00 | 09/02/2022 15:30 | MOSSYROCK-CHEHALIS NO 1 230KV LINE (UNGROUNDED) | PA, RP, PA
195 | 22-04668 | 11337184 | 08/29/2022 08:00 | 09/09/2022 17:30 | VANTAGE: A-1152 TERMINAL OF 500/230KV TRANSFORMER 2 | NOH
196 | 22-04010 | 11337227 | 08/29/2022 08:00 | 09/09/2022 17:30 | VANTAGE: 500/230KV TRANSFORMER 2, VANTAGE SUBSTATION 500/230KV TIE NO 1 230KV LINE | GEN, NOH, NWACI, SIG, COI, RATS, WI
197 | 22-00609 | 10916829 | 08/29/2022 08:00 | 08/29/2022 13:00 | SANTIAM: 230KV WEST MAIN BUS INCLUDING PCB'S A-514, A-516, & A-520 | COI, PDCI, NWACI, SIG, COI, PDCI, NWACI, COI, PDCI, NWACI, COI, PDCI, NWACI, COI, PDCI, NWACI, COI, PDCI, NWACI, COI, PDCI, SWORE, LOAD, GEN, WOCS, WOM, NWACI, PDCI, WOCS, COI, LOAD, NWACI, PDCI, COI
198 | 22-03055 | 11295373 | 08/29/2022 08:00 | 08/29/2022 17:00 | PHALEN GULCH-CENTRAL FERRY 230KV LINE INCLUDING CENTRAL FERRY PCB A-1762 AND PCB A-1780
199 | 22-08312 | 11750547 | 08/29/2022 08:00 | 08/29/2022 15:00 | RAYMOND-BALEVILLE SECTION OF RAYMOND-WILLAPA RIVER NO 1 115KV LINE INLCUDING RAYMOND: PCB B-122 AND 115KV AUX BUS
200 | 22-08225 | 11728808 | 08/29/2022 09:00 | 08/29/2022 15:00 | KEELER: 230/115KV TRANSFORMER 3 INCLUDING PCB 3W | SOA, SOA, LOAD
201 | 22-01755 | 11045182 | 08/29/2022 09:00 | 08/31/2022 17:00 | HARNEY: 115KV MAIN BUS INCLUDING PCB B-1708, PCB B-1710 AND THE 115KV REACTIVE GROUP 1 | LOAD, LOAD, ID-NW, SCORC, ID-NW, SCORC, ID-NW, SCORC, ID-NW
202 | 22-00917 | 11237862 | 08/29/2022 17:00 | 10/31/2022 07:30 | HANFORD: PCB 4098 INCLUDING MODS 4097 & 4099 | GEN, NWACI, PDCI, WOLM, COI, NOH, WOM, WOS
203 | 22-07434 | 11802974 | 08/29/2022 18:00 | 10/18/2022 05:00 | TACOMA: A-1071 MAIN AND AUX BUS DISCONNECTS (FORCES OUT TACOMA-TPWR NORTHEAST NO 3 230KV LINE)
204 | 22-04817 | 11363541 | 08/30/2022 06:30 | 09/02/2022 16:00 | MAPLE VALLEY: 500/230KV TRANSFORMER 2, ECHO LAKE-MAPLE VALLEY NO 1&2 500KV LINE | IROL, NOEL, SIG, SOC, WOCN, IROL, NOEL, SIG, SOC, WOCN
205 | 22-04642 | 11369592 | 08/30/2022 07:00 | 08/30/2022 09:00 | RAVER: PCB 4914 | NOEL, RP, SOC
206 | 22-09794 | 11901854 | 08/30/2022 08:00 | 09/01/2022 16:00 | SALEM: 230/115KV TRANSFORMER 1 | SLAL, WOCS
207 | 22-03053 | 11295423 | 08/30/2022 08:00 | 08/30/2022 17:00 | MULLAN-CENTRAL FERRY 230KV LINE INCLUDING CENTRAL FERRY: PCB A-1766 AND PCB A-1780
208 | 22-04965 | 11422339 | 08/30/2022 08:15 | 08/30/2022 08:45 | GRAND COULEE: PCB 1996, PCB 1992 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI
209 | 22-02477 | 11369597 | 08/30/2022 09:00 | 08/31/2022 09:00 | RAVER: PCB 4919 BFR | NOEL, RP, SOC, IROL, WOCN, NOEL, RP, SOC
210 | 22-04960 | 11422342 | 08/30/2022 09:15 | 08/30/2022 09:45 | GRAND COULEE: PCB 2096, PCB 2092 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI
211 | 22-04962 | 11422345 | 08/30/2022 10:15 | 08/30/2022 10:45 | GRAND COULEE: PCB 2296, PCB 2292 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI
212 | 22-04963 | 11422370 | 08/30/2022 11:15 | 08/30/2022 11:45 | GRAND COULEE: PCB 2396, PCB 2392 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI
213 | 22-05775 |  | 08/30/2022 12:00 | 08/30/2022 16:00 | JONES CANYON: MOD A-1649, JONES CANYON: MOD A-1680 NORTH BUS, JONES CANYON: MOD A-1687 SOUTH BUS
214 | 22-04964 | 11422375 | 08/30/2022 12:45 | 08/30/2022 13:15 | GRAND COULEE: PCB 2492, PCB 2496 | GEN, NOH, COI, NWACI, PDCI, GEN, WOCN, COI, NOH, NWACI, PDCI