## Request List
Row | Request# | CAISO# | Dart | Start | End | Main Element Impacted | Path Affected | Nature of Work
1 | 21-01711 | 9741845 | DART-1421102 | 02/03/2021 09:00 | 02/28/2023 17:00 | -USBR- GRAND COULEE 287/230KV TRANSFORMER KX-17-A (OLYMPIA-GRAND COULEE NO 1 287KV LINE OPERATING AT 230KV) | NOEL, PA, RP, SOC, WOCN, IROL, NOH, OKLA | OUT_OF_SERVICE
2 | 21-01577 |  | DART-1425338 | 02/28/2021 06:00 | 09/02/2022 16:00 | -AVA- NORTH LEWISTON: 230/115KV TRANSFORMER |  | OUT_OF_SERVICE
3 | 21-01581 |  | DART-1434254 | 04/30/2021 16:15 | 03/31/2023 18:00 | BCH - BURRARD SYNCHRONOUS CONDENSER STATION G2 | BCHT, BCHW, NI | OUT_OF_SERVICE
4 | 21-01797 | 10627354 | DART-1456044 | 08/25/2021 12:00 | 09/29/2022 23:59 | MCNARY: 500/230KV TRANSFORMER 2 (DERATED) | COI, PDCI, SIG, WOJD, WOM, NWACI | EQUIPMENT_DERATE
5 | 21-01773 | 10627358 | DART-1456052 | 08/25/2021 12:00 | 09/29/2022 23:59 | MAPLE VALLEY: 500/230KV TRANSFORMER 2 (DERATED) | IROL, NOEL, SIG, SOC, WOCN | EQUIPMENT_DERATE
6 | 21-01779 | 10627252 | DART-1456068 | 08/25/2021 12:00 | 08/31/2022 23:59 | CUSTER: 500/230KV TRANSFORMER 2 (DERATED) | NOEL, SIG, SOC, NI | EQUIPMENT_DERATE
7 | 21-01781 | 10627274 | DART-1456074 | 08/25/2021 12:00 | 08/31/2022 23:59 | SATSOP: 500/230KV TRANSFORMER 1 (DERATED) | PA, RP, LOAD | EQUIPMENT_DERATE
8 | 21-01596 |  | DART-1473178 | 12/14/2021 13:00 | 07/29/2022 18:00 | BCH- INGLEDOW 230KV REACTOR 1 (ING 2RX1) | BCHT, BCHW, NI | OUT_OF_SERVICE
9 | 22-03687 |  | DART-1479430 | 01/25/2022 19:08 | 01/31/2023 23:59 | AVA MOSCOW 230/115KV TRANSFORMER OOS |  | OUT_OF_SERVICE
10 | 22-05053 | 11570022 | DART-1484340 | 03/01/2022 07:00 | 07/01/2022 12:00 | CELILO: PCB 5512 INCLUDING BIG EDDY 2 500KV LINE CAP GROUP 3 | PDCI | OUT_OF_SERVICE
11 | 22-05275 | 11444005 | DART-1485018 | 03/04/2022 09:45 | 07/11/2022 07:30 | TROUTDALE: 500/230KV TRANSFORMER 8 (DERATED) | SIG, WOCS, SOA | EQUIPMENT_DERATE
12 | 22-06746 | 11593785 | DART-1335580 | 04/06/2022 06:30 | 12/30/2022 15:00 | CONKELLEY: LBD A-1575 INCLUDING 230KV CAP GROUP 2 SECTION 1 | MT-NW | OUT_OF_SERVICE
13 | 22-06836 | 11597875 |  | 04/06/2022 12:25 | 12/31/2022 15:00 | OSTRANDER-TROUTDALE 1 500KV LINE INCLUDING TROUTDALE: 500/230KV TRANSFORMER BANK 8 | SIG, SOA, WOCS, SIG, WOCS, SOA | OUT_OF_SERVICE
14 | 22-05580 | 11592848 |  | 04/11/2022 08:00 | 09/06/2022 16:00 | BREWSTER-OPHIR SECTION OF BREWSTER-OKANOGAN NO 1 115KV LINE | OKLA | OUT_OF_SERVICE
15 | 22-05491 |  |  | 05/02/2022 09:00 | 07/01/2022 14:30 | PACW- DIXONVILLE: ALVEY 1 500KV SERIES CAPS | NWACI, PDCI
16 | 22-00539 | 10388848 | DART-1442308,OTS-9944 | 05/16/2022 03:00 | 07/01/2022 19:00 | GRAND COULEE: GRAND COULEE SWITCHYARD 230-500KV TIE NO 1 500KV LINE INCLUDING PCBS 6582, 1996 AND 8692 | NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
17 | 22-03454 | 11268722 | DART-1478804 | 06/01/2022 00:01 | 10/31/2022 23:59 | COSMOPOLIS-ABERDEEN NO 1 115KV LINE (SUMMER RATING) | LOAD, PA | EQUIPMENT_DERATE
18 | 22-05648 |  |  | 06/01/2022 00:01 | 10/31/2022 23:59 | SOUTH ELMA-SATSOP PARK NO 1 115KV LINE(DERATED) | LOAD, PA, SOA | EQUIPMENT_DERATE
19 | 22-05645 |  | DART-1485548 | 06/01/2022 00:01 | 10/31/2022 23:59 | OLYMPIA-SOUTH ELMA NO 1 115KV LINE(DERATED) | LOAD, SI, PA, RP | EQUIPMENT_DERATE
20 | 22-04878 | 11369468 | DART-1482586 | 06/01/2022 00:01 | 10/31/2022 23:59 | OXBOW-NASELLE SECTION OF HOLCOMB-NASELLE NO 1 115KV LINE (SUMMER RATING) | PA | EQUIPMENT_DERATE
21 | 22-04877 | 11369465 | DART-1482582 | 06/01/2022 00:01 | 10/31/2022 23:59 | HOLCOMB-OXBOW SECTION OF HOLCOMB-NASELLE NO 1 115KV LINE (SUMMER RATING) | PA, RP | EQUIPMENT_DERATE
22 | 22-01027 | 11164008 | DART-1474904 | 06/01/2022 00:01 | 10/31/2022 23:59 | RIVERGATE-KEELER NO 1&2 230KV LINE (SUMMER DERATE) | SOA | EQUIPMENT_DERATE
23 | 22-00827 | 11129564 | DART-1461108 | 06/06/2022 08:00 | 07/22/2022 16:00 | LAPINE: 230/115/13.8KV TRANSFORMER 1 INCLUDING PCB A-1494, LAPINE: 230/115KV TRANSFORMER 1 | COI, PDCI, NWACI | OUT_OF_SERVICE
24 | 22-06059 | 10788125 |  | 06/13/2022 08:00 | 07/01/2022 16:00 | Horizon-St Marys-Trojan 230kV_V1688, Horizon-St Marys-Trojan 230kV_V12160, Horizon-St Marys-Trojan 230kV_V12159 | SOA
25 | 22-06145 | 11350063 |  | 06/13/2022 08:00 | 07/01/2022 16:00 | Murrayhill-Sherwood 1 230kV | SOA
26 | 22-04921 |  |  | 06/13/2022 08:00 | 07/01/2022 16:00 | PGE - MURRAYHILL-SHERWOOD 1 230KV | SOA | OUT_OF_SERVICE
27 | 22-02698 |  | DART-1471474 | 06/13/2022 08:00 | 07/01/2022 16:00 | PGE - HORIZON-ST MARYS-TROJAN 230KV LINE | SOA | OUT_OF_SERVICE
28 | 22-06340 | 11562405 |  | 06/13/2022 16:30 | 07/08/2022 15:00 | TACOMA: PCB A-1060 | NOEL, SOC | OUT_OF_SERVICE
29 | 22-05754 | 11593248 |  | 06/21/2022 07:00 | 07/01/2022 16:30 | ALVEY: 115KV NORTH M/B INCLUDING PCB B-588 | LOAD | OUT_OF_SERVICE
30 | 22-03581 | 11433734 | DART-1479184 | 06/23/2022 11:30 | 07/27/2022 12:00 | LONGVIEW: 230/115KV TRANSFORMER 3 INCLUDING BANK 3 CT'S, PCB B-328 AND B-328 M/B, T/S, A/B DISC'S | PA, SOA, LOAD, SOA | OUT_OF_SERVICE
31 | 22-06721 | 11596711 | DART-1475446 | 06/27/2022 08:00 | 07/01/2022 15:00 | BIG EDDY-DE MOSS NO 1 115KV LINE | GEN | OUT_OF_SERVICE
32 | 22-00990 | 11156884 | DART-1448108 | 06/27/2022 18:00 | 08/18/2022 07:00 | HANFORD: PCB 4089 INCLUDING MODS 4088 & 4090 | NOH, NWACI, PDCI, COI, WOM, WOS | OUT_OF_SERVICE
33 | 22-01792 | 11563128 | DART-1453676 | 06/28/2022 07:00 | 07/12/2022 15:30 | FRANKLIN: PCB B-1526 INCLUDING THE FRANKLIN-ZEPHYR HEIGHTS SECTION OF FRANKLIN-BADGER CANYON NO 1 115KV AND THE 115KV AUX BUS | LOAD | OUT_OF_SERVICE
34 | 22-04985 | 11412504 | DART-1483952,OTS-12365 | 06/28/2022 08:00 | 07/15/2022 17:00 | BONNEVILLE PH 2-NORTH BONNEVILLE NO 3 230KV LINE | GEN, FCRPS, WOCS, WOCS | OUT_OF_SERVICE
35 | 22-06274 | 11575419 | OTS-12573 | 07/01/2022 08:00 | 07/01/2022 10:00 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
36 | 22-06275 | 11575389 | OTS-12574 | 07/01/2022 10:00 | 07/01/2022 12:00 | GRAND COULEE: PCB 2092, GRAND COULEE: PCB 2096 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
37 | 22-02600 | 11058752 | DART-1470544,OTS-11769 | 07/05/2022 05:30 | 10/28/2022 15:00 | -USBR- HUNGRY HORSE PH: PCB 2382, PCB 2282 | WOH, WOH | OUT_OF_SERVICE
38 | 22-04868 | 11368007 | DART-1482504 | 07/05/2022 07:00 | 07/08/2022 15:00 | SHELTON-T3BA'DAS SECTION OF SHELTON-FAIRMOUNT NO 2 115KV LINE | PA | OUT_OF_SERVICE
39 | 22-02272 | 10940514 | DART-1466346 | 07/05/2022 07:00 | 07/06/2022 15:00 | CUSTER: PCB A-1540 | BCHT, BCHW, NOEL, SOC, NI | OUT_OF_SERVICE
40 | 22-03816 | 11295531 | DART-1479722,OTS-12193 | 07/05/2022 07:00 | 07/21/2022 16:00 | GOOSE LAKE-OKANOGAN SECTION OF GRAND COULEE-OKANOGAN NO 2 115KV LINE | LOAD | OUT_OF_SERVICE
41 | 22-02676 | 11233752 | DART-1471288 | 07/05/2022 07:00 | 07/07/2022 17:30 | NOXON-LIBBY NO 1 230KV LINE | MT-NW, WOH, FCRPS, GEN | OUT_OF_SERVICE
42 | 22-02772 | 11364216 | DART-1472336 | 07/05/2022 07:00 | 07/28/2022 17:00 | TOLEDO-WENDSON NO 1 230KV LINE INCLUDING TOLEDO: PCB A-1468 | SWORE, LOAD, LOAD | OUT_OF_SERVICE
43 | 22-06786 | 11597470 |  | 07/05/2022 07:30 | 07/09/2022 16:00 | SANTIAM-MARCOLA A500 SECTION OF SANTIAM-ALVEY NO 1&2 230KV LINE | NWACI, PDCI, COI, COI, PDCI, NWACI | OUT_OF_SERVICE
44 | 22-02040 | 11201302 | DART-1463368 | 07/05/2022 07:30 | 07/05/2022 12:00 | SCHULTZ: PCB 5160 | WOCN | OUT_OF_SERVICE
45 | 22-03051 | 11210267 | DART-1476712 | 07/05/2022 08:00 | 07/07/2022 16:00 | BOX CANYON-METALINE FALLS SECTION OF COLVILLE-BOUNDARY NO 1 115KV LINE (UNGROUNDED) | SOB | OUT_OF_SERVICE
46 | 22-01017 | 11175981 | DART-1474878,OTS-11997 | 07/05/2022 08:15 | 07/05/2022 08:45 | GRAND COULEE: PCB 1996, PCB 1992 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
47 | 22-06143 | 9826915 |  | 07/05/2022 09:00 | 09/02/2022 15:30 | Meridian 500kV Series Cap | PDCI, COI
48 | 22-06144 |  |  | 07/05/2022 09:00 | 09/02/2022 15:30 | PAC- MERIDIAN 500KV SERIES CAP GROUP 1 | COI, NWACI/PDCI | OUT_OF_SERVICE
49 | 22-01018 | 11175982 | DART-1474880,OTS-11998 | 07/05/2022 09:15 | 07/05/2022 09:45 | GRAND COULEE: PCB 2092, PCB 2096 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
50 | 22-01021 | 11175983 | DART-1474886,OTS-11999 | 07/05/2022 10:15 | 07/05/2022 10:45 | GRAND COULEE: PCB 2196, PCB 2192 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
51 | 22-01019 | 11175984 | DART-1474882,OTS-12000 | 07/05/2022 11:15 | 07/05/2022 11:45 | GRAND COULEE: PCB 2396, PCB 2392 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
52 | 22-02042 | 11201349 | DART-1463372 | 07/05/2022 12:00 | 07/05/2022 17:30 | SCHULTZ: PCB 5167 | WOCN | OUT_OF_SERVICE
53 | 22-01020 | 11175985 | DART-1474884,OTS-12001 | 07/05/2022 12:45 | 07/05/2022 13:15 | GRAND COULEE: PCB 2492, PCB 2496 | GEN, NOH, COI, NWACI, PDCI, GEN, WOCN, COI, NOH, NWACI, PDCI | OUT_OF_SERVICE
54 | 22-02671 | 11104832 | DART-1471210 | 07/06/2022 06:00 | 07/06/2022 15:00 | COSMOPOLIS-ABERDEEN NO 1 115KV LINE INCLUDING COSMOPOLIS: PCB B-1324, 115KV AUX BUS, AND ABERDEEN: PCB B-812 AND THE 115KV AUX BUS | PA, LOAD, PA | OUT_OF_SERVICE
55 | 22-02044 | 11201366 | DART-1463376 | 07/06/2022 07:00 | 07/06/2022 12:00 | SCHULTZ: PCB 5182 | WOCN | OUT_OF_SERVICE
56 | 22-02046 | 11201374 | DART-1463382 | 07/06/2022 12:00 | 07/06/2022 17:30 | SCHULTZ: PCB 5179 | NOH, WOCN | OUT_OF_SERVICE
57 | 22-02129 | 10888975 | DART-1464896 | 07/06/2022 13:00 | 07/06/2022 16:00 | PEARL: 500KV CAP GROUP 1 INCLUDING PCB 4342 | COI, PDCI, WOCS, NWACI, SOA, NWACI, PDCI, SOA, COI | OUT_OF_SERVICE
58 | 22-02048 | 11201401 | DART-1463388 | 07/07/2022 07:00 | 07/07/2022 12:00 | SCHULTZ: PCB 5170 | NOH, WOCN | OUT_OF_SERVICE
59 | 22-02050 | 11201413 | DART-1463392 | 07/07/2022 12:00 | 07/07/2022 17:30 | SCHULTZ: PCB 5157 | WOCN | OUT_OF_SERVICE
60 | 22-06277 | 11575418 | OTS-12576 | 07/08/2022 08:00 | 07/08/2022 10:00 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
61 | 22-06288 | 11575425 | OTS-12578 | 07/08/2022 10:00 | 07/08/2022 12:00 | GRAND COULEE: PCB 2292, GRAND COULEE: PCB 2296 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
62 | 22-02594 | 11045348 | DART-1470354,OTS-11762 | 07/11/2022 03:00 | 07/15/2022 17:00 | GRAND COULEE: PCB 2496, PCB 2492 | GEN, WOCN, COI, NOH, NWACI, PDCI, GEN, NOH, COI, NWACI, PDCI | OUT_OF_SERVICE
63 | 22-01953 | 10765434 | DART-1460984 | 07/11/2022 06:00 | 07/14/2022 19:00 | RAVER: 500KV SOUTH BUS INCLUDING PCBS 4921, 4789, 4308, 4299, 4220, 4876, 4858 | NOEL, RP, SOC, WOCN | OUT_OF_SERVICE
64 | 22-00843 | 11130689 | DART-1473332 | 07/11/2022 06:30 | 07/15/2022 16:00 | BELL-ADDY SECTION OF BELL-BOUNDARY NO 3 230KV LINE | SOB, BCHT, GEN, MT-NW, SOB, SOB | OUT_OF_SERVICE
65 | 22-05193 | 11438845 | DART-1484796 | 07/11/2022 07:00 | 07/22/2022 16:00 | B-1063 AND B-1064 TERMINALS OF THE PLEASANT HILL TAP TO THE LOOKOUT POINT - ALVEY #1 115KV LINE, PLEASANT HILL: EMERALD PUD 115KV FEEDER 1, PLEASANT HILL-ALVEY SECTION OF LOOKOUT POINT-ALVEY NO 1 115KV LINE, DEXTER-PLEASANT HILL SECTION OF LOOKOUT POINT-ALVEY NO 1 115KV LINE | GEN, GEN | OUT_OF_SERVICE
66 | 22-02051 | 11201427 | DART-1463398 | 07/11/2022 07:00 | 07/11/2022 17:30 | SCHULTZ: ECHO LAKE 1 500KV LINE SERIES CAP GROUP 1 INCLUDING PCB 5142 | IROL, NOEL, NWACI, PDCI, SOC, WOCN, COI, WOCN | OUT_OF_SERVICE
67 | 22-01939 | 10744137 | DART-1459852 | 07/11/2022 07:00 | 07/21/2022 16:00 | BELL: 500KV REACTOR 1 INCLUDING PCB 4559 | MT-NW, WOH, MT-NW, WOH | OUT_OF_SERVICE
68 | 22-04717 | 11346139 | DART-1481420 | 07/11/2022 07:00 | 07/14/2022 16:00 | GARRISON-TAFT NO 1 500KV LINE INCLUDING GARRISON: PCB 4415, PCB 4418, AND TAFT 1 500KV LINE SERIES CAP GROUP 1 | MT-NW, SIG, MT-NW, MT-NW, MT-NW | OUT_OF_SERVICE
69 | 22-02316 | 11443898 | DART-1466956 | 07/11/2022 07:30 | 07/15/2022 15:30 | ALBANY: 230/115KV TRANSFORMER 1, A539-ALBANY SECTION OF SANTIAM-ALBANY NO 1 230KV LINE, SANTIAM: CONSUMERS POWER 69KV FEEDER 1 | COI, PDCI, COI, PDCI | OUT_OF_SERVICE
70 | 22-00906 | 11151031 | DART-1474014 | 07/11/2022 07:30 | 07/15/2022 16:00 | TROUTDALE: 500/230KV TRANSFORMER 8 , OSTRANDER-TROUTDALE NO 1 500KV LINE | SIG, WOCS, SOA, SIG, SOA, WOCS | OUT_OF_SERVICE
71 | 22-01961 | 10264649 | DART-1439498 | 07/11/2022 08:00 | 07/14/2022 17:00 | ST JOHNS-DUTCH CANYON SECTION OF ST JOHNS-ST HELENS NO 1 115KV LINE | LOAD, SOA | OUT_OF_SERVICE
72 | 22-01762 | 10743630 | DART-1452262 | 07/11/2022 08:00 | 07/21/2022 15:00 | CAPTAIN JACK: PCB 4977 | NWACI, PDCI, COI | OUT_OF_SERVICE
73 | 22-02091 | 10880498 | DART-1464282 | 07/11/2022 08:00 | 07/14/2022 15:00 | ECHO LAKE: PCB 5072 BFR | BCHT, BCHW, NOEL, SOC, NI, WOCN, BCHT, BCHW, NOEL, SOC, NI, WOCN | OUT_OF_SERVICE
74 | 22-02729 | 11109175 | DART-1471834 | 07/11/2022 08:15 | 07/11/2022 16:00 | JOHN DAY: PCB 4134 | NWACI, PDCI, WOJD, COI | OUT_OF_SERVICE
75 | 22-02110 | 10912255 | DART-1464708 | 07/11/2022 08:30 | 07/13/2022 16:00 | MARION: 500KV CAP GROUP 1 INCLUDING PCB 4331 | COI, PDCI, WOCS, NWACI, NWACI, PDCI, COI | OUT_OF_SERVICE
76 | 22-01291 |  | DART-1424824 | 07/11/2022 09:00 | 07/22/2022 16:30 | PAC - DIXONVILLE-MERIDIAN NO 1 500KV LINE | BCHT, BCHW, NI, NWACI, PDCI, SIG, COI | OUT_OF_SERVICE
77 | 22-02638 | 11081000 | DART-1470814 | 07/11/2022 12:00 | 07/15/2022 14:00 | MURRAY: PCB B-1747 (FORCES OUT CAP GROUP 1 SECTIONS 1 AND 2) |  | OUT_OF_SERVICE
78 | 22-06142 | 9826995 |  | 07/11/2022 20:00 | 07/22/2022 08:00 | DIXONVILLE-MERIDIAN (PACW) | PDCI, COI, NI
79 | 22-02052 | 11201429 | DART-1463400 | 07/12/2022 07:00 | 07/12/2022 17:30 | SCHULTZ: RAVER 1 500KV LINE SERIES CAP GROUP INCLUDING PCB 5163 | IROL, NOEL, NWACI, PDCI, SOC, WOCN, COI, SIG, WOCN | OUT_OF_SERVICE
80 | 22-01222 | 11019540 | DART-1409850 | 07/12/2022 07:30 | 07/12/2022 15:00 | PILOT BUTTE-LAPINE NO 1 230KV LINE INCLUDING LAPINE: PCB A-1552 AND THE 230KV AUX BUS, LAPINE: 230/115KV TRANSFORMER 2 | NWACI, PDCI, COI, COI, PDCI, NWACI | OUT_OF_SERVICE
81 | 22-02730 | 11109187 | DART-1471836 | 07/12/2022 08:15 | 07/12/2022 16:00 | JOHN DAY: PCB 4158 | NWACI, PDCI, WOJD, COI | OUT_OF_SERVICE
82 | 22-02054 | 11201444 | DART-1463402 | 07/13/2022 07:00 | 07/13/2022 17:30 | SCHULTZ: PCB 5129 | WOCN | OUT_OF_SERVICE
83 | 22-05089 | 11540565 | DART-1484470 | 07/13/2022 07:00 | 07/13/2022 13:00 | SNOHOMISH: 230KV CAP GROUP 3 SECTIONS 1 & 2 INCLUDING PCB A-1040 | NOEL, SOC, WOCN, NOEL, SOC, WOCN, NOEL, SOC, WOCN, NOEL, SOC, WOCN | OUT_OF_SERVICE
84 | 22-02731 | 11109191 | DART-1471838 | 07/13/2022 08:15 | 07/13/2022 16:00 | JOHN DAY: PCB 4179 | NWACI, PDCI, WOJD, COI | OUT_OF_SERVICE
85 | 22-03780 | 11291272 | DART-1479560,OTS-12181 | 07/14/2022 07:00 | 07/14/2022 15:00 | BELL: GRAND COULEE-BELL NO 3 230KV LINE INCLUDING BELL PCBS A-558 AND A-552 | MT-NW, WOH, NOH, WOH, COI, NWACI, PDCI | OUT_OF_SERVICE
86 | 22-02732 | 11109192 | DART-1471840 | 07/14/2022 08:15 | 07/14/2022 16:00 | JOHN DAY: PCB 5441 | NWACI, PDCI, WOJD, WOM, WOS, COI | OUT_OF_SERVICE
87 | 22-02718 | 11176154 | DART-1471740,OTS-12006 | 07/15/2022 07:30 | 11/17/2022 12:00 | HILLS CREEK-OAKRIDGE SECTION OF HILLS CREEK-LOOKOUT POINT NO 1 115KV LINE | PDCI, COI | OUT_OF_SERVICE
88 | 22-03664 | 11289866 | DART-1479380,OTS-12168 | 07/15/2022 16:30 | 07/15/2022 17:00 | GRAND COULEE: PCB 2296, PCB 2292 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
89 | 22-02790 | 11120744 | DART-1472480,OTS-11861 | 07/18/2022 01:00 | 07/22/2022 19:00 | GRAND COULEE: PCB 2492 | GEN, NOH, COI, NWACI, PDCI | OUT_OF_SERVICE
90 | 22-03667 | 11289872 | DART-1479386,OTS-12171 | 07/18/2022 01:00 | 07/18/2022 01:30 | GRAND COULEE: PCB 2196, PCB 2192 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
91 | 22-01960 | 10765451 | DART-1461512 | 07/18/2022 06:00 | 07/21/2022 19:00 | RAVER: 500KV NORTH BUS INCLUDING PCBS 4844, 4914, 4792, 4314, 4305, 4296, 4846, 4849, AND 500KV REACTOR 2 | NOEL, RP, SOC, WOCN, NOEL, RP, SOC, NOEL, RP, SOC, WOCN, NOEL, RP, SOC, NOEL, RP, SOC, NOEL, RP, SOC, NOEL, RP, SOC, NOEL, RP, SOC | OUT_OF_SERVICE
92 | 22-02236 | 10917304 | DART-1466050,OTS-11181 | 07/18/2022 06:30 | 07/18/2022 07:00 | BIG EDDY: PCB A-824 OF THE DALLES PH-BIG EDDY NO 4 230KV LINE | GEN, FCRPS, COI, NWACI, PDCI, WOJD | OUT_OF_SERVICE
93 | 22-01167 | 8875384 | DART-1355850,OTS-4985 | 07/18/2022 06:30 | 07/24/2022 17:00 | ICE HARBOR-FRANKLIN NO 1 115KV LINE | GEN, TCLA | OUT_OF_SERVICE
94 | 22-02657 | 11120690 | DART-1471036 | 07/18/2022 07:00 | 07/21/2022 16:00 | GARRISON: PCB 4360 | MT-NW | OUT_OF_SERVICE
95 | 22-02627 | 11076000 | DART-1470686 | 07/18/2022 07:00 | 07/18/2022 16:00 | ABERDEEN TAP TO SATSOP PARK-COSMOPOLIS NO 1 115KV LINE INCLUDING ABERDEEN: PCB B-808 AND THE 115KV AUX BUS | PA, RP | OUT_OF_SERVICE
96 | 22-00846 | 11131005 | DART-1473350 | 07/18/2022 07:00 | 07/29/2022 16:00 | COLVILLE-SPIRIT SECTION OF COLVILLE-BOUNDARY NO 1 115KV LINE | SOB | OUT_OF_SERVICE
97 | 22-00845 | 11131003 | DART-1473352 | 07/18/2022 07:00 | 07/29/2022 16:00 | ADDY-BOUNDARY SECTION OF BELL-BOUNDARY NO 3 230KV LINE , BELL-ADDY SECTION OF BELL-BOUNDARY NO 3 230KV LINE, ADDY TAP TO BELL-BOUNDARY NO 3 230KV LINE | SOB, GEN, SOB, SOB | OUT_OF_SERVICE
98 | 22-02055 | 11201450 | DART-1463406 | 07/18/2022 07:00 | 07/22/2022 17:30 | SCHULTZ: 500KV REACTOR 1 INCLUDING PCB 5106 | WOCN, WOCN | OUT_OF_SERVICE
99 | 22-02325 | 11035848 | DART-1467112 | 07/18/2022 07:30 | 07/21/2022 15:00 | GREEN VALLEY: 230/69KV TRANSFORMER 1 INCLUDING THE SS TRANSFORMER BANK 1 ,PCB A-507 AND 69KV PCB L-431, DRAIN: DOUGLAS ELEC COOP 69KV FEEDER 1 TO OAKLAND, GREEN VALLEY TAP TO ALVEY-FAIRVIEW NO 1 230KV LINE | LOAD, SWORE | OUT_OF_SERVICE
100 | 22-01943 | 10776055 | DART-1460684 | 07/18/2022 07:30 | 07/19/2022 16:00 | OSTRANDER: 500KV CAP GROUP 2 INCLUDING PCB 5138 | WOCS, NWACI, PDCI, WOCS, COI | OUT_OF_SERVICE
101 | 22-01643 | 10139230 | DART-1433226 | 07/18/2022 08:00 | 07/21/2022 15:00 | GRIZZLY: PCB 4222 INCLUDING 500KV REACTOR 1 | COI, NWACI, PDCI, COI, PDCI, NWACI | OUT_OF_SERVICE
102 | 22-04772 | 11342517 | DART-1481590 | 07/18/2022 08:00 | 07/20/2022 14:00 | MIDWAY: A-336 TERMINAL OF MIDWAY-A-9 SECTION OF MIDWAY-HEW NO 1 230KV LINE | GEN, TCLA, WOM | OUT_OF_SERVICE
103 | 22-02065 | 10863602 | DART-1464014 | 07/18/2022 08:00 | 07/21/2022 16:00 | ST JOHNS-DUTCH CANYON SECTION OF ST JOHNS-ST HELENS NO 1 115KV LINE | LOAD, SOA | OUT_OF_SERVICE
104 | 22-02706 | 11120667 | DART-1471684 | 07/18/2022 08:00 | 07/22/2022 15:00 | LOWER MONUMENTAL: 500KV REACTOR 1 INCLUDING PCB 4600 | WOLM, WOLM | OUT_OF_SERVICE
105 | 22-02093 | 10884869 | DART-1464284 | 07/18/2022 08:00 | 07/21/2022 15:00 | ECHO LAKE: PCB 5075 BFR | BCHT, BCHW, NOEL, SOC, WOCN, NI | OUT_OF_SERVICE
106 | 22-05984 | 11575616 |  | 07/19/2022 06:15 | 07/19/2022 16:30 | SNOHOMISH: 230KV MAIN BUS SECTION 1 INCLUDING PCB'S A-201, A-198, A-202, A-319, A-298 AND A-386 | NOEL, SOC, BCHT, BCHW, NOEL, SOC, NOEL, SOC, NOEL, SOC, BCHT, BCHW, NOEL, SOC, NOEL, SOC, NOEL, SOC, NOEL, SOC | OUT_OF_SERVICE
107 | 22-01067 | 11180083 | DART-1475374,OTS-12015 | 07/19/2022 08:15 | 07/19/2022 08:45 | GRAND COULEE: PCB 1992, PCB 1996 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
108 | 22-01068 | 11180085 | DART-1475376,OTS-12017 | 07/19/2022 09:15 | 07/19/2022 09:45 | GRAND COULEE: PCB 2092, PCB 2096 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
109 | 22-01069 | 11180086 | DART-1475378,OTS-12019 | 07/19/2022 10:15 | 07/19/2022 10:45 | GRAND COULEE: PCB 2292, PCB 2296 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
110 | 22-01070 | 11180087 | DART-1475380,OTS-12021 | 07/19/2022 11:15 | 07/19/2022 11:45 | GRAND COULEE: PCB 2392, PCB 2396 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
111 | 22-01071 | 11180091 | DART-1475382,OTS-12023 | 07/19/2022 12:45 | 07/19/2022 13:15 | GRAND COULEE: PCB 2496, PCB 2492 | GEN, WOCN, COI, NOH, NWACI, PDCI, GEN, NOH, COI, NWACI, PDCI | OUT_OF_SERVICE
112 | 22-02193 | 10914252 | DART-1465666 | 07/20/2022 09:00 | 07/20/2022 16:00 | MCMINNVILLE: PCB B-1314 , MCMINNVILLE-PGE DAYTON NO 1 115KV LINE | LOAD, SOA | OUT_OF_SERVICE
113 | 22-03179 | 11230004 | DART-1477132 | 07/21/2022 08:00 | 07/21/2022 12:00 | LOWER GRANITE: PCB 4770 | GEN, MT-NW, NOH, WOH, WOLM, GEN | OUT_OF_SERVICE
114 | 22-03878 | 11300412 | DART-1479974 | 07/21/2022 08:00 | 07/21/2022 12:00 | VANTAGE: PCB 5339 | GEN, NOH, NWACI, PDCI, WOCN, COI | OUT_OF_SERVICE
115 | 22-02556 | 11059854 | DART-1470038 | 07/21/2022 08:00 | 07/21/2022 12:00 | OSTRANDER: PCB 4432 | WOCS | OUT_OF_SERVICE
116 | 22-03182 | 11232464 | DART-1477510 | 07/21/2022 12:00 | 07/21/2022 16:00 | LOWER GRANITE: PCB 4772 | GEN, MT-NW, WOH, WOLM | OUT_OF_SERVICE
117 | 22-03879 | 11300414 | DART-1479976 | 07/21/2022 12:00 | 07/21/2022 16:00 | VANTAGE: PCB 5342 | GEN, NOH, NWACI, PDCI, WOCN, COI | OUT_OF_SERVICE
118 | 22-02557 | 11059855 | DART-1470040 | 07/21/2022 12:00 | 07/21/2022 16:00 | OSTRANDER: PCB 5139 | SOA, WOCN | OUT_OF_SERVICE
119 | 22-06291 | 11575429 | OTS-12580 | 07/22/2022 08:00 | 07/22/2022 10:00 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
120 | 22-06292 | 11575435 | OTS-12582 | 07/22/2022 10:00 | 07/22/2022 12:00 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 | GEN, NOH, COI, NWACI, PDCI, GEN, WOCN, COI, NOH, NWACI, PDCI | OUT_OF_SERVICE
121 | 22-02793 | 11120750 | DART-1472516,OTS-11863 | 07/25/2022 03:00 | 07/29/2022 17:00 | GRAND COULEE: PCB 2496 | GEN, WOCN, COI, NOH, NWACI, PDCI | OUT_OF_SERVICE
122 | 22-02598 | 11059118 | DART-1470540,OTS-11766 | 07/25/2022 05:30 | 07/29/2022 15:00 | COLUMBIA FALLS: PCB A-311 TERMINAL OF THE HUNGRY HORSE - COLUMBIA FALLS LINE NO 1 230KV LINE | WOH, WOH, MT-NW, GEN, MT-NW | OUT_OF_SERVICE
123 | 22-01175 | 11368763 | DART-1390718 | 07/25/2022 06:00 | 07/29/2022 18:00 | -PACW- RUNYAN-TROUTDALE 115KV LINE | LOAD | OUT_OF_SERVICE
124 | 22-02819 | 11232556 | DART-1472658 | 07/25/2022 06:00 | 07/28/2022 16:00 | GARRISON: 500KV REACTOR #4 RELAY SETS 1 & 2 (REACTOR 4 OUT OF SERVICE) | MT-NW | OUT_OF_SERVICE
125 | 22-02192 | 10912311 | DART-1465664,OTS-11106 | 07/25/2022 07:00 | 08/05/2022 17:00 | LOWER MONUMENTAL: 4318 TERMINAL OF LOWER MONUMENTAL PH-LOWER MONUMENTAL NO 1 500KV LINE | GEN | OUT_OF_SERVICE
126 | 22-04983 | 11428362 | DART-1483878,OTS-12360 | 07/25/2022 07:00 | 07/28/2022 16:00 | JOHN DAY: 4165/4166 TERMINAL OF JOHN DAY PH-JOHN DAY NO 3 500KV LINE | GEN, NWACI, COI, FCRPS, PDCI, SIG, WOJD | OUT_OF_SERVICE
127 | 22-02658 | 11120714 | DART-1471040 | 07/25/2022 07:00 | 07/28/2022 16:00 | GARRISON: PCB 4418 | MT-NW | OUT_OF_SERVICE
128 | 22-01264 | 9759672 | DART-1421106 | 07/25/2022 07:00 | 08/14/2022 16:00 | CENTRALIA SWITCHING STATION-TPWR COWLITZ SECTION OF CHEHALIS-COVINGTON NO 1 230KV LINE | PA, RP, NOEL, SOC | OUT_OF_SERVICE
129 | 22-00607 | 10912568 | DART-1465858 | 07/25/2022 07:00 | 07/25/2022 17:00 | JONES CANYON: 230KV REACTIVE BUS INCLUDING 230KV CAP GROUP 1 SECTION 1 & 2, PCB'S A-1688 & A-1689 | WOCS, WOCS, WOCS, WOCS, WOCS, WOCS | OUT_OF_SERVICE
130 | 22-01258 | 9759650 | DART-1421798 | 07/25/2022 07:00 | 07/25/2022 08:00 | TPWR COWLITZ-COVINGTON SECTION OF CHEHALIS-COVINGTON NO 1 230KV LINE, COWLITZ TAP TO CHEHALIS-COVINGTON NO 1 230KV LINE | PA, RP, LOAD, PA, RP, BCHT, BCHW, NOEL, SOC | OUT_OF_SERVICE
131 | 22-02786 | 11233393 | DART-1472438 | 07/25/2022 07:30 | 07/29/2022 15:00 | ABERDEEN: 230/115KV TRANSFORMER 4, SATSOP-ABERDEEN NO 2 230KV LINE | PA, LOAD, LOAD, PA, SI, SI | OUT_OF_SERVICE
132 | 22-02401 | 11100119 | DART-1468424 | 07/25/2022 08:00 | 08/04/2022 16:30 | TAHKENITCH-REEDSPORT NO 1 115KV LINE | SWORE, LOAD | OUT_OF_SERVICE
133 | 22-01038 | 11300476 | DART-1475168 | 07/25/2022 09:30 | 08/04/2022 14:00 | CAPTAIN JACK: PCB 4998 INCLUDING 500KV REACTOR 1 | COI, NWACI, PDCI, COI, NWACI, PDCI | OUT_OF_SERVICE
134 | 22-02102 | 10879232 | DART-1464518,OTS-10921 | 07/25/2022 22:00 | 07/25/2022 22:30 | GRAND COULEE: PCB 1996, PCB 1992 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
135 | 22-00464 | 9692912 | DART-1416532,OTS-8622 | 07/26/2022 16:30 | 07/26/2022 17:00 | GRAND COULEE: PCB 1992, PCB 1996 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
136 | 22-04728 | 11346216 | DART-1481488 | 07/28/2022 07:00 | 07/28/2022 12:00 | BELL: 230KV CAP GROUP 10 SECTION 1 INCLUDING LBD A-925 | MT-NW, WOH | OUT_OF_SERVICE
137 | 22-04661 | 11433748 | DART-1481462 | 07/28/2022 07:30 | 07/28/2022 17:00 | LONGVIEW: 115KV SOUTH MAIN BUS INCLUDING PCB B-328 | PA, SOA, LOAD, SOA, PA, PA, SOA, PA, SOA, LOAD, LOAD | OUT_OF_SERVICE
138 | 22-02531 | 11059857 | DART-1469968 | 07/28/2022 07:30 | 07/28/2022 12:00 | OSTRANDER: PCB 4448 | WOCS | OUT_OF_SERVICE
139 | 22-04729 | 11346217 | DART-1481490 | 07/28/2022 12:00 | 07/28/2022 16:30 | BELL: 230KV CAP GROUP 10 SECTION 2 INCLUDING LBD A-926 | MT-NW, WOH | OUT_OF_SERVICE
140 | 22-02532 | 11059858 | DART-1469972 | 07/28/2022 12:00 | 07/28/2022 16:00 | OSTRANDER: PCB 4450 | WOCS | OUT_OF_SERVICE
141 | 22-02238 | 10917309 | DART-1466052,OTS-11183 | 07/28/2022 16:30 | 07/28/2022 17:00 | BIG EDDY: PCB A-824 OF THE DALLES PH-BIG EDDY NO 4 230KV LINE | GEN, FCRPS, COI, NWACI, PDCI, WOJD | OUT_OF_SERVICE
142 | 22-02663 | 11120582 | DART-1472346 | 07/29/2022 09:30 | 07/29/2022 12:00 | PAUL: PCB 4530 | RP, GEN, PA, WOCS | OUT_OF_SERVICE
143 | 22-02664 | 11120584 | DART-1472348 | 07/29/2022 12:00 | 07/29/2022 14:30 | PAUL: PCB 4532 | PA, RP, WOCS, GEN | OUT_OF_SERVICE
144 | 22-02794 | 11120751 | DART-1472518,OTS-11864 | 08/01/2022 03:00 | 08/05/2022 17:00 | GRAND COULEE: PCB 2392 | GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
145 | 22-02126 | 11080923 | DART-1464863 | 08/01/2022 07:00 | 08/11/2022 12:00 | MCNARY: 500/230KV TRANSFORMER 1 | COI, GEN, PDCI, SIG, WOJD, WOM, NWACI | OUT_OF_SERVICE
146 | 22-04056 | 11369332 | DART-1480824 | 08/01/2022 07:00 | 08/02/2022 16:00 | RAVER: PCB 4858 | NOEL, RP, SOC | OUT_OF_SERVICE
147 | 22-01911 | 10699638 | DART-1458926 | 08/01/2022 07:00 | 09/16/2022 15:30 | MCNARY-ROSS NO 1 345KV LINE, MCNARY: 345/230KV TRANSFORMER 8, ROSS: 345/230KV TRANSFORMER 4 | SOA, WOCS, WOM, GEN, SOA, WOCS, WOM, SIG, SOA, WOCS, WOM, SOA, WOCS, WOM, SOA, WOCS | OUT_OF_SERVICE
148 | 22-00841 | 11136698 | DART-1473330 | 08/01/2022 07:00 | 08/03/2022 15:00 | CHIEF JOSEPH: PCB 4588 | BCHT, BCHW, GEN, NOH, NWACI, PDCI, WOCN, COI | OUT_OF_SERVICE
149 | 22-04748 | 11342255 | DART-1481542 | 08/01/2022 07:30 | 08/02/2022 16:00 | DEXTER-PLEASANT HILL SECTION OF LOOKOUT POINT-ALVEY NO 1 115KV LINE(UNGROUNDED) | GEN | OUT_OF_SERVICE
150 | 22-02605 | 11059907 | DART-1470632,OTS-11786 | 08/01/2022 07:30 | 08/21/2022 16:00 | OLYMPIA-GRAND COULEE NO 1 287KV LINE, OLYMPIA: 287/230KV TRANSFORMER 3 | NOEL, NOH, RP, SOC, WOCN, IROL, NOEL, PA, RP, SOC, WOCN, IROL | OUT_OF_SERVICE
151 | 22-03061 | 11210987 | DART-1476746 | 08/01/2022 07:30 | 08/21/2022 16:00 | COVINGTON-BETTAS ROAD 1 230KV LINE, COVINGTON-BETTAS ROAD NO 1 230KV LINE | NOEL, SOC, WOCN, IROL | OUT_OF_SERVICE
152 | 22-03062 | 11211060 | DART-1476738 | 08/01/2022 07:30 | 08/21/2022 16:00 | BETTAS ROAD: A-3043, A-3040 TERMINALS OF THE COVINGTON-BETTAS ROAD NO 1 230KV LINE | NOEL, SOC, WOCN, NOEL, SOC, WOCN | OUT_OF_SERVICE
153 | 22-02472 | 11025107 | DART-1469352 | 08/01/2022 07:30 | 08/02/2022 15:00 | RAVER: PCB 4914 | NOEL, RP, SOC | OUT_OF_SERVICE
154 | 22-00871 | 11135001 | DART-1473874 | 08/01/2022 08:00 | 08/04/2022 15:00 | BOUNDARY-NELWAY NO 1 230KV LINE | BCHT, GEN, NI, NOEL, SOB, SOC | OUT_OF_SERVICE
155 | 22-03791 | 11300176 | DART-1479590 | 08/01/2022 08:00 | 08/01/2022 15:00 | LOWER GRANITE: PCB 4772 | GEN, MT-NW, WOH, WOLM | OUT_OF_SERVICE
156 | 22-04066 | 11337303 | DART-1480862 | 08/01/2022 08:00 | 08/25/2022 19:00 | CHIEF JOSEPH: 345/230KV TRANSFORMER 2 (CHIEF JOSEPH-SNOHOMISH 4 LINE OPERATED AT 230KV), SNOHOMISH: 345/230KV TRANSFORMER 6 | NOEL, NOH, SOC, WOCN, FCRPS, NI, NOEL, SOC, WOCN, GEN, IROL, NOH | OUT_OF_SERVICE
157 | 22-01169 | 9309407 | DART-1402938 | 08/01/2022 08:00 | 08/05/2022 16:00 | LEXINGTON: 230/115KV TRANSFORMER 1 INCLUDING 230KV MAIN BUS, 115 AUX BUS, & PCB B-1465 | PA, SOA, LOAD, PA, SOA, LOAD, LOAD, PA, RP, SOA, SOA, GEN, LOAD, SOA | OUT_OF_SERVICE
158 | 22-02403 | 11013345 | DART-1468426 | 08/01/2022 08:00 | 08/04/2022 16:30 | NORWAY-MORRISON SECTION OF FAIRVIEW-BANDON NO 1 115KV LINE | SWORE | OUT_OF_SERVICE
159 | 22-01289 | 11206149 | DART-1472338 | 08/01/2022 08:00 | 08/25/2022 17:00 | WREN-TOLEDO SECTION OF SANTIAM-TOLEDO NO 1 230KV LINE INCLUDING TOLEDO: PCB A-1472 | SWORE, LOAD, LOAD | OUT_OF_SERVICE
160 | 22-01660 |  | DART-1437826 | 08/01/2022 08:00 | 08/31/2022 16:00 | PGE - HARBORTON-RIVERGATE 1 230KV LINE | SOA | OUT_OF_SERVICE
161 | 22-04064 | 11337305 | DART-1480876 | 08/01/2022 08:00 | 08/01/2022 10:00 | CHIEF JOSEPH-SNOHOMISH NO 4 345KV LINE, CHIEF JOSEPH: 345/230KV TRANSFORMER 2, SNOHOMISH: 345/230KV TRANSFORMER 6 | NOEL, NOH, SOC, WOCN, FCRPS, NI, NOEL, SOC, WOCN, GEN, IROL, NOH, GEN, IROL, NOEL, NOH, SOC, WOCN | OUT_OF_SERVICE
162 | 22-01281 | 9801605 | DART-1423902 | 08/01/2022 08:30 | 08/31/2022 12:00 | ROGUE: 230/115KV TRANSFORMER 1 | SWORE, LOAD, SWORE, SIG | OUT_OF_SERVICE
163 | 22-04058 | 11603998 | DART-1480878 | 08/02/2022 07:00 | 08/02/2022 16:00 | SCHULTZ: PCB 5148 BFR | WOCN | OUT_OF_SERVICE
164 | 22-03851 | 11313527 | DART-1479844 | 08/02/2022 08:00 | 08/03/2022 14:30 | HATWAI: PCB 4710 | GEN, MT-NW, NOH, WOH, WOLM | OUT_OF_SERVICE
165 | 22-02119 | 10888978 | DART-1464854 | 08/02/2022 08:00 | 08/02/2022 16:00 | PEARL: PCB 4280 | SOA | OUT_OF_SERVICE
166 | 22-03520 | 11282975 | DART-1479074,OTS-12145 | 08/02/2022 08:15 | 08/02/2022 08:45 | GRAND COULEE: PCB 1996, PCB 1992 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
167 | 22-03676 | 11350846 | DART-1479406 | 08/02/2022 08:30 | 08/03/2022 15:00 | NAPAVINE: 500KV PCB 5232 BFR | PA | OUT_OF_SERVICE
168 | 22-03521 | 11282977 | DART-1479076,OTS-12147 | 08/02/2022 09:15 | 08/02/2022 09:45 | GRAND COULEE: PCB 2096, PCB 2092 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
169 | 22-03522 | 11282978 | DART-1479078,OTS-12149 | 08/02/2022 10:15 | 08/02/2022 10:45 | GRAND COULEE: PCB 2296, PCB 2292 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
170 | 22-03523 | 11282979 | DART-1479080,OTS-12151 | 08/02/2022 11:15 | 08/02/2022 11:45 | GRAND COULEE: PCB 2396, PCB 2392 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
171 | 22-03524 | 11282981 | DART-1479082,OTS-12153 | 08/02/2022 12:45 | 08/02/2022 13:15 | GRAND COULEE: PCB 2492, PCB 2496 | GEN, NOH, COI, NWACI, PDCI, GEN, WOCN, COI, NOH, NWACI, PDCI | OUT_OF_SERVICE
172 | 22-04059 | 11604030 | DART-1480882 | 08/03/2022 07:00 | 08/03/2022 16:00 | SCHULTZ: PCB 5151 BFR | WOCN | OUT_OF_SERVICE
173 | 22-04767 | 11342457 | DART-1481564 | 08/03/2022 07:30 | 08/04/2022 16:00 | PLEASANT HILL-ALVEY SECTION OF LOOKOUT POINT-ALVEY NO 1 115KV LINE(UNGROUNDED) | GEN | OUT_OF_SERVICE
174 | 22-02474 | 11025111 | DART-1469354 | 08/03/2022 08:00 | 08/04/2022 15:00 | RAVER: PCB 4921 | NOEL, RP, SOC | OUT_OF_SERVICE
175 | 22-05366 |  | DART-1485290 | 08/03/2022 22:00 | 08/14/2022 06:00 | -EWEB- MCKENZIE EWEB: 1M33 TERMINAL OF THE DIAMOND HILL SECTION OF ALVEY-DIAMOND HILL NO 3 230KV LINE INCLUDING |  | OUT_OF_SERVICE
176 | 22-05367 |  | DART-1485288 | 08/03/2022 22:00 | 08/14/2022 06:00 | -PACW- MCKENZIE-DIAMOND HILL SECTION OF ALVEY-DIAMOND HILL NO 3 230KV LINE | NWACI, PDCI, COI | OUT_OF_SERVICE
177 | 22-02516 | 11035687 | DART-1469718 | 08/04/2022 08:00 | 08/04/2022 12:00 | OSTRANDER: PCB 4450 | WOCS | OUT_OF_SERVICE
178 | 22-02517 | 11035700 | DART-1469720 | 08/04/2022 12:00 | 08/04/2022 16:00 | OSTRANDER: PCB 5134 | WOCS | OUT_OF_SERVICE
179 | 22-04752 | 11342500 | DART-1481558 | 08/05/2022 07:30 | 08/05/2022 16:00 | MT. VERNON-ALVEY SECTION OF LOOKOUT POINT-ALVEY NO 2 115KV LINE INCLUDING MT. VERNON TAP (UNGROUNDED), MT. VERNON: SPRNGFLD UTIL BRD 115KV FEEDER 1 | GEN, GEN | OUT_OF_SERVICE
180 | 22-04768 | 11342495 | DART-1481576 | 08/06/2022 07:30 | 08/06/2022 16:00 | LOOKOUT POINT- MT.VERNON SECTION OF LOOKOUT POINT-ALVEY NO 2 115KV LINE (UNGROUNDED) | GEN | OUT_OF_SERVICE
181 | 22-02715 | 11176227 | DART-1471778,OTS-12008 | 08/06/2022 22:30 | 08/07/2022 08:00 | OAKRIDGE: LBD B-367, LANE ELEC COOP 115KV FEEDER 1, OAKRIDGE: LANE ELEC COOP 115KV FEEDER 1, OAKRIDGE-LOOKOUT POINT SECTION OF HILLS CREEK-LOOKOUT POINT NO 1 115KV LINE | PDCI, COI | OUT_OF_SERVICE
182 | 22-02795 | 11120752 | DART-1472520,OTS-11865 | 08/08/2022 03:00 | 08/12/2022 17:00 | GRAND COULEE: PCB 2396 | GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
183 | 22-01869 | 10670162 | DART-1457732,OTS-10663 | 08/08/2022 06:00 | 08/08/2022 18:00 | LOWER GRANITE: 4771/4773 TERMINAL OF LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE (UNGROUNDED) | GEN, GEN, MT-NW, NOH, WOH, WOLM, GEN, MT-NW, WOH, WOLM | OUT_OF_SERVICE
184 | 22-02820 | 11232537 | DART-1472660 | 08/08/2022 06:00 | 08/11/2022 16:00 | GARRISON: 500KV REACTOR #3 RELAY SETS 1 & 2 (REACTOR 3 OUT OF SERVICE) | MT-NW | OUT_OF_SERVICE
185 | 22-02656 | 11108932 | DART-1471032 | 08/08/2022 07:00 | 08/11/2022 16:00 | GARRISON: PCB 4415 | MT-NW | OUT_OF_SERVICE
186 | 22-04062 | 11604109 | DART-1480852 | 08/08/2022 07:00 | 08/08/2022 16:00 | SCHULTZ: PCB 5170 BFR | WOCN | OUT_OF_SERVICE
187 | 22-00785 | 11125539 | DART-1473086 | 08/08/2022 08:00 | 08/18/2022 14:30 | ROGUE-GOLD BEACH NO 1 115KV LINE , BANDON-ROGUE NO 1 115KV LINE | SWORE | OUT_OF_SERVICE
188 | 22-02109 | 10912330 | DART-1464706 | 08/08/2022 09:00 | 08/11/2022 16:00 | MARION: PCB 4371 | NWACI, PDCI, WOCS, COI | OUT_OF_SERVICE
189 | 22-01865 | 10670164 | DART-1457920,OTS-10702 | 08/09/2022 06:00 | 08/09/2022 18:00 | LOWER GRANITE: 4771/4773 TERMINAL OF LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE (UNGROUNDED) | GEN, GEN, MT-NW, NOH, WOH, WOLM, GEN, MT-NW, WOH, WOLM | OUT_OF_SERVICE
190 | 22-04060 | 11604087 | DART-1480888 | 08/09/2022 07:00 | 08/09/2022 16:00 | SCHULTZ: PCB 5154 BFR | WOCN | OUT_OF_SERVICE
191 | 22-01866 | 10670167 | DART-1457922,OTS-10703 | 08/10/2022 06:00 | 08/10/2022 18:00 | LOWER GRANITE: 4771/4773 TERMINAL OF LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE (UNGROUNDED) | GEN, GEN, MT-NW, NOH, WOH, WOLM, GEN, MT-NW, WOH, WOLM | OUT_OF_SERVICE
192 | 22-04061 | 11604104 | DART-1480890 | 08/10/2022 07:00 | 08/10/2022 16:00 | SCHULTZ: PCB 5157 BFR | WOCN | OUT_OF_SERVICE
193 | 22-01867 | 10670169 | DART-1457924,OTS-10704 | 08/11/2022 06:00 | 08/11/2022 18:00 | LOWER GRANITE: 4771/4773 TERMINAL OF LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE (UNGROUNDED) | GEN, GEN, MT-NW, NOH, WOH, WOLM, GEN, MT-NW, WOH, WOLM | OUT_OF_SERVICE
194 | 22-05171 | 11487829 | DART-1484694 | 08/11/2022 09:00 | 08/11/2022 12:00 | CENTRAL FERRY: PCB 5415 | MT-NW, WOH, WOLM, SIG | OUT_OF_SERVICE
195 | 22-05553 | 11487758 |  | 08/11/2022 09:00 | 08/11/2022 12:00 | LITTLE GOOSE: PCB 4350 | WOLM | OUT_OF_SERVICE
196 | 22-05453 | 11487838 |  | 08/11/2022 12:00 | 08/11/2022 15:00 | CENTRAL FERRY: PCB 5418 | MT-NW, WOH, WOLM | OUT_OF_SERVICE
197 | 22-05554 | 11487778 |  | 08/11/2022 12:00 | 08/11/2022 15:00 | LITTLE GOOSE: PCB 4632 | WOLM | OUT_OF_SERVICE
198 | 22-01868 | 10670184 | DART-1457926,OTS-10705 | 08/12/2022 06:00 | 08/12/2022 18:00 | LOWER GRANITE: 4771/4773 TERMINAL OF LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE (UNGROUNDED) | GEN, GEN, MT-NW, NOH, WOH, WOLM, GEN, MT-NW, WOH, WOLM | OUT_OF_SERVICE
199 | 22-02716 | 11176235 | DART-1471786,OTS-12009 | 08/13/2022 22:30 | 08/14/2022 08:00 | OAKRIDGE: LBD B-367, LANE ELEC COOP 115KV FEEDER 1, OAKRIDGE: LANE ELEC COOP 115KV FEEDER 1, OAKRIDGE-LOOKOUT POINT SECTION OF HILLS CREEK-LOOKOUT POINT NO 1 115KV LINE | PDCI, COI | OUT_OF_SERVICE
200 | 22-01259 | 9759668 | DART-1421802 | 08/14/2022 15:00 | 08/14/2022 16:00 | TPWR COWLITZ-COVINGTON SECTION OF CHEHALIS-COVINGTON NO 1 230KV LINE INCLUDING COWLITZ TAP | PA, RP, LOAD, PA, RP, BCHT, BCHW, NOEL, SOC | OUT_OF_SERVICE
201 | 22-02796 | 11120755 | DART-1472522,OTS-11866 | 08/15/2022 03:00 | 08/19/2022 17:00 | GRAND COULEE: PCB 9292 | GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
202 | 22-03716 | 11309791 | DART-1479504,OTS-12177 | 08/15/2022 06:00 | 08/31/2022 16:00 | GRAND COULEE-CHIEF JOSEPH NO 1 230KV LINE (UNGROUNDED) | GEN, NOH, FCRPS | OUT_OF_SERVICE
203 | 22-03912 | 11312941 | DART-1480238,OTS-12212 | 08/15/2022 06:30 | 08/15/2022 07:00 | MCNARY: PCB B-990 OF MCNARY PH-MCNARY NO 6 115KV LINE | GEN, FCRPS, WOM | OUT_OF_SERVICE
204 | 22-02660 | 11155950 | DART-1471066 | 08/15/2022 07:00 | 08/18/2022 16:00 | GARRISON: TAFT 2 500KV LINE SERIES CAP GROUP 2 INCLUDING PCB 4458 | MT-NW, MT-NW | OUT_OF_SERVICE
205 | 22-01260 | 9761304 | DART-1421108 | 08/15/2022 07:00 | 08/21/2022 16:00 | CHEHALIS-CENTRALIA SWITCHING STATION SECTION OF CHEHALIS-COVINGTON NO 1 230KV LINE | PA, RP | OUT_OF_SERVICE
206 | 22-02122 | 11314580 | DART-1464859 | 08/15/2022 07:00 | 08/25/2022 15:00 | MCNARY: 230/115/13.2KV TRANSFORMER #9, MCNARY: 230/115KV TRANSFORMER 9 | WOM | OUT_OF_SERVICE
207 | 22-02785 | 11104836 | DART-1472442 | 08/15/2022 07:30 | 08/19/2022 15:00 | ABERDEEN: 230/115KV TRANSFORMER 4, SATSOP-ABERDEEN NO 2 230KV LINE | PA, LOAD, LOAD, PA, SI, SI | OUT_OF_SERVICE
208 | 22-01922 | 10951925 | DART-1459530 | 08/15/2022 07:30 | 08/18/2022 16:30 | ALLSTON: 500/230KV TRANSFORMER 1 | SIG, SOA, PA, SOA, PA, SOA | OUT_OF_SERVICE
209 | 22-03584 | 11300194 | DART-1479190 | 08/15/2022 07:30 | 08/17/2022 15:00 | MALIN: PCB 4064 | NWACI, PDCI, COI | OUT_OF_SERVICE
210 | 22-04757 | 11427923 | DART-1483514 | 08/15/2022 08:00 | 08/26/2022 16:00 | PLEASANT HILL-ALVEY SECTION OF LOOKOUT POINT-ALVEY NO 1 115KV LINE (UNGROUNDED) | GEN | OUT_OF_SERVICE
211 | 22-04758 | 11427930 | DART-1483526 | 08/15/2022 08:00 | 08/25/2022 19:00 | ALVEY-GOSHEN (PACW) SECTION OF ALVEY-MARTIN CREEK NO 1 115KV LINE, VILLAGE GREEN-DORENA SECTION OF ALVEY-MARTIN CREEK NO 1 115KV LINE | LOAD | OUT_OF_SERVICE
212 | 22-02121 | 10888980 | DART-1464858 | 08/15/2022 08:00 | 08/15/2022 16:00 | PEARL: PCB 5458 | SOA | OUT_OF_SERVICE
213 | 22-02095 | 10884879 | DART-1464286 | 08/15/2022 08:00 | 08/18/2022 15:00 | ECHO LAKE: PCB 5078 | BCHT, BCHW, NOEL, SOC, WOCN, NI | OUT_OF_SERVICE
214 | 22-06187 | 11587862 |  | 08/15/2022 08:30 | 09/09/2022 15:00 | ADDY-BOUNDARY SECTION OF BELL-BOUNDARY NO 3 230KV LINE | SOB, GEN, BCHT, GEN, MT-NW, SOB | OUT_OF_SERVICE
215 | 22-04762 | 11427971 | DART-1483562 | 08/16/2022 07:00 | 08/18/2022 16:00 | ALVEY-CURRIN 115KV LINE | NWACI, PDCI, COI | OUT_OF_SERVICE
216 | 22-04916 | 11382303 | DART-1482920,OTS-12312 | 08/16/2022 08:15 | 08/16/2022 08:45 | GRAND COULEE: PCB 1992, PCB 1996 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
217 | 22-04917 | 11382304 | DART-1482922,OTS-12314 | 08/16/2022 09:15 | 08/16/2022 09:45 | GRAND COULEE: PCB 2092, PCB 2096 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
218 | 22-04918 | 11382305 | DART-1482924,OTS-12316 | 08/16/2022 10:15 | 08/16/2022 10:45 | GRAND COULEE: PCB 2292, PCB 2296 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
219 | 22-04919 | 11382306 | DART-1482928,OTS-12318 | 08/16/2022 11:15 | 08/16/2022 11:45 | GRAND COULEE: PCB 2392, PCB 2396 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
220 | 22-04920 | 11382308 | DART-1482930,OTS-12320 | 08/16/2022 12:45 | 08/16/2022 13:15 | GRAND COULEE: PCB 2496, PCB 2492 | GEN, WOCN, COI, NOH, NWACI, PDCI, GEN, NOH, COI, NWACI, PDCI | OUT_OF_SERVICE
221 | 22-00992 | 11156894 | DART-1463200,OTS-11855 | 08/18/2022 07:00 | 08/18/2022 16:00 | GRAND COULEE-HANFORD NO 1 500KV LINE INCLUDING HANFORD PCB 4089 | NOH, NWACI, PDCI, COI, WOM, WOS, BCHT, BCHW, GEN, NI, NOH, SIG, COI, NWACI, PDCI, WOCN | OUT_OF_SERVICE
222 | 22-04671 | 11345434 | DART-1481676 | 08/18/2022 07:30 | 08/18/2022 11:00 | SCHULTZ: PCB 5154 | WOCN | OUT_OF_SERVICE
223 | 22-04672 | 11345435 | DART-1481678 | 08/18/2022 11:00 | 08/18/2022 15:00 | SCHULTZ: PCB 5157 | WOCN | OUT_OF_SERVICE
224 | 22-00993 | 11156982 | DART-1474728 | 08/18/2022 16:00 | 08/19/2022 07:00 | HANFORD: PCB 4089 | NOH, NWACI, PDCI, COI, WOM, WOS | OUT_OF_SERVICE
225 | 22-00994 | 11156902 | DART-1440962,OTS-10104 | 08/19/2022 07:00 | 08/19/2022 16:00 | HANFORD: 500KV NORTH BUS INCLUDING PCB 4089 | COI, NOH, NWACI, PDCI, WOM, WOS, NOH, NWACI, PDCI, COI, WOM, WOS | OUT_OF_SERVICE
226 | 22-02603 | 11059981 | DART-1470630 | 08/22/2022 06:00 | 08/26/2022 18:00 | COVINGTON: 230KV MAIN BUS SECTION 1 INCLUDING PCB A-692 AND RAVER-COVINGTON NO 3 230KV LINE | NOEL, SOC, WOCN, NOEL, SOC, BCHT, BCHW, NOEL, RP, SOC, NOEL, SOC, NOEL, SOC, NOEL, RP, SOC, PA, RP, NOEL, RP, SOC, NOEL, SOC, NOEL, SOC, NOEL, SOC, BCHT, BCHW, RP, NOEL, SOC, NOEL, SOC, NOEL, RP, SOC, WOCN, NOEL, SOC, NOEL, SOC | OUT_OF_SERVICE
227 | 22-04702 | 11337200 | DART-1481290,OTS-12255 | 08/22/2022 07:00 | 08/22/2022 09:00 | LOWER MONUMENTAL: 4318 TERMINAL OF LOWER MONUMENTAL PH-LOWER MONUMENTAL NO 1 500KV LINE | GEN | OUT_OF_SERVICE
228 | 22-03123 | 11215567 | DART-1476954 | 08/22/2022 07:00 | 08/26/2022 15:00 | CHEHALIS: 230/115KV TRANSFORMER 2 | LOAD, PA, LOAD | OUT_OF_SERVICE
229 | 22-02661 | 11120726 | DART-1471070 | 08/22/2022 07:00 | 08/23/2022 16:00 | GARRISON: BROADVIEW 1 500KV LINE SERIES CAP GROUP 1 INCL PCB 4469 | MT-NW, MT-NW | OUT_OF_SERVICE
230 | 22-01261 | 9761343 | DART-1421114 | 08/22/2022 07:00 | 09/16/2022 16:00 | TPWR COWLITZ-COVINGTON SECTION OF CHEHALIS-COVINGTON NO 1 230KV LINE | PA, RP | OUT_OF_SERVICE
231 | 22-01262 | 9761346 | DART-1421918 | 08/22/2022 07:00 | 08/22/2022 08:00 | CENTRALIA SWITCHING STATION-TPWR COWLITZ SECTION OF CHEHALIS-COVINGTON NO 1 230KV LINE INCLUDING COWLITZ TAP | PA, RP, NOEL, SOC, PA, RP, LOAD, BCHT, BCHW, NOEL, SOC | OUT_OF_SERVICE
232 | 22-02338 | 11131096 | DART-1467260 | 08/22/2022 07:30 | 08/25/2022 16:00 | ALLSTON: 230/115KV TRANSFORMER 3 | SOA, LOAD, SOA | OUT_OF_SERVICE
233 | 22-01290 | 9878455 | DART-1424634 | 08/22/2022 07:30 | 09/16/2022 16:00 | SANTIAM-WREN SECTION OF SANTIAM-TOLEDO NO 1 230KV LINE INCLUDING SANTIAM: PCB A-524 AND 230KV AUX BUS | SWORE, LOAD, COI, PDCI, NWACI | OUT_OF_SERVICE
234 | 22-03783 | 11350854 | DART-1479572 | 08/22/2022 07:30 | 08/25/2022 16:00 | NAPAVINE: 500KV PCB 5229 BFR AND PCB DIFF RELAY | GEN, NWACI, PA, PDCI, COI | OUT_OF_SERVICE
235 | 22-03585 | 11300199 | DART-1479192 | 08/22/2022 07:30 | 08/24/2022 15:00 | MALIN: PCB 4186 | NWACI, PDCI, RATS, COI | OUT_OF_SERVICE
236 | 22-02406 | 11175525 | DART-1468442 | 08/22/2022 08:00 | 09/08/2022 16:30 | HAUSER-GLASGOW SECTION OF REEDSPORT-FAIRVIEW NO 1 115KV LINE | LOAD, SWORE | OUT_OF_SERVICE
237 | 22-05597 | 11493040 |  | 08/22/2022 08:00 | 11/18/2022 15:00 | BETTAS ROAD-COLUMBIA NO 1 230KV LINE INCLUDING BETTAS ROAD 230KV EAST BUS AND PCB A-3046 | NOEL, SOC, WOCN, WOCN, CI, NOEL, NOH, SOC, WOCN, IROL, NOEL, SOC, WOCN, NOEL, SOC, WOCN | OUT_OF_SERVICE
238 | 22-03771 | 11228834 | DART-1476724 | 08/22/2022 08:00 | 08/26/2022 15:00 | CENTRAL FERRY: 500/230KV TRANSFORMER 1 INCLUDING PCB'S A-1762 & A-1766 | WOLM, WOLM, GEN, SIG, WOLM, GEN, SIG, WOLM, WOH, WOLM | OUT_OF_SERVICE
239 | 22-00324 | 11009037 | DART-1469358,OTS-11684 | 08/23/2022 16:30 | 08/23/2022 17:00 | THE DALLES PH-BIG EDDY NO 6 230KV LINE | GEN, FCRPS | OUT_OF_SERVICE
240 | 22-02662 | 11120732 | DART-1471078 | 08/24/2022 07:00 | 08/25/2022 16:00 | GARRISON: BROADVIEW 2 500KV LINE SERIES CAP GROUP 2 INCL PCB 4468 | MT-NW, MT-NW | OUT_OF_SERVICE
241 | 22-02118 | 10910752 | DART-1464746 | 08/24/2022 08:30 | 08/24/2022 16:00 | SANTIAM: 230KV REACTIVE GROUP 1 CAP SECTION 1 INCLUDING PCB A-502 | COI, PDCI, NWACI, COI, NWACI, PDCI | OUT_OF_SERVICE
242 | 22-02111 | 10912339 | DART-1464710 | 08/25/2022 09:00 | 08/25/2022 16:00 | MARION: 500KV REACTOR 1 INCLUDING PCB 4012 | COI | OUT_OF_SERVICE
243 | 22-04065 | 11337308 | DART-1480886 | 08/25/2022 17:00 | 08/25/2022 19:00 | CHIEF JOSEPH-SNOHOMISH NO 4 345KV LINE, CHIEF JOSEPH: 345/230KV TRANSFORMER 2, SNOHOMISH: 345/230KV TRANSFORMER 6 | NOEL, NOH, SOC, WOCN, FCRPS, NI, NOEL, SOC, WOCN, GEN, IROL, NOH, GEN, IROL, NOEL, NOH, SOC, WOCN | OUT_OF_SERVICE
244 | 22-00920 | 11237846 | DART-1474060 | 08/29/2022 06:30 | 08/29/2022 17:00 | LOWER MONUMENTAL-HANFORD NO 1 500KV LINE INCLUDING HANFORD 500KV NORTH BUS AND PCB 4095 | COI, NOH, NWACI, PDCI, WOM, WOS, NOH, NWACI, PDCI, SIG, WOLM, COI, GEN, NWACI, PDCI, WOLM, COI, NOH, WOM, WOS, GEN, NWACI, PDCI, WOLM, COI, NOH, WOM, WOS | OUT_OF_SERVICE
245 | 22-02505 | 11017829 | DART-1469566,OTS-11718 | 08/29/2022 06:30 | 08/29/2022 07:00 | MCNARY: PCB A-420 OF THE PH-MCNARY NO 3&4 230KV LINE | GEN, WOM | OUT_OF_SERVICE
246 | 22-02476 | 11369588 | DART-1469366 | 08/29/2022 07:30 | 08/30/2022 09:00 | RAVER: PCB 4917 BFR | NOEL, RP, SOC, IROL, WOCN, NOEL, RP, SOC | OUT_OF_SERVICE
247 | 22-04668 | 11337184 | DART-1481282 | 08/29/2022 08:00 | 09/09/2022 17:30 | VANTAGE: A-1152 TERMINAL OF 500/230KV TRANSFORMER 2 | NOH | OUT_OF_SERVICE
248 | 22-06520 | 11596836 |  | 08/29/2022 08:00 | 09/02/2022 16:00 | LOWER MONUMENTAL: 500KV WEST BUS INCLUDING PCB 4263 | WOLM, WOLM | OUT_OF_SERVICE
249 | 22-00609 | 10916829 | DART-1465836 | 08/29/2022 08:00 | 08/29/2022 13:00 | SANTIAM: 230KV WEST MAIN BUS INCLUDING PCB'S A-514, A-516, & A-520 | COI, PDCI, NWACI, SIG, COI, PDCI, NWACI, COI, PDCI, NWACI, COI, PDCI, NWACI, COI, PDCI, NWACI, COI, PDCI, NWACI, COI, PDCI, SWORE, LOAD, GEN, WOCS, WOM, NWACI, PDCI, WOCS, COI, LOAD, NWACI, PDCI, COI | OUT_OF_SERVICE
250 | 22-04010 | 11337227 | DART-1480632 | 08/29/2022 08:00 | 09/09/2022 17:30 | VANTAGE: 500/230KV TRANSFORMER 2, VANTAGE SUBSTATION 500/230KV TIE NO 1 230KV LINE | GEN, NOH, NWACI, SIG, COI, RATS, WI | OUT_OF_SERVICE
251 | 22-00817 | 11135857 | DART-1473232 | 08/29/2022 08:00 | 09/02/2022 15:30 | MOSSYROCK-CHEHALIS NO 1 230KV LINE (UNGROUNDED) | PA, RP, PA | OUT_OF_SERVICE
252 | 22-04802 | 11350615 | DART-1481928 | 08/29/2022 08:00 | 09/09/2022 16:00 | ELLENSBURG-CLYMER SECTION OF ELLENSBURG-MOXEE NO 1 115KV LINE | TCLA | OUT_OF_SERVICE
253 | 22-01755 | 11045182 | DART-1451080 | 08/29/2022 09:00 | 08/31/2022 17:00 | HARNEY: 115KV MAIN BUS INCLUDING PCB B-1708, PCB B-1710 AND THE 115KV REACTIVE GROUP 1 | LOAD, LOAD, ID-NW | OUT_OF_SERVICE
254 | 22-00917 | 11237862 | DART-1474086 | 08/29/2022 17:00 | 10/31/2022 07:30 | HANFORD: PCB 4098 INCLUDING MODS 4097 & 4099 | GEN, NWACI, PDCI, WOLM, COI, NOH, WOM, WOS | OUT_OF_SERVICE
255 | 22-04817 | 11363541 | DART-1482034 | 08/30/2022 06:30 | 09/02/2022 16:00 | MAPLE VALLEY: 500/230KV TRANSFORMER 2, ECHO LAKE-MAPLE VALLEY NO 1&2 500KV LINE | IROL, NOEL, SIG, SOC, WOCN, IROL, NOEL, SIG, SOC, WOCN | OUT_OF_SERVICE
256 | 22-04642 | 11369592 | DART-1482568 | 08/30/2022 07:00 | 08/30/2022 09:00 | RAVER: PCB 4914 | NOEL, RP, SOC | OUT_OF_SERVICE
257 | 22-04965 | 11422339 | DART-1483756,OTS-12332 | 08/30/2022 08:15 | 08/30/2022 08:45 | GRAND COULEE: PCB 1996, PCB 1992 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
258 | 22-02477 | 11369597 | DART-1469368 | 08/30/2022 09:00 | 08/31/2022 09:00 | RAVER: PCB 4919 BFR | NOEL, RP, SOC, IROL, WOCN, NOEL, RP, SOC | OUT_OF_SERVICE
259 | 22-04960 | 11422342 | DART-1483746,OTS-12334 | 08/30/2022 09:15 | 08/30/2022 09:45 | GRAND COULEE: PCB 2096, PCB 2092 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
260 | 22-04962 | 11422345 | DART-1483750,OTS-12336 | 08/30/2022 10:15 | 08/30/2022 10:45 | GRAND COULEE: PCB 2296, PCB 2292 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
261 | 22-04963 | 11422370 | DART-1483752,OTS-12338 | 08/30/2022 11:15 | 08/30/2022 11:45 | GRAND COULEE: PCB 2396, PCB 2392 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
262 | 22-04964 | 11422375 | DART-1483754,OTS-12340 | 08/30/2022 12:45 | 08/30/2022 13:15 | GRAND COULEE: PCB 2492, PCB 2496 | GEN, NOH, COI, NWACI, PDCI, GEN, WOCN, COI, NOH, NWACI, PDCI | OUT_OF_SERVICE
263 | 22-02479 | 11369604 | DART-1469374 | 08/31/2022 09:00 | 09/01/2022 10:00 | RAVER: PCB 4722 BFR | NOEL, RP, SOC, IROL, WOCN, NOEL, RP, SOC | OUT_OF_SERVICE
264 | 22-04643 | 11369605 | DART-1482572 | 09/01/2022 07:00 | 09/01/2022 10:00 | RAVER: PCB 4921 | NOEL, RP, SOC | OUT_OF_SERVICE
265 | 22-01184 | 10085244 | DART-1433846 | 09/01/2022 08:00 | 10/27/2022 14:00 | BENTON-RINGOLD SECTION OF BENTON-SCOOTENEY NO 1 115KV LINE, MIDWAY-SCOOTENEY TAP SECTION OF MIDWAY-BENTON NO 1 115KV LINE | TCLA, TCLA, GEN | OUT_OF_SERVICE
266 | 22-03824 | 11300215 | DART-1479754 | 09/01/2022 09:30 | 09/01/2022 10:30 | MALIN: PCB 4064 | NWACI, PDCI, COI | OUT_OF_SERVICE
267 | 22-03823 | 11300223 | DART-1479756 | 09/01/2022 10:30 | 09/01/2022 11:30 | MALIN: PCB 4186 | NWACI, PDCI, RATS, COI | OUT_OF_SERVICE
268 | 22-06528 | 11596882 |  | 09/02/2022 16:01 | 09/26/2022 07:59 | LOWER MONUMENTAL: PCB 4263 AND MOD 4257 | WOLM | OUT_OF_SERVICE
269 | 22-01210 | 9551422 | DART-1405218,OTS-7756 | 09/05/2022 05:00 | 09/22/2022 17:30 | CHIEF JOSEPH: 4731/4734 TERMINAL OF CHIEF JOSEPH PH-CHIEF JOSEPH NO 6 500KV LINE | GEN, FCRPS, NOH | OUT_OF_SERVICE
270 | 22-02408 | 10982948 | DART-1468446,OTS-11462 | 09/05/2022 07:00 | 09/15/2022 17:00 | JOHN DAY: 4174/4175 TERMINAL OF JOHN DAY PH-JOHN DAY NO 4 500KV LINE | GEN, NWACI, COI, FCRPS, PDCI, SIG, WOJD | OUT_OF_SERVICE
271 | 22-05202 | 11438861 | DART-1484824,OTS-12408 | 09/06/2022 06:30 | 09/23/2022 17:00 | BELL: A-558 TERMINAL OF THE GRAND COULEE-BELL NO 3 230KV LINE (UNGROUNDED) | NOH, WOCN, COI, NWACI, PDCI, NOH, WOH, COI, NWACI, PDCI | OUT_OF_SERVICE
272 | 22-02452 | 11034636 | DART-1469242 | 09/06/2022 07:00 | 09/08/2022 17:00 | MONROE: PCB 4513 INCLUDING 500KV CAP GROUP 4 AND PCB 4508 | BCHT, BCHW, NOEL, SOC, NI, IROL, NI, NOEL, SOC, WOCN, BCHT, NOEL, SOC, WOCN, NI | OUT_OF_SERVICE
273 | 22-05727 | 11508102 |  | 09/06/2022 07:00 | 09/06/2022 16:00 | COYOTE SPRINGS: PCB 5193 | GEN, NWACI, PDCI, WOLM, WOM, COI | OUT_OF_SERVICE
274 | 22-00812 | 11136746 | DART-1473184 | 09/06/2022 07:00 | 09/15/2022 16:00 | TAFT-BELL NO 1 500KV LINE INCLUDING BELL: 500KV LINE SERIES CAP GROUP 1 AND PCB 5320 | GEN, MT-NW, SIG, WOH, COI, NWACI, RATS, RP, MT-NW, WOH, WOH, MT-NW, WOH, MT-NW, WOH, GEN, MT-NW, WOH, GEN, MT-NW, WOH, MT-NW, WOH, GEN, MT-NW, WOH | OUT_OF_SERVICE
275 | 22-06163 | 11576327 |  | 09/06/2022 07:30 | 09/08/2022 15:30 | PAUL: PCB 4550 | NWACI, PA, PDCI, COI, WOCS | OUT_OF_SERVICE
276 | 22-00818 | 11135910 | DART-1473234 | 09/06/2022 08:00 | 09/09/2022 15:30 | CHEHALIS-SILVER CREEK SECTION OF CHEHALIS-MAYFIELD NO 1 230KV LINE (UNGROUNDED) | PA, RP, PA | OUT_OF_SERVICE
277 | 22-01244 | 9708248 | DART-1414360 | 09/06/2022 08:00 | 09/07/2022 15:30 | KEELER: 230/115KV TRANSFORMER 1 INCLUDING SPARE PHASE | SOA, LOAD, SOA | OUT_OF_SERVICE
278 | 22-02734 | 11120763 | DART-1471844 | 09/06/2022 08:15 | 09/06/2022 16:00 | JOHN DAY: PCB 4128 | NWACI, PDCI, WOJD, WOS, COI | OUT_OF_SERVICE
279 | 22-06205 | 11562231 |  | 09/06/2022 09:00 | 09/08/2022 15:00 | JOHN DAY: PCB 5444 BFR & DIFFERENTIAL RELAYS, MCNARY 2 LINE LOR AND WEST BUS LOR SET 2 | NWACI, PDCI, WOJD, WOM, WOS, COI | OUT_OF_SERVICE
280 | 22-05732 | 11508106 |  | 09/07/2022 07:00 | 09/07/2022 16:00 | COYOTE SPRINGS: PCB 5190 | NWACI, PDCI, WOLM, WOM, COI | OUT_OF_SERVICE
281 | 22-02280 | 10940567 | DART-1466372 | 09/07/2022 07:30 | 09/07/2022 16:00 | CUSTER: PCB 4274 INCLUDING THE 500KV REACTOR 1 | BCHT, BCHW, NOEL, SOC, NI, NOEL, SOC | OUT_OF_SERVICE
282 | 22-02737 | 11120764 | DART-1471850 | 09/07/2022 08:15 | 09/07/2022 16:00 | JOHN DAY: PCB 4822 | JDAY, NWACI, PDCI, WOJD | OUT_OF_SERVICE
283 | 22-02738 | 11120767 | DART-1471854 | 09/08/2022 08:15 | 09/08/2022 16:00 | JOHN DAY: PCB 5444 | NWACI, PDCI, WOJD, WOM, WOS, COI | OUT_OF_SERVICE
284 | 22-06258 | 11562247 |  | 09/08/2022 16:00 | 09/08/2022 16:30 | JOHN DAY: PCB 5441 | NWACI, PDCI, WOJD, WOM, WOS, COI | OUT_OF_SERVICE
285 | 22-02506 | 11017851 | DART-1469568,OTS-11720 | 09/08/2022 17:00 | 09/08/2022 17:30 | MCNARY: PCB A-420 OF THE PH-MCNARY NO 3&4 230KV LINE | GEN, WOM | OUT_OF_SERVICE
286 | 22-02507 | 11017963 | DART-1469576,OTS-11722 | 09/12/2022 06:30 | 09/12/2022 07:00 | MCNARY: PCB A-434 OF THE PH-MCNARY NO 5 230KV LINE | GEN, FCRPS, WOM, WOM | OUT_OF_SERVICE
287 | 22-01064 | 11180236 | DART-1475358 | 09/12/2022 07:00 | 09/16/2022 17:00 | CHIEF JOSEPH-MONROE NO 1 500KV LINE | GEN, IROL, NOEL, NOH, SIG, SOC, WOCN, COI, NWACI, BCHT, BCHW, NI, NOEL, SOC, WOCN, BCHT, BCHW, NI, NOEL, SOC, WOCN, GEN, NOEL, SOC, WOCN, GEN, NOEL, SOC, WOCN | OUT_OF_SERVICE
288 | 22-02633 | 11209505 | DART-1470756 | 09/12/2022 08:00 | 09/16/2022 18:00 | YEW AVENUE-BRASADA SECTION OF REDMOND-BRASADA NO 1 115KV LINE | ID-NW | OUT_OF_SERVICE
289 | 22-02423 | 11175658 | DART-1468522 | 09/12/2022 08:00 | 09/13/2022 16:30 | WENDSON-BERRYDALE SECTION OF WENDSON-TAHKENITCH NO 1 115KV LINE | SWORE | OUT_OF_SERVICE
290 | 22-04801 | 11350616 | DART-1481934 | 09/12/2022 08:00 | 10/21/2022 16:00 | CLYMER-MOXEE SECTION OF ELLENSBURG-MOXEE NO 1 115KV LINE | TCLA | OUT_OF_SERVICE
291 | 22-02573 | 11045003 | DART-1470208 | 09/12/2022 08:30 | 09/13/2022 16:00 | JOHN DAY: PCB 4167 | JDAY, NWACI, WOCS, WOJD, COI | OUT_OF_SERVICE
292 | 22-06141 | 9946360 |  | 09/12/2022 09:00 | 09/16/2022 18:30 | BPA LaPine-Chiloquin 230 kV line | PDCI, COI
293 | 22-04033 | 11323668 | DART-1480780 | 09/12/2022 13:00 | 09/12/2022 14:30 | BOUNDARY: 230KV BUS SECTIONALIZING PCB A-1233 | SOB | OUT_OF_SERVICE
294 | 22-04884 | 11374268 | DART-1482622 | 09/13/2022 06:00 | 09/13/2022 16:00 | ALVEY: BANK #3 INCLUDING PCB'S A-242, B-584, 16W, BUS TIE PCB'S A-248 & B-586 & A-242 & B-584 BFR'S O.A.T., ALVEY: 230/115KV TRANSFORMER 3 | COI, PDCI, COI, PDCI, NWACI | OUT_OF_SERVICE
295 | 22-02281 | 10940570 | DART-1466374 | 09/13/2022 07:30 | 09/13/2022 15:00 | CUSTER: PCB A-1546 | BCHT, BCHW, NOEL, SOC, NI | OUT_OF_SERVICE
296 | 22-04966 | 11422380 | DART-1483758,OTS-12341 | 09/13/2022 08:15 | 09/13/2022 08:45 | GRAND COULEE: PCB 1992, PCB 1996 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
297 | 22-04961 | 11422382 | DART-1483748,OTS-12343 | 09/13/2022 09:15 | 09/13/2022 09:45 | GRAND COULEE: PCB 2092, PCB 2096 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
298 | 22-04967 | 11422384 | DART-1483760,OTS-12345 | 09/13/2022 10:15 | 09/13/2022 10:45 | GRAND COULEE: PCB 2292, PCB 2296 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
299 | 22-04968 | 11422385 | DART-1483762,OTS-12347 | 09/13/2022 11:15 | 09/13/2022 11:45 | GRAND COULEE: PCB 2392, PCB 2396 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
300 | 22-04038 | 11323690 | DART-1480802 | 09/13/2022 12:00 | 09/13/2022 14:00 | BOUNDARY: PCB A-1222 | SOB, GEN | OUT_OF_SERVICE
301 | 22-00899 | 11136935 | DART-1474004,OTS-11920 | 09/13/2022 12:00 | 09/13/2022 15:00 | CHIEF JOSEPH PH-CHIEF JOSEPH NO 1 230KV LINE INCLUDING CHIEF JOSEPH: PCB A-576, PCB A-584 | GEN, NOH, FCRPS, WOCN | OUT_OF_SERVICE
302 | 22-04969 | 11422388 | DART-1483764,OTS-12349 | 09/13/2022 12:45 | 09/13/2022 13:15 | GRAND COULEE: PCB 2496, PCB 2492 | GEN, WOCN, COI, NOH, NWACI, PDCI, GEN, NOH, COI, NWACI, PDCI | OUT_OF_SERVICE
303 | 22-02282 | 10940572 | DART-1466378 | 09/14/2022 07:30 | 09/14/2022 15:00 | CUSTER: PCB A-1250 | BCHT, BCHW, NOEL, SOC, NI | OUT_OF_SERVICE
304 | 22-00981 | 11156434 | DART-1474576 | 09/14/2022 08:00 | 09/15/2022 16:00 | JOHN DAY: PCB 4131 | NWACI, PDCI, WOJD, WOS, COI | OUT_OF_SERVICE
305 | 22-04040 | 11323708 | DART-1480806 | 09/14/2022 09:00 | 09/14/2022 10:00 | BOUNDARY: PCB A-1230 | SOB | OUT_OF_SERVICE
306 | 22-04044 | 11323712 | DART-1480808 | 09/14/2022 10:00 | 09/14/2022 11:00 | BOUNDARY: PCB A-1234 | SOB | OUT_OF_SERVICE
307 | 22-04045 | 11323728 | DART-1480810 | 09/14/2022 11:00 | 09/14/2022 12:00 | BOUNDARY: PCB A-1235 | SOB | OUT_OF_SERVICE
308 | 22-04047 | 11323763 | DART-1480816 | 09/14/2022 12:00 | 09/14/2022 14:30 | BOUNDARY: PCB A-1228 & PCB B-1398 INCLUDING 230/115KV TRANSFORMER 1 AND METALINE FALLS-BOUNDARY SECTION OF COLVILLE-BOUNDARY 1 115KV LINE | SOB, SOB, LOAD, NI, NOEL, SOC, SOB | OUT_OF_SERVICE
309 | 22-00903 | 11136982 | DART-1474020,OTS-11922 | 09/15/2022 12:00 | 09/15/2022 15:00 | CHIEF JOSEPH PH-CHIEF JOSEPH NO 2 230KV LINE INCLUDING CHIEF JOSEPH: PCB A-580, PCB A-584 | GEN, NOH, FCRPS, GEN, WOCN | OUT_OF_SERVICE
310 | 22-01263 | 9761357 | DART-1421920 | 09/16/2022 15:00 | 09/16/2022 16:00 | CENTRALIA SWITCHING STATION-TPWR COWLITZ SECTION OF CHEHALIS-COVINGTON NO 1 230KV LINE INCLUDING COWLITZ TAP | PA, RP, NOEL, SOC, PA, RP, LOAD, BCHT, BCHW, NOEL, SOC | OUT_OF_SERVICE
311 | 22-02586 | 11045000 | DART-1470330,OTS-11760 | 09/19/2022 01:00 | 09/23/2022 17:00 | GRAND COULEE: 500KV NORTH BUS INCLUDING PCB 1896, PCB 2092, PCB 2192, PCB 2292, PCB 2392, PCB 2492, PCB 1992, | MT-NW, WOH, COI, NOH, NWACI, PDCI, WOCN, GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI, COI, NOH, NWACI, PDCI, WOCN | OUT_OF_SERVICE
312 | 22-02194 | 10928037 | DART-1465672,OTS-11109 | 09/19/2022 07:00 | 09/19/2022 09:00 | LOWER MONUMENTAL: 4318 TERMINAL OF LOWER MONUMENTAL PH-LOWER MONUMENTAL NO 1 500KV LINE | GEN | OUT_OF_SERVICE
313 | 22-02693 | 11337686 | DART-1471404 | 09/19/2022 07:00 | 10/06/2022 15:00 | TAFT-HOT SPRINGS #1 500KV LINE (UNGROUNDED) INCLUDING: HOT SPRINGS: 500/230KV TRANSFORMER 1, 500KV REACTOR 1, PCB 4478, PCB 4562 | GEN, MT-NW, WOH, MT-NW, WOH, GEN, MT-NW, SIG, WOH, MT-NW, WOH, GEN, MT-NW, WOH | OUT_OF_SERVICE
314 | 22-04649 | 11337753 | DART-1481336 | 09/19/2022 07:00 | 09/19/2022 08:00 | TAFT: 500KV BUS 1, PCB 4111, PCB 4122, PCB 4148 | MT-NW, WOH, GEN, MT-NW, NOH, WOH, GEN, MT-NW, WOH, GEN, MT-NW, WOH | OUT_OF_SERVICE
315 | 22-03279 | 11282941 | DART-1477712 | 09/19/2022 07:30 | 09/22/2022 17:00 | VANTAGE-HANFORD NO 1 500KV LINE | BCHT, BCHW, NI, NOH, NWACI, PDCI, SIG, COI, WOCS, NOH, NWACI, PDCI, COI, WOM, WOS, NOH, NWACI, PDCI, COI, WOM, WOS, GEN, NOH, NWACI, PDCI, WOCN, COI, GEN, NOH, NWACI, PDCI, WOCN, COI | OUT_OF_SERVICE
316 | 22-02451 | 11025434 | DART-1469238 | 09/19/2022 07:30 | 09/21/2022 14:00 | MONROE: PCB 4508, INCLUDING 500KV CAP GROUP 4 | IROL, NI, NOEL, SOC, WOCN | OUT_OF_SERVICE
317 | 22-00860 | 11140962 | DART-1473816 | 09/19/2022 07:30 | 09/22/2022 15:00 | PAUL-SATSOP NO 1 500KV LINE INCLUDING SATSOP: 500/230KV TRANSFORMER 1 AND PCB'S A-622 & A-625 | LOAD, PA, RP, SI, SIG, PA, RP, LOAD, PA, RP, PA, RP | OUT_OF_SERVICE
318 | 22-02324 | 11346066 | DART-1467110 | 09/19/2022 07:30 | 09/19/2022 11:30 | LEBANON: PCB B-848, AIRPORT-LEBANON SECTION OF ALBANY-LEBANON NO 1 115KV LINE | SLAL, SLAL | OUT_OF_SERVICE
319 | 22-03882 | 11300574 | DART-1479984 | 09/19/2022 07:30 | 09/23/2022 16:00 | SANTIAM-TOLEDO NO 1 230KV LINE INCLUDING THE WREN: 230/69KV XFMR #2, LBD A-1604 & PCB L-856, WREN: CONSUMERS POWER 69KV FEEDER 1 | SWORE, LOAD, SWORE | OUT_OF_SERVICE
320 | 22-01299 | 9878761 | DART-1426546 | 09/19/2022 07:30 | 09/23/2022 16:00 | SANTIAM-TOLEDO NO 1 230KV LINE INCLUDING SANTIAM: PCB A-524 AND TOLEDO: PCB A-1472 AND WREN: LBD A-1604 & 230/69KV TRANSFORMER 2 | SWORE, LOAD, LOAD, SWORE | OUT_OF_SERVICE
321 | 22-06385 | 11563776 |  | 09/19/2022 08:00 | 09/28/2022 16:00 | REDMOND: A-262 TERMINAL OF THE REDMOND-PGE ROUND BUTTE #1 230KV LINE (UNGROUNDED) | COI, NWACI, PDCI, SIG | OUT_OF_SERVICE
322 | 22-02411 | 11175702 | DART-1468454 | 09/19/2022 08:00 | 09/22/2022 16:30 | SUMNER-FAIRVIEW SECTION OF REEDSPORT-FAIRVIEW NO 1 115KV LINE | LOAD, SWORE | OUT_OF_SERVICE
323 | 22-02897 | 11313552 | DART-1476308 | 09/19/2022 08:00 | 09/21/2022 12:00 | DWORSHAK: 500KV REACTOR 2 INCLUDING PCB 4650 | MT-NW, GEN, MT-NW, WOH | OUT_OF_SERVICE
324 | 22-02450 | 11025430 | DART-1469802 | 09/19/2022 08:00 | 09/21/2022 14:00 | MONROE: 500KV CAP GROUP 2 & 3 (PCBS ON LOCAL/ AVCS IN MANUAL) | IROL, NI, NOEL, SOC, WOCN, IROL, NOEL, SOC, WOCN, NI | ENERGIZED_WORK
325 | 22-04821 | 11356165 | DART-1482126 | 09/19/2022 09:30 | 09/19/2022 13:00 | BOUNDARY: PCB A-1228 | SOB | OUT_OF_SERVICE
326 | 22-01039 | 11300305 | DART-1475174 | 09/19/2022 09:30 | 09/22/2022 14:00 | CAPTAIN JACK: PCB 4924 | NWACI, PDCI, COI | OUT_OF_SERVICE
327 | 22-04823 | 11356168 | DART-1482128 | 09/19/2022 13:00 | 09/19/2022 16:30 | BOUNDARY: PCB A-1230 | SOB | OUT_OF_SERVICE
328 | 22-03704 | 11313823 | DART-1479478 | 09/20/2022 06:00 | 09/24/2022 17:00 | MONROE-CUSTER NO 1 500KV LINE | BCHT, BCHW, IROL, NOEL, SIG, SOC, NI | OUT_OF_SERVICE
329 | 22-04824 | 11364426 | DART-1482130 | 09/20/2022 07:00 | 09/20/2022 16:30 | CUSICK-BOUNDARY SECTION OF USK-BOUNDARY 1 230KV LINE INCLUDING BOUNDARY: PCB A-1235 AND 230KV AUX BUS (UNGROUNDED) | SOB, SOB | OUT_OF_SERVICE
330 | 22-04825 | 11364560 | DART-1482132 | 09/21/2022 06:00 | 09/21/2022 11:30 | BOUNDARY-NELWAY NO 1 230KV LINE INCLUDING BOUNDARY: PCB A-1220 AND 230KV AUX BUS | SOB, BCHT, GEN, NI, NOEL, SOB, SOC | OUT_OF_SERVICE
331 | 22-02437 | 11034528 | DART-1468938,OTS-11670 | 09/21/2022 06:30 | 09/29/2022 17:00 | DWORSHAK: 4657/4658 TERMINAL OF DWORSHAK PH-DWORSHAK NO 1 500KV LINE | GEN, SIG, FCRPS | OUT_OF_SERVICE
332 | 22-06352 | 11591887 |  | 09/21/2022 08:00 | 09/21/2022 10:00 | ROCK CREEK: PCB 5294 | NWACI, PDCI, RKCR, COI | OUT_OF_SERVICE
333 | 22-06216 | 11591882 |  | 09/21/2022 10:00 | 09/21/2022 12:00 | ROCK CREEK: PCB 5288 | NWACI, PDCI, RKCR, COI | OUT_OF_SERVICE
334 | 22-04827 | 11364624 | DART-1482136 | 09/21/2022 11:30 | 09/21/2022 14:30 | BOUNDARY-SACHEEN NO 1 230KV LINE INCLUDING BOUNDARY: PCB A-1234 AND 230KV AUX BUS | SOB | OUT_OF_SERVICE
335 | 22-04826 | 11364644 | DART-1482134 | 09/22/2022 07:00 | 09/22/2022 16:30 | ADDY-BOUNDARY SECTION OF BELL-BOUNDARY 3 230KV LINE INCLUDING BOUNDARY: PCB A-1222 AND 230KV AUX BUS | SOB, GEN, SOB, GEN, BCHT, GEN, MT-NW, SOB | OUT_OF_SERVICE
336 | 22-04779 | 11345438 | DART-1481686 | 09/22/2022 07:30 | 09/22/2022 11:00 | SCHULTZ: PCB 5151 | WOCN | OUT_OF_SERVICE
337 | 22-04780 | 11345439 | DART-1481690 | 09/22/2022 11:00 | 09/22/2022 15:30 | SCHULTZ: PCB 5148 | WOCN | OUT_OF_SERVICE
338 | 22-02508 | 11017970 | DART-1469578,OTS-11724 | 09/22/2022 16:30 | 09/22/2022 17:00 | MCNARY PH-MCNARY NO 5 230KV LINE | GEN, FCRPS, WOM, WOM | OUT_OF_SERVICE
339 | 22-02103 | 10879173 | DART-1464550,OTS-10924 | 09/26/2022 01:00 | 10/07/2022 20:00 | GRAND COULEE: PCB 2296, PCB 2292 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
340 | 22-03186 | 11220346 | DART-1477276 | 09/26/2022 06:00 | 10/07/2022 22:00 | RAS - DITTMER: RAS AC-A CONTROLLER, DC-A CONTROLLER, WS-A CONTROLLER AND SYNCHROPHASOR-A CONTROLLER | SIG, COI, NOH, NWACI, PDCI, WOM, WOS, SIG, COI, NOH, NWACI, PDCI, WOM, WOS, BCHT, BCHW, NI, NOEL, PA, RP, SIG, SOA, SOC | COMMUNICATIONS
341 | 22-06513 | 11597287 | DART-1458668,OTS-12604 | 09/26/2022 07:00 | 10/07/2022 16:00 | CHIEF JOSEPH: 500/230KV TRANSFORMER 3 | NOEL, NOH, NWACI, PDCI, SOC, COI, FCRPS, GEN, GEN, NOEL, NOH, NWACI, PDCI, SOC, WOCN, COI, BCHT, BCHW, GEN, WOCN | OUT_OF_SERVICE
342 | 22-04893 | 11374462 | DART-1482756 | 09/26/2022 08:00 | 11/03/2022 12:00 | OLYMPIA: A-1772 TERMINAL INCLUDING PCB A-1772 | PA, RP, WOCN | OUT_OF_SERVICE
343 | 22-06522 | 11596932 |  | 09/26/2022 08:00 | 09/30/2022 15:00 | LOWER MONUMENTAL: 500KV WEST BUS INCLUDING PCB 4263 | WOLM, WOLM | OUT_OF_SERVICE
344 | 22-04894 | 11374283 | DART-1482732 | 09/26/2022 08:00 | 11/03/2022 12:00 | PAUL-OLYMPIA NO 1 500KV LINE INCLUDING OLYMPIA: 500/230KV TRANSFORMER 5, PCB A-1772 AND PAUL PCB'S 4550 & 4554 | LOAD, PA, RP, SIG, LOAD, NOEL, PA, RP, SIG, IROL, NWACI, PA, PDCI, COI, WOCS, PA, RP, WOCS | OUT_OF_SERVICE
345 | 22-02413 | 11175721 | DART-1468458 | 09/26/2022 08:00 | 09/29/2022 16:30 | SUMNER-FAIRVIEW SECTION OF REEDSPORT-FAIRVIEW NO 1 115KV LINE | LOAD, SWORE | OUT_OF_SERVICE
346 | 22-02901 | 11313555 | DART-1476324 | 09/26/2022 08:00 | 09/29/2022 15:30 | DWORSHAK: 500KV REACTOR 1 INCLUDING PCB 4665 | MT-NW, GEN, MT-NW, WOH | OUT_OF_SERVICE
347 | 22-01219 | 10393605 | DART-1408244 | 09/26/2022 09:00 | 09/30/2022 17:30 | CAPTAIN JACK-OLINDA NO 1 500KV LINE | BCHT, BCHW, COI, NI, NWACI, PDCI, NWACI, PDCI, COI, NWACI, PDCI, COI, NWACI, PDCI, COI, NWACI, PDCI, COI, NWACI, PDCI, COI | OUT_OF_SERVICE
348 | 22-02458 | 11040341 | DART-1469272 | 09/27/2022 07:00 | 09/27/2022 15:30 | ECHO LAKE-MONROE NO 1 500KV LINE INCLUDING SNO-KING TAP AND MONROE: PCB'S 4522 & 4526, SNO-KING: 500/230KV TRANSFORMER 4 | IROL, NI, NOEL, SIG, SOC, WOCN, COI, NWACI, PDCI, BCHT, BCHW, NOEL, SIG, SOC, WOCN, IROL, NI, LOAD, NOEL, SIG, SOC, IROL, WOCN, BCHT, BCHW, NI, NOEL, SOC, WOCN | OUT_OF_SERVICE
349 | 22-05807 | 11540621 | OTS-12514 | 09/27/2022 08:15 | 09/27/2022 08:45 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
350 | 22-05808 | 11540626 | OTS-12516 | 09/27/2022 09:15 | 09/27/2022 09:45 | GRAND COULEE: PCB 2092, GRAND COULEE: PCB 2096 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
351 | 22-05809 | 11540655 | OTS-12518 | 09/27/2022 10:15 | 09/27/2022 10:45 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI | OUT_OF_SERVICE
352 | 22-00913 | 11137184 | DART-1474058,OTS-11924 | 09/27/2022 11:00 | 09/27/2022 14:00 | CHIEF JOSEPH PH-CHIEF JOSEPH NO 3 230KV LINE RELAYS INCLUDING CHIEF JOSEPH: PCB A-592 AND PCB A-598 | GEN, NOH, FCRPS, GEN, WOCN | OUT_OF_SERVICE
353 | 22-05810 | 11540661 | OTS-12520 | 09/27/2022 11:15 | 09/27/2022 11:45 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 | GEN, NOH, COI, NWACI, PDCI, GEN, WOCN, COI, NOH, NWACI, PDCI | OUT_OF_SERVICE
354 | 22-01104 | 11347113 | DART-1475490 | 09/29/2022 11:30 | 09/29/2022 15:30 | ALBANY: 115KV CAP GROUP 1 SECTION 2 INCLUDING PCB B-521 |  | OUT_OF_SERVICE
355 | 22-00921 | 11137207 | DART-1474066,OTS-11926 | 09/29/2022 12:00 | 09/29/2022 15:00 | CHIEF JOSEPH PH-CHIEF JOSEPH NO 4 230KV LINE INCLUDING CHIEF JOSEPH: PCBS A-598, A-602 | GEN, NOH, FCRPS, GEN, WOCN | OUT_OF_SERVICE