## Request List
Request# | Start | End | CAISO# | Main Element Impacted | Path Affected
20-00283 | 12/31/2020 15:00 | 12/15/2031 23:59 | 11219795 | PAUL: 4569 TERMINAL OF PAUL-CENTRALIA THERMAL PH NO 1 500KV LINE | GEN, PA
22-01254 | 06/01/2023 08:00 | 08/31/2023 17:00 | 9684180 | NORTH BONNEVILLE-TROUTDALE NO 2 230KV LINE | GEN, LOAD, WOCS, FCRPS
22-01257 | 06/01/2023 08:00 | 08/31/2023 17:00 | 9684333 | NORTH BONNEVILLE-ROSS NO 2 230KV LINE INCLUDING SIFTON TAP, SIFTON TAP TO NORTH BONNEVILLE-ROSS NO 2 230KV LINE | GEN, LOAD, WOCS, FCRPS, GEN, SOA, WOCS, LOAD
22-02304 | 06/03/2023 22:00 | 09/03/2023 09:00 | 10945141 | NORTH BONNEVILLE-ALFALFA SECTION OF NORTH BONNEVILLE-MIDWAY NO 1 230KV LINE | WOCS
23-00166 | 06/26/2023 07:00 | 07/13/2023 17:00 | 11729140 | CENTRAL FERRY-LOWER GRANITE NO 2 500KV LINE | WOH, WOLM
23-00016 | 07/17/2023 06:30 | 07/28/2023 17:00 | 9556218 | GRAND COULEE: PCB 2092, PCB 2096 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI
23-00019 | 07/31/2023 01:00 | 07/31/2023 01:30 | 9556212 | GRAND COULEE: PCB 2292, PCB 2296 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI
23-00064 | 07/31/2023 05:00 | 08/12/2023 17:00 |  | LITTLE GOOSE PH: INLAND P+L 13.8KV FEEDER 1 BY US CORPS ENGIN
23-00063 | 07/31/2023 05:00 | 08/12/2023 17:00 | 10941473 | LITTLE GOOSE: 4349/4351 TERMINAL OF LITTLE GOOSE PH-LITTLE GOOSE NO 1 500KV LINE | GEN, WOLM, WOLM, WOLM
23-00093 | 07/31/2023 08:00 | 08/04/2023 16:00 | 11350620 | EAST ELLENSBURG-ELLENSBURG SECTION OF COLUMBIA-ELLENSBURG NO 1 115KV LINE | TCLA