## Request List
Row | Request# | CAISO# | Start | End | Main Element Impacted | Path Affected
1 | 21-01711 | 9741845 | 02/03/2021 09:00 | 02/28/2023 17:00 | -USBR- GRAND COULEE 287/230KV TRANSFORMER KX-17-A (OLYMPIA-GRAND COULEE NO 1 287KV LINE OPERATING AT 230KV) | NOEL, PA, RP, SOC, WOCN, IROL, NOH, OKLA
2 | 21-01581 |  | 04/30/2021 16:15 | 03/31/2023 18:00 | BCH - BURRARD SYNCHRONOUS CONDENSER STATION G2 | BCHT, BCHW, NI
3 | 21-01767 | 10359382 | 06/30/2021 10:00 | 02/03/2023 16:00 | PAUL: 4805 TERMINAL OF PAUL-PSE TONO NO 1 500KV LINE | LOAD, RP, SIG, PA
4 | 21-01784 | 11699929 | 08/25/2021 12:00 | 12/31/2022 23:59 | GARRISON: 500/230KV TRANSFORMER 1 (DERATED) | MT-NW
5 | 21-01905 | 11126783 | 12/14/2021 13:54 | 12/30/2022 17:00 | AVA - MOSOW: CB_R580, CB_R480
6 | 22-03687 |  | 01/25/2022 19:08 | 01/31/2023 23:59 | AVA MOSCOW 230/115KV TRANSFORMER OOS
7 | 22-06746 | 11593785 | 04/06/2022 06:30 | 12/30/2022 15:00 | CONKELLEY: LBD A-1575 INCLUDING 230KV CAP GROUP 2 SECTION 1 | MT-NW
8 | 22-06836 | 11597875 | 04/06/2022 12:25 | 12/31/2022 15:00 | OSTRANDER-TROUTDALE 1 500KV LINE INCLUDING TROUTDALE: 500/230KV TRANSFORMER BANK 8 | SIG, SOA, WOCS, SIG, WOCS, SOA
9 | 22-10319 | 11976164 | 08/01/2022 08:00 | 12/31/2022 15:00 | NORTH BONNEVILLE: B-1518 TERMINAL OF THE UNDERWOOD TAP TO BONNEVILLE PH1-ALCOA NO 1&2 115 KV LINE
10 | 22-12945 |  | 08/15/2022 08:00 | 12/15/2022 16:00 | BCH - MICA CREEK: 500KV REACTOR 3(MCA 5RX3) | BCHT, BCHW, NI
11 | 22-13128 | 12263690 | 08/17/2022 08:00 | 12/30/2022 15:00 | MAPLE VALLEY: 500/230KV TRANSFORMER 2, (DERATED) | IROL, NOEL, SIG, SOC, WOCN
12 | 22-12182 | 12155060 | 08/19/2022 08:00 | 11/19/2022 18:00 | SCL - DIABLO-BOTHELL 3 230KV LINE | SOC/NOEL
13 | 22-05597 | 11493040 | 08/22/2022 08:00 | 11/18/2022 15:00 | BETTAS ROAD-COLUMBIA NO 1 230KV LINE INCLUDING BETTAS ROAD: 230KV EAST BUS AND PCB'S A-3046 AND A-3043 | NOEL, SOC, WOCN, CI, NOH, IROL
14 | 22-04894 | 11374283 | 09/26/2022 13:00 | 11/03/2022 12:00 | PAUL-OLYMPIA NO 1 500KV LINE INCLUDING OLYMPIA: 500/230KV TRANSFORMER 5, PCB A-1772 AND PAUL PCB'S 4550 & 4554 | NWACI, PDCI, COI, WOCS, SOA, RP, LOAD, PA, SIG, NOEL, IROL
15 | 22-01952 | 10821249 | 10/03/2022 07:00 | 11/17/2022 17:00 | LONGVIEW: 230KV CAP GROUP 6 SECTIONS 1 AND 2 INCLUDING PCB A-648, LBD'S A-1640 AND A-1641, AND ALL ASSOCIATED RELAYS AND WIRING | LOAD, SOA, LOAD, SOA, SOA
16 | 22-06014 | 11537545 | 10/03/2022 08:00 | 11/18/2022 17:00 | GRIZZLY: 500KV REACTOR 3 INCLUDING PCB 4038 | COI, NWACI, PDCI, COI, PDCI, NWACI
17 | 22-02115 |  | 10/03/2022 08:00 | 11/02/2022 16:00 | -PGE- BETHEL (PGE)-ROUND BUTTE 230KV LINE | COI, NWACI, PDCI, WOCS
18 | 22-01956 | 10764220 | 10/04/2022 15:00 | 11/09/2022 08:00 | SCHULTZ-WAUTOMA NO 1 500KV LINE INCLUDING WAUTOMA: PCBS 5241 & 5244 & BAY 2E TO REMOVED BUS BETWEEN MOD 5240 & PCB 5241 AND BAY 2E PORTION OF EAST BUS TO REMOVED BUS BETWEEN BAYS 2E (SCHULTZ #1) TO BAY 3E ( HANFORD #1) | BCHT, BCHW, IROL, NI, NOH, NWACI, PDCI, SIG, WOCN, COI, NOH, WOCN, NOH, WOCN, NOH, WOCN, WOCN
19 | 22-02060 | 10848035 | 10/10/2022 08:00 | 03/31/2023 16:00 | HATWAI-AVA MOSCOW NO 3 230KV LINE, HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE (UNGROUNDED) | WOH
20 | 22-01754 | 11045396 | 10/13/2022 11:00 | 11/22/2022 15:00 | HINES-HARNEY NO 1 115KV LINE INCLUDING HARNEY: PCB B-1710 AND THE 115KV AUX BUS (UNGROUNDED) | ID-NW
21 | 22-13176 | 12269357 | 10/15/2022 04:00 | 11/08/2022 15:00 | BIG EDDY: 4214 TERMINAL OF THE BIG EDDY-CELILO #1, 4207 TERMINAL OF THE BIG EDDY-CELILO #2 500KV LINES, CELILO: 9085 TERMINAL OF THE CELILO-SYLMAR POLE 3, 9084 TERMINAL OF THE CELILO-SYLMAR POLE 4 1000KV LINE, CELILO: 9054 & 9092 TERMINALS AT RICE FLATS | PDCI, SIG, COI, NWACI, BGEDY
22 | 22-05458 | 8999942 | 10/15/2022 04:00 | 11/13/2022 21:00 | CELILO: 9085 TERMINAL OF CELILO-SYLMAR POLE 3 AND 9084 TERMINAL OF CELILO-SYLMAR POLE 4 1000KV LINE | PDCI, SIG
23 | 22-09962 | 11908026 | 10/15/2022 08:00 | 11/08/2022 15:00 | CELILO: RAS DC-A CONTROLLER SCADA MASTER CKT 6196, CELILO: RAS DC-B CONTROLLER SCADA MASTER CKT 6218
24 | 22-08328 | 11755636 | 10/17/2022 08:00 | 11/08/2022 15:00 | MCNARY: 345/230KV TRANSFORMER 8 | SOA, WOCS, WOM
25 | 22-08162 | 11755644 | 10/17/2022 08:00 | 11/08/2022 15:00 | ROSS: 345/230KV TRANSFORMER 4 | SOA, WOCS, WOM
26 | 22-08243 | 11755980 | 10/21/2022 15:00 | 11/09/2022 08:00 | MCNARY-ROSS NO 1 345KV LINE OPERATED AT 230KV | SOA, WOCS, WOM
27 | 22-12278 | 12225668 | 10/24/2022 07:00 | 11/11/2022 16:00 | MT. VERNON-ALVEY SECTION OF THE LOOKOUT POINT-ALVEY NO 2 115KV LINE INCLUDING ALVEY: PCB B-572 AND THE 115KV SOUTH AUX. BUS (UNGROUNDED) | GEN
28 | 22-09615 | 11874119 | 10/24/2022 07:00 | 11/06/2022 18:00 | SUMMER LAKE: 4951/4952 TERMINAL OF , HEMINGWAY-SUMMER LAKE NO 1 500KV LINE | ID-NW, NWACI, SIG, COI
29 | 22-12197 | 12353639 | 10/24/2022 08:00 | 11/09/2022 15:00 | KEELER: A-899 TERMINAL OF KEELER-PGE ST MARYS NO 1 230KV LINE (UNGROUNDED) | SOA, SIG, LOAD
30 | 22-00982 | 11455440 | 10/25/2022 08:00 | 11/17/2022 14:30 | NORTH BONNEVILLE-OUTLOOK SECTION OF NORTH BONNEVILLE-MIDWAY NO 1 230KV LINE INCLUDING ALFALFA TAP, ALFALFA: 230/34.5KV TRANSFORMER 1, PCB A-1272 AND 34.5KV PCBS L-1456 & L-1458 AND YAKAMA POWER 34.5KV FEEDER #1 SATUS TO OPEN JUMPERS AT A001-1605, FEEDER #2 HARRAH TO OPEN JUMPERS AT A139-1605, NORTH BONNEVILLE-ALFALFA SECTION OF NORTH BONNEVILLE-MIDWAY NO 1 230KV LINE, ALFALFA TAP TO NORTH BONNEVILLE-MIDWAY NO 1 230KV LINE, ALFALFA-OUTLOOK SECTION OF NORTH BONNEVILLE-MIDWAY NO 1 230KV LINE, ALFALFA: YAKAMA POWER 34.5KV FEEDER 1, ALFALFA: YAKAMA POWER 34.5KV FEEDER 2, OUTLOOK: PACIFICORP (PACW) 230KV FEEDER 1 | WOCS, WOCS, NWACI, PDCI, WOCS, COI, WOCS
31 | 22-13053 | 12261489 | 10/26/2022 08:00 | 11/22/2022 17:00 | BIG EDDY-MAUPIN NO 1 230KV LINE | COI, NWACI, PDCI, WOJD
32 | 22-12069 | 12226431 | 10/28/2022 08:00 | 11/04/2022 15:00 | ICE HARBOR-FRANKLIN NO 2 115KV LINE INCLUDING THE FRANKLIN COUNTY PUD FB103 DISCONNECT | TCLA, GEN, FCRPS, LOAD
33 | 22-06517 | 11575255 | 10/29/2022 07:00 | 11/01/2022 16:00 | JOHN DAY-BIG EDDY NO 2 500KV LINE | NWACI, PDCI, SIG, WOJD
34 | 22-05654 | 11497947 | 10/30/2022 22:00 | 11/18/2022 17:00 | BELL: A-382 TERMINAL OF THE GRAND COULEE-BELL NO 5 230KV LINE (UNGROUNDED) | MT-NW, WOH, WOH, COI, NOH, NWACI, PDCI, WOCN, NOH, WOH, COI, NWACI, PDCI
35 | 22-01791 | 11563094 | 10/31/2022 07:00 | 11/08/2022 15:30 | FRANKLIN: PCB B-1522 INCLUDING THE GLADE-FRANKLIN SECTION OF BENTON-FRANKLIN NO 2 115KV LINE AND THE 115KV AUX BUS | TCLA
36 | 22-10820 | 12001723 | 10/31/2022 07:00 | 11/03/2022 15:00 | -MITIGATION- FAIRMOUNT: PCB B-1376 OF SHELTON-FAIRMOUNT NO 1 115KV LINE | PA
37 | 22-04979 | 11423286 | 10/31/2022 07:00 | 11/01/2022 16:00 | RAVER: PCB 4849 | NOEL, RP, SOC
38 | 22-04868 | 11368007 | 10/31/2022 07:00 | 11/03/2022 15:00 | SHELTON-T3BA'DAS SECTION OF SHELTON-FAIRMOUNT NO 2 115KV LINE | LOAD
39 | 22-00919 | 11242019 | 10/31/2022 07:30 | 11/04/2022 07:30 | LOWER MONUMENTAL-HANFORD NO 1 500KV LINE, INCLUDING HANFORD: PCB'S 4098 & 4095 | NWACI, PDCI, WOLM, COI, NOH, WOM, SIG
40 | 22-04696 | 11356174 | 10/31/2022 08:00 | 11/02/2022 15:00 | ASHE: PCB 5463 | NOH, NWACI, PDCI, COI, FCRPS
41 | 22-13633 | 12333101 | 10/31/2022 08:00 | 11/04/2022 17:30 | BIG EDDY-DE MOSS NO 1 115KV LINE | GEN
42 | 22-02093 | 10884869 | 10/31/2022 08:00 | 11/03/2022 15:00 | ECHO LAKE: PCB 5075 BFR | BCHT, BCHW, NOEL, SOC, WOCN, NI
43 | 22-08018 | 11704445 | 10/31/2022 08:30 | 11/04/2022 15:30 | LOWER MONUMENTAL PH-LOWER MONUMENTAL 1 500KV LINE INCLUDING: LOMO PCB 4316 | WOLM, GEN
44 | 22-13618 | 12326944 | 11/01/2022 07:00 | 11/01/2022 14:00 | GOSHEN: PCB B-309 (OPEN ENDS SWAN VALLEY-GOSHEN 1 161KV LINE) | GEN, LOAD, SEIL
45 | 22-12399 | 12186370 | 11/01/2022 07:00 | 11/01/2022 12:00 | SCHULTZ: PCB 5182 | WOCN
46 | 22-12787 | 12232111 | 11/01/2022 07:30 | 11/01/2022 18:30 | ALLSTON: 115KV MAIN BUS | LOAD, SOA
47 | 22-13271 | 12288587 | 11/01/2022 08:00 | 11/01/2022 16:00 | COWLITZ: PCB B-344 INCLUDING THE B-344 FEEDER SIDE DISCONNECT AND 7TH AVENUE-COWLTIZ NO 1 115KV LINE | LOAD, SOA
48 | 22-13116 | 12263131 | 11/01/2022 08:00 | 11/10/2022 15:00 | NORTH BONNEVILLE-ROSS NO 2 230KV LINE INCLUDING SIFTON TAP | GEN, SOA, WOCS, LOAD, FCRPS
49 | 22-13106 |  | 11/01/2022 08:00 | 11/10/2022 15:00 | NORTH BONNEVILLE-TROUTDALE NO 2 230KV LINE | GEN, LOAD, WOCS, FCRPS
50 | 22-13713 | 12353344 | 11/01/2022 08:00 | 11/16/2022 15:00 | WALLA WALLA: PCB B-206, INCLUDING 115kV AUX BUS AND WALLA WALLA TO DAYTON SECTION OF THE WALLA WALLA -TUCANNON RIVER #1 115kV LINE. | WAWA, GEN
51 | 22-01186 | 10665484 | 11/01/2022 08:30 | 12/09/2022 16:00 | CONNELL-SCOOTENEY SECTION OF BENTON-SCOOTENEY NO 1 115KV LINE (BETWEEN B-301, B-213 AND B-302 LINE SECTIONALIZING DISCONNECTS) | TCLA
52 | 22-12401 | 12186360 | 11/01/2022 12:00 | 11/01/2022 16:00 | SCHULTZ: PCB 5179 | NOH, WOCN
53 | 22-13619 | 12326980 | 11/02/2022 07:00 | 11/02/2022 14:00 | GOSHEN: PCB B-828 (FORCES OUT GOSHEN-DRUMMOND 1 161KV LINE) | GEN, LOAD, SEIL
54 | 22-10911 | 12011733 | 11/02/2022 07:00 | 11/02/2022 15:00 | OLYMPIA-SHELTON NO 3 230KV LINE INCLUDING OLYMPIA: PCB A-350 AND SHELTON: PCBS A-79 AND A-967 | LOAD, SOA, NOEL, PA, RP, SOC, WOCN
55 | 22-12834 | 12237154 | 11/02/2022 07:30 | 11/02/2022 16:30 | LONGVIEW: 230KV SOUTH MAIN BUS | SOA, PA, LOAD
56 | 22-09166 | 11908023 | 11/02/2022 08:00 | 11/03/2022 19:00 | ASHE-MARION NO 2 500KV LINE, (UNGROUNDED) | BCHT, BCHW, NI, NWACI, PDCI, SIG, WOCS, WOJD, WOM, COI
57 | 22-06310 | 11597466 | 11/02/2022 08:00 | 11/03/2022 15:30 | BIG EDDY: 500/230 TIE NO. 2 500KV LINE RELAYS | GEN, NWACI, PDCI, WOJD, COI, GEN, PDCI, SIG, WOJD, FCRPS, NWACI, GEN, NWACI, PDCI, WOJD, COI, GEN, NWACI, PDCI, WOJD, COI, COI, NWACI, PDCI, WOJD
58 | 22-06819 | 11597631 | 11/02/2022 08:00 | 11/03/2022 15:30 | BIG EDDY: A-834 PCB, M/B, T/S & A/B DISCONNECTS | COI, NWACI, PDCI, WOJD
59 | 22-09169 | 11907993 | 11/02/2022 08:00 | 11/03/2022 19:00 | BUCKLEY-MARION NO 1 500KV LINE, (UNGROUNDED) | NWACI, PDCI, SIG, WOCS, WOJD, COI
60 | 22-13139 | 12353780 | 11/03/2022 06:30 | 11/03/2022 16:00 | McNary 230kV Main Bus Section #1 including PCB A-414 | WOCS, WOM, FCRPS
61 | 22-09085 | 11942765 | 11/03/2022 07:00 | 11/03/2022 16:00 | ECHO LAKE: PCB 5114 | BCHT, BCHW, NOEL, SOC, WOCN, NI
62 | 22-13623 | 12327212 | 11/03/2022 07:00 | 11/03/2022 14:00 | GOSHEN: PCB B-1346 (FORCES OUT CATTLE CREEK-GOSHEN 1 115V LINE) | SEIL, GEN
63 | 22-06519 | 11575492 | 11/03/2022 07:00 | 11/05/2022 16:00 | JOHN DAY-GRIZZLY 2 500KV LINE INCLUDING BAKEOVEN SERIES CAP GROUP 2, . | BCHT, BCHW, NI, NWACI, PDCI, SIG, WOJD, NWACI, PDCI, COI, WOJD
64 | 22-05215 | 11439883 | 11/03/2022 07:00 | 11/03/2022 08:30 | MONROE: PCB 4672 | BCHT, BCHW, NOEL, SOC, NI, WOCN
65 | 22-13014 | 12256755 | 11/03/2022 07:00 | 11/03/2022 16:00 | SHELTON: PCB A-984 INCLUDING THE 230KV CAP GRP 2 | PA, RP
66 | 22-02556 | 11059854 | 11/03/2022 08:00 | 11/03/2022 12:00 | OSTRANDER: PCB 4432 | WOCS
67 | 22-13602 | 12327175 | 11/03/2022 08:00 | 11/03/2022 16:00 | SLATT:230KV CAP GROUP 3 SECTION 1 INCLUDING PCB A-1799 | COI, NWACI, PDCI, WOJD
68 | 22-05214 | 11439904 | 11/03/2022 08:30 | 11/03/2022 10:00 | MONROE: PCB 4714 | BCHT, BCHW, NOEL, SOC, NI, WOCN
69 | 22-05221 | 11439990 | 11/03/2022 10:00 | 11/03/2022 11:30 | CUSTER: PCB 4494 | BCHT, BCHW, NOEL, SOC, NI
70 | 22-05220 | 11439996 | 11/03/2022 12:00 | 11/03/2022 13:30 | CUSTER: PCB 4496 | BCHT, BCHW, NOEL, SOC, NI
71 | 22-02557 | 11059855 | 11/03/2022 12:00 | 11/03/2022 16:00 | OSTRANDER: PCB 5139 | SOA, WOCS
72 | 22-00918 | 11238493 | 11/04/2022 07:30 | 11/04/2022 15:00 | HANFORD: 500KV NORTH BUS, INCLUDING PCB 4098 | NWACI, PDCI, WOLM, COI, NOH, WOM, WOS
73 | 22-07009 | 11704577 | 11/04/2022 16:00 | 01/03/2023 08:00 | LOWER MONUMENTAL: MOD 4317 INCLUDING PCB 4316 | WOLM
74 | 22-03190 | 11220351 | 11/05/2022 06:00 | 11/06/2022 23:00 | RAS - DITTMER: RAS DC-A CONTROLLER AND MUNRO: RAS DC-B CONTROLLER (ALTERNATE DATES) | SIG, COI, NOH, NWACI, PDCI, WOM, WOS, SIG, COI, NWACI, PDCI, WOM, WOS
75 | 22-03188 | 11220350 | 11/05/2022 06:00 | 11/06/2022 23:00 | RAS - DITTMER: RAS WS-A CONTROLLER AND MUNRO: RAS WS-B CONTROLLER (ALTERNATE DATES) | BCHT, BCHW, NI, NOEL, PA, RP, SIG, SOA, SOC, BCHT, BCHW, NI, NOEL, PA, RP, SIG, SOA, SOC
76 | 22-08588 | 11940970 | 11/07/2022 07:00 | 11/07/2022 16:00 | MCNARY: PCB 5199 | WOM, WOS, COI, NWACI, PDCI
77 | 22-03702 | 11570019 | 11/07/2022 07:30 | 11/09/2022 15:00 | CAPTAIN JACK: PCB 4996, BFR | NWACI, PDCI, COI
78 | 22-12376 | 12182104 | 11/07/2022 07:30 | 11/10/2022 15:30 | RAVER: PCB 4876 | NOEL, RP, SOC
79 | 22-04695 | 11356175 | 11/07/2022 08:00 | 11/09/2022 15:00 | ASHE: PCB 5466 | NWACI, WOJD, WOM, WOS, COI, FCRPS
80 | 22-12397 | 12199683 | 11/07/2022 08:00 | 11/09/2022 15:00 | ASHE-WHITE BLUFFS NO 1 230KV LINE, INCLUDING, WHITE BLUFFS: 230/115/13.8KV TRANSFORMER 1, WHITE BLUFFS: PCB B-270, WHITE BLUFFS: PCB B-215, ASHE: PCB A-920, AND, ASHE: PCB A-924 | GEN, FCRPS, LOAD, TCLA, COI, NOH, PDCI, NWACI
81 | 22-13196 | 12270091 | 11/07/2022 08:00 | 11/13/2022 14:30 | -H.E.W.- A-6-ASHE TAP SECTION OF MIDWAY-HEW NO 2 230KV LINE | TCLA
82 | 22-06139 | 10846821 | 11/07/2022 08:00 | 03/31/2023 16:00 | HATWAI-AVA MOSCOW 3 230KV LINE
83 | 22-02196 | 12075639 | 11/07/2022 08:00 | 11/10/2022 15:00 | KEELER: PCB 4763, INCLUDING 500KV CAP GROUP 3 | COI, PDCI, SOA, WOCS, NWACI
84 | 22-11372 | 12075548 | 11/07/2022 08:00 | 11/09/2022 16:00 | MARION: 500KV REACTOR 2, INCLUDING PCB 4020 | COI, NWACI, PDCI
85 | 22-09153 | 11941078 | 11/07/2022 08:00 | 12/02/2022 15:00 | PAUL: PCB 4548, BFR | NWACI, PDCI, COI, WOCS, SOA
86 | 22-02781 | 11364224 | 11/07/2022 08:00 | 11/10/2022 15:00 | SHELTON-T3BA'DAS SECTION OF SHELTON-FAIRMOUNT NO 2 115KV LINE
87 | 22-07143 | 11637362 | 11/07/2022 08:00 | 11/07/2022 17:00 | VANTAGE: 230KV MAIN BUS SECTION 1 INCLUDING PCB'S A-1147, A-1150, A-1152, A-1156, A-1153 AND A-1161 | NOH, NOH, NOH, NOH, NOH, GEN, WI, GEN, NOH, NWACI, SIG, COI, RATS, WI
88 | 22-02595 | 11232469 | 11/07/2022 08:30 | 11/07/2022 15:00 | ROCK CREEK: PCB 5294 | RKCR
89 | 22-08291 | 11941407 | 11/07/2022 09:00 | 11/11/2022 15:00 | LITTLE GOOSE PH-LITTLE GOOSE NO 1 500KV LINE, INCLUDING PCBs 4348 & 4350 | WOLM, GEN
90 | 22-13844 | 12346383 | 11/07/2022 09:00 | 11/07/2022 16:00 | OLYMPIA-SATSOP NO 2 230KV LINE | LOAD, SI, RP
91 | 22-10138 | 11932322 | 11/08/2022 07:00 | 11/10/2022 18:00 | BIG EDDY: 115KV MAIN BUS SECTIONS 1 AND 2 | GEN, WOJD, BGEDY, SOA, FCRPS
92 | 22-10629 | 11977601 | 11/08/2022 07:00 | 11/10/2022 16:00 | BIG EDDY-DE MOSS NO 1 115KV LINE | GEN
93 | 22-07167 | 11637541 | 11/08/2022 08:00 | 11/08/2022 17:00 | VANTAGE: 230KV MAIN BUS SECT. #2, INCLUDING PCB'S A-1158, A-1160, A-1163, A-1164, A-1153, AND A-1161 | NOH, NOH, NOH, NOH, NOH, NOH, NOH, GEN, NOH, WI, GEN, WI, GEN, NOH, CI, SIG, GEN, NOH, NWACI, PDCI, SIG, COI, WI
94 | 22-13146 | 12300860 | 11/09/2022 07:00 | 11/09/2022 15:00 | MCNARY: 230KV MAIN BUS SECTION 2 | WOCS, WOM, FCRPS
95 | 22-10266 | 11932414 | 11/09/2022 07:00 | 11/10/2022 18:00 | -MITIGATION- HOOD RIVER: PCB B-1680 AND NORTH BONNEVILLE ANNEX 115KV CAP GROUPS
96 | 22-10331 | 11977367 | 11/09/2022 07:00 | 11/10/2022 14:00 | SPAR CANYON; 230KV MAIN BUS INCLUDING THE LOST RIVER-SPAR CANYON NO 1 230KV LINE | GEN, LOAD
97 | 22-09261 | 11901778 | 11/09/2022 07:00 | 11/11/2022 17:00 | WAUTOMA: 500KV REACTOR 1 | COI, NWACI, NWACI, COI
98 | 22-08693 | 11907846 | 11/09/2022 08:00 | 11/09/2022 12:00 | DWORSHAK: PCB 4656 | MT-NW
99 | 22-09560 | 12041287 | 11/09/2022 08:00 | 11/17/2022 15:00 | FRANKLIN-BURBANK SECTION OF FRANKLIN-WALLA WALLA NO 1 115KV LINE INCLUDING PCB B-606 AND THE WEST SECTION OF THE 115KV AUX BUS.
100 | 22-08169 | 11755940 | 11/09/2022 08:00 | 11/10/2022 15:00 | MCNARY-ROSS NO 1 345KV LINE INCLUDING ROSS BANK 4 AND PCB A-142 AND MCNARY BANK 8 AND PCB A-432 | SOA, WOCS, SOA, WOCS, WOM, SOA, WOCS, WOM, SOA, WOCS, WOM, SOA, WOCS, WOM
101 | 22-01957 | 10764223 | 11/09/2022 08:00 | 11/11/2022 15:00 | SCHULTZ-WAUTOMA NO 1 500KV LINE INCLUDING WAUTOMA: 500KV EAST BUS, PCBS 5241, 5244, 5253, 5262 AND SCHULTZ: PCBS 5170, 5173 | BCHT, BCHW, IROL, NI, NOH, NWACI, PDCI, SIG, WOCN, COI, WOCN, NOH, WOCN, NOH, WOCN, NWACI, COI, NOH, WOCN, WOCN, COI, NWACI, NOH, WOCN, WOCN
102 | 22-07276 | 11740350 | 11/09/2022 08:00 | 11/09/2022 17:00 | VANTAGE-COLUMBIA NO 1 230KV LINE, INCLUDING VANTAGE: 230KV AUX BUS SECTION 2, AND PCB A-1163 | GEN, NOH, CI, SIG
103 | 22-08695 | 11907849 | 11/09/2022 12:00 | 11/09/2022 15:00 | DWORSHAK: PCB 4652 | MT-NW
104 | 22-10188 | 12192407 | 11/10/2022 08:00 | 11/10/2022 15:00 | FRANKLIN: 115KV WEST MAIN BUS | TCLA, GEN, WAWA
105 | 22-12487 |  | 11/10/2022 08:00 | 11/23/2022 16:00 | PGE - MURRAYHILL-ST MARYS 230KV LINE | SOA
106 | 22-08540 | 11907943 | 11/10/2022 10:15 | 11/10/2022 10:45 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 | GEN, NOH, WOCN, GEN, NOH, WOCN
107 | 22-08541 | 11907985 | 11/10/2022 11:15 | 11/10/2022 11:45 | GRAND COULEE: PCB 2092, GRAND COULEE: PCB 2096 | GEN, NOH, WOCN, GEN, NOH, WOCN
108 | 22-08542 | 12188018 | 11/10/2022 12:45 | 11/10/2022 13:15 | GRAND COULEE: PCB 2292, GRAND COULEE: PCB 2296 | GEN, NOH, WOCN
109 | 22-08543 | 11942783 | 11/10/2022 13:45 | 11/10/2022 14:15 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 | GEN, NOH, WOCN, GEN, NOH, WOCN
110 | 22-08544 | 11942790 | 11/10/2022 14:45 | 11/10/2022 15:15 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 | GEN, NOH, GEN, WOCN, NOH
111 | 22-13668 | 12326404 | 11/11/2022 08:00 | 11/18/2022 17:00 | PSE- SAMMAMISH-MAPLE VALLEY NO. 1 230KV LINE | NOEL, SOC
112 | 22-13665 | 12326375 | 11/11/2022 08:00 | 11/18/2022 17:00 | -PSE- SAMMAMISH-NOVELTY HILL NO. 2 230KV LINE | SOC/NOEL
113 | 22-03189 | 11220349 | 11/12/2022 07:00 | 11/13/2022 23:00 | RAS - DITTMER: RAS WS-A CONTROLLER AND MUNRO: RAS WS-B CONTROLLER | BCHT, BCHW, NI, NOEL, PA, RP, SIG, SOA, SOC, BCHT, BCHW, NI, NOEL, PA, RP, SIG, SOA, SOC
114 | 22-07846 | 11942899 | 11/13/2022 22:00 | 11/14/2022 17:00 | COLUMBIA: 4039/4040 TERMINAL OF GRAND COULEE-SCHULTZ 2 500KV LINE (UNGROUNDED) | GEN, NOH, WOCN, IROL, NOEL, NWACI, PDCI, SOC, COI, FCRPS, SIG
115 | 22-13600 | 12327192 | 11/14/2022 07:00 | 11/17/2022 15:00 | CAPTAIN JACK: PCB 4996 | NWACI, PDCI, COI
116 | 22-04981 | 11439016 | 11/14/2022 07:00 | 11/15/2022 16:00 | ECHO LAKE: PCB 5075 | BCHT, BCHW, NOEL, SOC, WOCN, NI
117 | 22-09247 | 11907712 | 11/14/2022 07:00 | 11/15/2022 17:00 | WAUTOMA: PCB 5259 | WOCN
118 | 22-01824 | 11211082 | 11/14/2022 07:30 | 11/15/2022 15:00 | HANFORD: PCB 4083 | NOH, NWACI, PDCI, WOM, WOS
119 | 22-12377 | 12186391 | 11/14/2022 07:30 | 11/17/2022 15:30 | RAVER: PCB 4314 | NOEL, RP, SOC
120 | 22-12698 | 12218460 | 11/14/2022 07:30 | 11/17/2022 15:00 | T3BA'DAS-FAIRMOUNT SECTION OF SHELTON-FAIRMOUNT NO 2 115KV LINE | PA
121 | 22-08465 | 11942938 | 11/14/2022 08:00 | 11/15/2022 15:00 | CAPTAIN JACK: PCB 4926, BFR | COI, NWACI, PDCI
122 | 22-09268 | 11942980 | 11/14/2022 08:00 | 11/17/2022 15:00 | CHIEF JOSEPH: PCB 4724, BFR & DIFFERENTIAL RELAY | NOEL, NOH, NWACI, PDCI, SOC, WOCN
123 | 22-13081 | 12264072 | 11/14/2022 08:00 | 11/17/2022 15:00 | DIAMOND LAKE-ALBENI FALLS SECTION OF THE SACHEEN-ALBENI FALLS NO 1 115KV LINE INCLUDING PCB B-960 AND THE B-960 L/S DISCONNECT | SOB
124 | 22-10940 | 12077224 | 11/14/2022 08:00 | 11/15/2022 15:00 | GARRISON: HSGS 7883 RELAY (FORCES OUT GARRISON-TAFT 2 500KV LINE) | MT-NW, SIG
125 | 22-08597 | 11871415 | 11/14/2022 08:00 | 11/18/2022 16:00 | LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE, INCLUDING LOWER GRANITE PCB'S 4770 & 4772 | GEN, GEN, MT-NW, NOH, WOH, WOLM, GEN, MT-NW, WOH, WOLM
126 | 22-11373 | 12075705 | 11/14/2022 08:00 | 11/14/2022 16:00 | MARION: PCB 4383 | NWACI, PDCI, COI
127 | 22-07084 | 11942919 | 11/14/2022 08:00 | 11/15/2022 15:00 | TAFT: HSGS 7882 RELAY (FORCES OUT GARRISON-TAFT 2 500KV LINE) | MT-NW, SIG, WOH
128 | 22-07287 | 11642088 | 11/14/2022 08:00 | 11/14/2022 17:00 | VANTAGE: 500KV EAST BUS, INCLUDING PCB 5339. PCB 5345, 500/230KV TRANSFORMER 1, 230KV AUX BUS SECTION 2, AND PCB A-1164 | NOH, WOCN, GEN, NOH, NWACI, PDCI, SIG, COI, WI, NOH, GEN, NOH, NWACI, PDCI, WOCN, COI, GEN, NOH, NWACI, PDCI, WOCN, COI
129 | 22-13471 | 12305835 | 11/14/2022 16:30 | 11/14/2022 17:00 | BIG EDDY: PCB A-836 OF, THE DALLES PH-BIG EDDY NO 5 230KV LINE | GEN, FCRPS
130 | 22-13791 | 12348067 | 11/15/2022 08:00 | 11/15/2022 17:00 | GRAYS RIVER-NASELLE SECTION OF DRISCOLL-NASELLE #1 115 KV LINE INCLUDING NASELLE PCB B-1721 AND NASELLE 115 KV AUX BUS | SOA
131 | 22-13117 | 12263365 | 11/15/2022 08:00 | 11/23/2022 15:00 | NORTH BONNEVILLE-ROSS NO 2 230KV LINE INCLUDING SIFTON TAP | GEN, SOA, WOCS, LOAD, FCRPS
132 | 22-13115 | 12263355 | 11/15/2022 08:00 | 11/23/2022 15:00 | NORTH BONNEVILLE-TROUTDALE NO 2 230KV LINE | GEN, LOAD, WOCS, FCRPS
133 | 22-07303 | 11642058 | 11/15/2022 08:00 | 11/15/2022 17:00 | VANTAGE: 500KV WEST BUS, INCLUDING PCB 5342, PCB 5351, AND 500/230KV TRANSFORMER 2 | NOH, WOCN, GEN, NOH, NWACI, PDCI, WOCN, COI, GEN, NOH, NWACI, PDCI, WOCN, COI, GEN, NOH, NWACI, SIG, COI, RATS, WI
134 | 22-07162 | 11740369 | 11/16/2022 06:00 | 11/16/2022 17:30 | VALHALLA: 115 KV WEST MAIN BUS INCLUDING PCB'S B-274, B-276, B-280, AND B-282 | CI, CI
135 | 22-13505 | 12338222 | 11/16/2022 07:00 | 11/16/2022 16:00 | COSMOPOLIS: PCB B-1330 (OPEN ENDS RAYMOND-COSMOPOLIS 1 115KV LINE) | PA, LOAD
136 | 22-04982 | 11439018 | 11/16/2022 07:00 | 11/17/2022 16:00 | ECHO LAKE: PCB 5078 | BCHT, BCHW, NOEL, SOC, WOCN, NI
137 | 22-09250 | 11907724 | 11/16/2022 07:00 | 11/17/2022 17:00 | WAUTOMA: PCB 5250 | WOCN
138 | 22-09438 | 12075741 | 11/17/2022 07:00 | 11/17/2022 15:00 | ASHE: 500KV SOUTH BUS, INCLUDING 500KV REACTOR 2 | COI, NOH, NWACI, PDCI, FCRPS
139 | 22-06629 | 12192418 | 11/17/2022 07:00 | 11/17/2022 15:00 | MONROE: 500/230KV TRANSFORMER 1 INCLUDING PCBS 5050, 5053, AND A-1421 | IROL, NOEL, SIG, SOC, NI, BCHT, BCHW, WOCN
140 | 22-09561 | 12082349 | 11/18/2022 08:00 | 11/30/2022 15:00 | FRANKLIN-ZEPHYR HEIGHTS SECTION OF THE FRANKLIN-BADGER CANYON NO 1 115KV LINE INCLUDING FRANKLIN 115KV AUX BUS AND PCB B-B1526 | TCLA, LOAD
141 | 22-12183 | 12155445 | 11/18/2022 08:00 | 11/19/2022 18:00 | SCL - DIABLO-BOTHELL 3 230KV LINE AND DIABLO BUS F
142 | 22-02195 | 10928040 | 11/18/2022 15:00 | 11/18/2022 17:00 | LOWER MONUMENTAL: 4318 TERMINAL OF LOWER MONUMENTAL PH-LOWER MONUMENTAL NO 1 500KV LINE | GEN
143 | 22-09563 | 12192427 | 11/18/2022 16:00 | 01/09/2023 08:00 | LOWER GRANITE: PCB 4770, INCLUDING MOD 4771 | GEN, MT-NW, NOH, WOH, WOLM
144 | 22-06087 | 12192475 | 11/21/2022 01:00 | 11/21/2022 01:30 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 | GEN, NOH, WOCN
145 | 22-07241 | 11832741 | 11/21/2022 06:00 | 11/21/2022 17:30 | VALHALLA: 115KV EAST MAIN BUS INCLUDING PCB'S B-284, B-286,B-288, AND THE 115 KV MAIN BUS PT'S | CI, NOH
146 | 22-09251 | 11907727 | 11/21/2022 07:00 | 11/22/2022 17:00 | WAUTOMA: PCB 5256 | NOH, WOCN
147 | 22-08466 | 11943083 | 11/21/2022 08:00 | 11/22/2022 15:00 | CAPTAIN JACK: PCB 4928 INCLUDING 500KV CAP GROUP 3 | COI, NWACI, PDCI
148 | 22-11798 | 12212500 | 11/21/2022 08:00 | 11/21/2022 15:00 | PEARL: 500KV CAP GROUP 1 INCLUDING PCB 4342 | SOA, COI, PDCI, WOCS, NWACI
149 | 22-07859 | 11943080 | 11/21/2022 08:00 | 11/21/2022 12:00 | SCHULTZ-ECHO LAKE NO 1 500KV LINE, RELAYS AND ECOL LAKE PCBS 5075 & 5078 | BCHT, BCHW, NOEL, SOC, WOCN, NI, IROL, NOH, NWACI, PDCI, SIG, COI
150 | 22-09443 | 12001528 | 11/21/2022 08:00 | 11/21/2022 15:00 | WAUTOMA: 500KV WEST BUS, INCLUDING PCB 5247 | WOCN
151 | 22-02265 | 10918122 | 11/21/2022 11:30 | 11/21/2022 17:00 | BIG EDDY: PCB A-812 OF THE DALLES PH-BIG EDDY NO 3 230KV LINE | GEN, FCRPS, COI, NWACI, PDCI, WOJD
152 | 22-11442 | 12301828 | 11/22/2022 08:00 | 11/22/2022 15:00 | WHITE BLUFFS: PCB B-1352 | TCLA, LOAD
153 | 22-05655 | 12192485 | 11/27/2022 22:00 | 12/16/2022 17:00 | COLUMBIA-GRAND COULEE NO 1 230KV LINE, GRAND COULEE: PCB 5686 | CI, NOH, WOCN, COI, NWACI, PDCI
154 | 22-02207 | 10941417 | 11/28/2022 05:00 | 12/02/2022 17:00 | LITTLE GOOSE: 4349/4351 TERMINAL OF LITTLE GOOSE PH-LITTLE GOOSE NO 1 500KV LINE | GEN, WOLM, WOLM, WOLM
155 | 22-03245 | 11233802 | 11/28/2022 06:30 | 11/28/2022 17:30 | COLUMBIA: 115KV NORTH MAIN BUS INCLUDING 115KV CENTER MAIN BUS INCLUDING PCBS B-404, B-410, B-412 AND B-314 | LOAD, WOCN, CI, CI, CI, LOAD, WOCN, CI
156 | 22-09255 | 11907731 | 11/28/2022 07:00 | 11/29/2022 17:00 | WAUTOMA: PCB 5247 | WOCN
157 | 22-12379 | 12186483 | 11/28/2022 07:30 | 12/01/2022 15:30 | RAVER: PCB 4842 | NOEL, RP, SOC
158 | 22-06371 | 11597728 | 11/28/2022 08:00 | 12/01/2022 15:30 | BIG EDDY: PCB 4860 BFR AND BREAKER DIFFERENTIAL RELAYS | NWACI, PDCI, WOJD, COI
159 | 22-06349 | 11597716 | 11/28/2022 08:00 | 12/07/2022 15:00 | CAPTAIN JACK: PCB 4983 | NWACI, PDCI, COI
160 | 22-08467 | 11943093 | 11/28/2022 08:00 | 11/29/2022 15:00 | CAPTAIN JACK: PCB 4998 INCLUDING 500KV REACTOR 1 | COI, NWACI, PDCI
161 | 22-12274 | 12192488 | 11/28/2022 08:00 | 12/23/2022 16:00 | GRIZZLY: PCB 5040 | NWACI, WOJD, COI
162 | 22-09330 | 11943167 | 11/28/2022 08:00 | 12/01/2022 15:00 | OSTRANDER: PCB 5139 | SOA, WOCN
163 | 22-11795 | 12353737 | 11/28/2022 08:00 | 12/01/2022 15:00 | PEARL: 500/230KV TRANSFORMER 1 | LOAD, SIG, SOA, WOCS
164 | 22-13363 | 12353760 | 11/30/2022 07:00 | 12/01/2022 15:00 | BOARDMAN: 115KV MAIN BUS | GEN, LOAD
165 | 22-09258 | 11907732 | 11/30/2022 07:00 | 12/01/2022 17:00 | WAUTOMA: PCB 5253 | WOCN