## Request List
Row | Request# | CAISO# | Start | End | Main Element Impacted | Path Affected
1 | 20-00289 | 11706255 | 01/22/2020 10:30 | 03/31/2023 17:00 | DETROIT: A-329 TERMINAL | GEN
2 | 21-01711 | 9741845 | 02/03/2021 09:00 | 02/28/2023 17:00 | -USBR- GRAND COULEE 287/230KV TRANSFORMER KX-17-A (OLYMPIA-GRAND COULEE NO 1 287KV LINE OPERATING AT 230KV) | NOEL, PA, RP, SOC, WOCN, IROL, NOH, OKLA
3 | 21-01581 |  | 04/30/2021 16:15 | 03/31/2023 18:00 | BCH - BURRARD SYNCHRONOUS CONDENSER STATION G2 | BCHT, BCHW, NI
4 | 21-01767 | 10359382 | 06/30/2021 10:00 | 02/03/2023 16:00 | PAUL: 4805 TERMINAL OF PAUL-PSE TONO NO 1 500KV LINE | LOAD, RP, SIG, PA
5 | 21-01784 | 11699929 | 08/25/2021 12:00 | 12/31/2022 23:59 | GARRISON: 500/230KV TRANSFORMER 1 (DERATED) | MT-NW
6 | 21-01785 | 10627331 | 08/25/2021 12:00 | 10/31/2022 23:59 | HOT SPRINGS: 500/230KV TRANSFORMER 1 (DERATED) | GEN, MT-NW, WOH
7 | 22-03687 |  | 01/25/2022 19:08 | 01/31/2023 23:59 | AVA MOSCOW 230/115KV TRANSFORMER OOS
8 | 22-04192 | 11700469 | 02/08/2022 06:00 | 10/31/2023 17:30 | MINIDOKA PH: PCB 1972 | GEN
9 | 22-06746 | 11593785 | 04/06/2022 06:30 | 12/30/2022 15:00 | CONKELLEY: LBD A-1575 INCLUDING 230KV CAP GROUP 2 SECTION 1 | MT-NW
10 | 22-06836 | 11597875 | 04/06/2022 12:25 | 12/31/2022 15:00 | OSTRANDER-TROUTDALE 1 500KV LINE INCLUDING TROUTDALE: 500/230KV TRANSFORMER BANK 8 | SIG, SOA, WOCS, SIG, WOCS, SOA
11 | 22-07667 | 11668432 | 04/21/2022 13:00 | 12/30/2022 15:00 | TROUTDALE: 500/230KV TRANSFORMER 8 | SIG, WOCS, SOA
12 | 22-07848 | 11733297 | 04/26/2022 15:00 | 10/06/2022 15:00 | ALVEY: 230KV CAP. GROUP 2, SECTION 2 INCLUDING PCB A-237 | COI, PDCI, NWACI
13 | 22-09334 | 12145389 | 06/01/2022 00:00 | 10/31/2022 23:59 | BIG EDDY-MAUPIN NO 1 230KV LINE, (DERATE)
14 | 22-08395 | 11739865 | 06/01/2022 00:00 | 10/31/2022 23:59 | BOUNDARY-SACHEEN NO 1 230KV LINE (DERATE)
15 | 22-08527 | 11756807 | 06/01/2022 00:00 | 10/31/2022 23:59 | HAT ROCK TAP TO MCNARY-PACW WALLULA NO 1 230KV LINE | WOM
16 | 22-09335 | 12145416 | 06/01/2022 00:00 | 10/31/2022 23:59 | MAUPIN-REDMOND NO 1 230KV LINE, (DERATE)
17 | 22-09321 | 12145376 | 06/01/2022 00:00 | 10/31/2022 23:59 | SACHEEN-DAY MT SPOKANE SECTION OF SACHEEN-BELL NO 1 230KV LINE, DAY MT SPOKANE-BELL SECTION OF SACHEEN-BELL NO 1 230KV LINE, (DERATED) | SOB, SOB
18 | 22-07563 | 11662212 | 06/01/2022 00:01 | 10/31/2022 23:59 | COVINGTON: 500/230KV TRANSFORMER 4, DERATED | NOEL, RP, SIG, SOC, NI, WOCN
19 | 22-07562 | 11662150 | 06/01/2022 00:01 | 10/31/2022 23:59 | COVINGTON: 500/230KV TRANSFORMER 5, DERATED | NOEL, RP, SIG, SOC, NI, WOCN
20 | 22-01027 | 11164008 | 06/01/2022 00:01 | 10/31/2022 23:59 | RIVERGATE-KEELER NO 1&2 230KV LINE (SUMMER DERATE) | SOA
21 | 22-10498 | 11965261 | 06/21/2022 15:00 | 10/31/2022 23:59 | OLYMPIA-SOUTH ELMA NO 1 115KV LINE, -DERATE- | LOAD, SI, PA, RP
22 | 22-02718 | 11176154 | 07/14/2022 07:30 | 11/17/2022 12:00 | HILLS CREEK-OAKRIDGE SECTION OF HILLS CREEK-LOOKOUT POINT NO 1 115KV LINE | GEN, COI
23 | 22-02600 | 12046993 | 07/25/2022 06:30 | 10/28/2022 15:00 | -USBR- HUNGRY HORSE PH: PCB 2382, PCB 2282 | WOH
24 | 22-10319 | 11976164 | 08/01/2022 08:00 | 12/31/2022 15:00 | NORTH BONNEVILLE: B-1518 TERMINAL OF THE UNDERWOOD TAP TO BONNEVILLE PH1-ALCOA NO 1&2 115 KV LINE | WOCS
25 | 22-12182 | 12155060 | 08/19/2022 08:00 | 11/19/2022 18:00 | SCL - DIABLO-BOTHELL 3 230KV LINE | NOEL, SOC
26 | 22-05597 | 11493040 | 08/22/2022 08:00 | 11/18/2022 15:00 | BETTAS ROAD-COLUMBIA NO 1 230KV LINE INCLUDING BETTAS ROAD 230KV EAST BUS AND PCB A-3046 | NOEL, SOC, WOCN, WOCN, CI, NOEL, NOH, SOC, WOCN, IROL, NOEL, SOC, WOCN, NOEL, SOC, WOCN
27 | 22-00917 | 11237862 | 08/29/2022 17:00 | 10/31/2022 07:30 | HANFORD: PCB 4098 INCLUDING MODS 4097 & 4099 | NWACI, PDCI, WOLM, COI, NOH, WOM
28 | 22-01184 | 10085244 | 09/01/2022 08:00 | 10/27/2022 14:00 | BENTON-RINGOLD SECTION OF BENTON-SCOOTENEY NO 1 115KV LINE , MIDWAY-SCOOTENEY TAP SECTION OF MIDWAY-BENTON NO 1 115KV LINE | TCLA, TCLA, GEN
29 | 22-04801 | 11350616 | 09/12/2022 08:00 | 10/21/2022 16:00 | CLYMER-MOXEE SECTION OF ELLENSBURG-MOXEE NO 1 115KV LINE | TCLA
30 | 22-07682 | 11685020 | 09/13/2022 08:00 | 10/06/2022 15:00 | NORTH BONNEVILLE-ROSS NO 2 230KV LINE INCLUDING SIFTON TAP | GEN, SOA, WOCS, LOAD, GEN, LOAD, WOCS, FCRPS
31 | 22-07686 | 11684994 | 09/13/2022 08:00 | 10/06/2022 15:00 | NORTH BONNEVILLE-TROUTDALE NO 2 230KV LINE | GEN, LOAD, WOCS, FCRPS, WOCS
32 | 22-07738 | 11683455 | 09/19/2022 07:00 | 10/02/2022 17:30 | ALVEY: A-656 TERMINAL OF ALVEY-DIXONVILLE NO 1 230KV LINE -UNGROUNDED- | COI, NWACI, PDCI, COI, PDCI, NWACI
33 | 22-02693 | 11337686 | 09/19/2022 07:00 | 10/06/2022 15:00 | TAFT-HOT SPRINGS #1 500KV LINE (UNGROUNDED) INCLUDING: HOT SPRINGS: 500/230KV TRANSFORMER 1, 500KV REACTOR 1, PCB 4478, PCB 4562, TAFT-HOT SPRINGS NO 1 500KV LINE | GEN, MT-NW, WOH, MT-NW, WOH, GEN, MT-NW, SIG, WOH, MT-NW, WOH, GEN, MT-NW, WOH
34 | 22-02103 | 10879173 | 09/26/2022 01:00 | 10/07/2022 20:00 | GRAND COULEE: PCB 2296, PCB 2292 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI
35 | 22-03186 | 11220346 | 09/26/2022 06:00 | 10/07/2022 22:00 | RAS - DITTMER: RAS AC-A CONTROLLER, DC-A CONTROLLER, WS-A CONTROLLER AND SYNCHROPHASOR-A CONTROLLER | SIG, COI, NOH, NWACI, PDCI, WOM, WOS, SIG, COI, NOH, NWACI, PDCI, WOM, WOS, BCHT, BCHW, NI, NOEL, PA, RP, SIG, SOA, SOC
36 | 22-06513 | 11597287 | 09/26/2022 07:00 | 10/16/2022 16:00 | CHIEF JOSEPH: 500/230KV TRANSFORMER 3, INCLUDING PCB 4728 | NOEL, NOH, SOC, FCRPS, GEN, NOEL, NOH, NWACI, PDCI, SOC, WOCN, COI, BCHT, BCHW, WOCN
37 | 22-04894 | 11374283 | 09/26/2022 13:00 | 11/03/2022 12:00 | PAUL-OLYMPIA NO 1 500KV LINE INCLUDING OLYMPIA: 500/230KV TRANSFORMER 5, PCB A-1772 AND PAUL PCB'S 4550 & 4554 | NWACI, PDCI, COI, WOCS, SOA, RP, WOCS, SOA, LOAD, PA, RP, SIG, LOAD, NOEL, PA, RP, SIG, IROL
38 | 22-00837 | 10858433 | 09/26/2022 14:00 | 10/03/2022 13:00 | LAPINE: 115KV MAIN BUS INCLUDING PCB B-1279 AND 230/115KV TRANSFORMER 1 | LOAD, COR, NWACI, COI
39 | 22-06528 | 11596882 | 09/30/2022 16:01 | 10/24/2022 08:00 | LOWER MONUMENTAL: PCB 4263 AND MOD 4257 | WOLM
40 | 22-06383 | 11563686 | 10/01/2022 07:00 | 10/01/2022 16:00 | CAPTAIN JACK-MALIN NO 1 500KV LINE | NWACI, PDCI, SIG, COI, COI, NWACI, PDCI, COI, NWACI, PDCI
41 | 22-06384 | 11563715 | 10/02/2022 07:00 | 10/02/2022 16:00 | GRIZZLY-CAPTAIN JACK 1 500KV LINE INCLUDING SAND SPRINGS, FORT ROCK AND SYCAN SERIES CAP GROUPS 1 | COI, PDCI, NWACI, BCHT, BCHW, NI, NWACI, PDCI, SIG, BCHT, BCHW, NI, NWACI, PDCI, SIG, COI, SIG, COI, NWACI, PDCI
42 | 22-02596 | 11285522 | 10/02/2022 22:00 | 10/07/2022 17:00 | CHIEF JOSEPH: 4578/4729 TERMINAL OF GRAND COULEE-CHIEF JOSEPH NO 3 500KV LINE | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, SIG, COI, FCRPS, MT-NW, NWACI, PDCI, WOCN, WOH, WOLM
43 | 22-06200 | 11575501 | 10/03/2022 07:00 | 10/06/2022 16:00 | BELL: PCB 5307 | GEN, MT-NW, WOH
44 | 22-08293 | 12045986 | 10/03/2022 07:00 | 10/06/2022 15:00 | CELILO: PCB 5515, INCLUDING BIG EDDY 1 LINE CAP GROUP 4 | PDCI
45 | 22-02661 | 11120726 | 10/03/2022 07:00 | 10/04/2022 16:00 | GARRISON: BROADVIEW 1 500KV LINE SERIES CAP GROUP 1 INCL PCB 4469 | MT-NW
46 | 22-01952 | 10821249 | 10/03/2022 07:00 | 11/17/2022 17:00 | LONGVIEW: 230KV CAP GROUP 6 SECTIONS 1 AND 2 INCLUDING PCB A-648, LBD'S A-1640 AND A-1641, AND ALL ASSOCIATED RELAYS AND WIRING | LOAD, SOA, LOAD, SOA, SOA
47 | 22-06387 | 11563771 | 10/03/2022 07:00 | 10/04/2022 16:00 | MCNARY-JOHN DAY NO 2 500KV LINE | NWACI, PDCI, SIG, WOJD, WOM, WOS, COI, WOCS
48 | 22-02676 | 11233752 | 10/03/2022 07:00 | 10/06/2022 17:30 | NOXON-LIBBY NO 1 230KV LINE | MT-NW, WOH, FCRPS, GEN
49 | 22-12094 | 12148648 | 10/03/2022 07:00 | 10/06/2022 16:30 | -OKPUD- OKANOGAN-SANDFLAT SECTION OF THE OKANOGAN-EAST OMAK NO 1 115KV LINE | OKLA
50 | 22-02454 | 11040116 | 10/03/2022 07:30 | 10/04/2022 14:00 | MONROE: PCB 5047, INCLUDING 500KV CAP GROUP 3 | WOCN, NI, NOEL, SOC, IROL, NOEL, SOC, WOCN, NI
51 | 22-07837 | 11699754 | 10/03/2022 07:30 | 10/03/2022 15:00 | SLATT: PCB 5003 | GEN, NWACI, PDCI, COI
52 | 22-10475 | 11964596 | 10/03/2022 08:00 | 10/20/2022 16:00 | BELL: A-362 TERMINAL OF THE AVA WESTSIDE-BELL NO 1 230KV LINE | MT-NW, WOH, SOB
53 | 22-06347 | 11597384 | 10/03/2022 08:00 | 10/13/2022 15:00 | CAPTAIN JACK: PCB 4986 | NWACI, PDCI, COI
54 | 22-06014 | 11537545 | 10/03/2022 08:00 | 11/18/2022 17:00 | GRIZZLY: 500KV REACTOR 3 INCLUDING PCB 4038 | COI, NWACI, PDCI, COI, PDCI, NWACI
55 | 22-03703 | 11300375 | 10/03/2022 08:00 | 10/05/2022 15:00 | MALIN: PCB 4072 | NWACI, PDCI, COI
56 | 22-00864 | 11234448 | 10/03/2022 08:00 | 10/07/2022 18:30 | MAUPIN-REDMOND NO 1 230KV LINE
57 | 22-11905 |  | 10/03/2022 08:00 | 10/07/2022 15:00 | -PACW- FRY-PARRISH GAP 230KV LINE | COI, NWACI, SLAL
58 | 22-02115 |  | 10/03/2022 08:00 | 11/02/2022 16:00 | -PGE- BETHEL (PGE)-ROUND BUTTE 230KV LINE | COI, NWACI, PDCI, WOCS
59 | 22-07321 | 11901524 | 10/03/2022 08:00 | 10/06/2022 15:00 | SCHULTZ-RAVER NO 3 500KV LINE | IROL, NOEL, NOH, NWACI, PDCI, SIG, SOC, WOCN, COI
60 | 22-01958 | 10764208 | 10/03/2022 08:00 | 10/04/2022 15:00 | SCHULTZ-WAUTOMA NO 1 500KV LINE INCLUDING WAUTOMA: 500KV EAST BUS, PCBS 5241, 5244, 5253, 5262 AND SCHULTZ: PCBS 5170, 5173 | BCHT, BCHW, IROL, NI, NOH, NWACI, PDCI, SIG, WOCN, COI, WOCN, NOH, WOCN, NOH, WOCN, NWACI, COI, NOH, WOCN, WOCN, COI, NWACI, NOH, WOCN, WOCN
61 | 22-10217 |  | 10/03/2022 08:00 | 10/04/2022 15:00 | -SCL- NORTH 120kV BUS 4 / BANK 54 / BKR'S 120-77 & 120-79
62 | 22-02415 | 11175742 | 10/03/2022 08:00 | 10/04/2022 16:30 | SUMNER-FAIRVIEW SECTION OF REEDSPORT-FAIRVIEW NO 1 115KV LINE | LOAD, SWORE
63 | 22-01164 | 7851020 | 10/03/2022 08:30 | 10/04/2022 14:00 | BADGER CANYON-REATA NO 1 115KV LINE INCLUDING THE LESLIE RD TAP AND BADGER CANYON: 115KV AUX BUS
64 | 22-12109 | 12154623 | 10/03/2022 09:30 | 10/03/2022 10:30 | GARRISON: BROADVIEW 2 500KV LINE SERIES CAP GROUP 2 INCLUDING PCB 4468 | MT-NW
65 | 22-12110 | 12154674 | 10/03/2022 10:30 | 10/03/2022 11:30 | GARRISON: TAFT 1 500KV LINE SERIES CAP GROUP 1 INCLUDING PCB 4461 | MT-NW
66 | 22-12111 | 12154680 | 10/03/2022 11:30 | 10/03/2022 12:30 | GARRISON: TAFT 2 500KV LINE SERIES CAP GROUP 1 INCLUDING PCB 4458 | MT-NW
67 | 22-00836 | 10858155 | 10/03/2022 14:00 | 10/10/2022 14:00 | LAPINE: 115KV MAIN BUS INCLUDING PCB B-1280 AND 230/115KV TRANSFORMER 2 | LOAD, NWACI, COI, LOAD
68 | 22-08172 | 11724758 | 10/04/2022 06:30 | 10/04/2022 12:00 | COLVILLE-KETTLE FALLS SECTION OF COLVILLE-REPUBLIC 1 115KV LINE INCLUDING PCB B-1768 AND 115KV AUX BUS
69 | 22-07838 | 11804179 | 10/04/2022 07:30 | 10/04/2022 15:00 | SLATT: PCB 5021 | NWACI, PDCI, WOJD, COI
70 | 22-09449 | 12047923 | 10/04/2022 08:00 | 10/05/2022 15:00 | MIDWAY: 230/115KV TRANSFORMER 3 INCLUDING PCB B-154 AND THE 115KV AUX BUS | TCLA
71 | 22-08215 | 12181509 | 10/04/2022 12:00 | 10/04/2022 16:00 | COLVILLE: PCB B-1766 (OPEN ENDS COLVILLE-BOUNDARY NO 1 115KV LINE) | SOB
72 | 22-01956 | 10764220 | 10/04/2022 15:00 | 11/09/2022 08:00 | SCHULTZ-WAUTOMA NO 1 500KV LINE INCLUDING WAUTOMA: PCBS 5241 & 5244 & BAY 2E TO REMOVED BUS BETWEEN MOD 5240 & PCB 5241 AND BAY 2E PORTION OF EAST BUS TO REMOVED BUS BETWEEN BAYS 2E (SCHULTZ #1) TO BAY 3E ( HANFORD #1) | BCHT, BCHW, IROL, NI, NOH, NWACI, PDCI, SIG, WOCN, COI, NOH, WOCN, NOH, WOCN, NOH, WOCN, WOCN
73 | 22-11498 | 12087900 | 10/05/2022 06:00 | 10/05/2022 08:00 | KALISPELL: 115kV Cap Group 1 Sections 1,2,3 including PCBs B-1297, B-1962, and B-1963
74 | 22-12134 | 12154537 | 10/05/2022 07:00 | 10/05/2022 08:00 | Columbia Falls: 115kv Cap Group 1 Sections 1 and 2
75 | 22-02662 | 11120732 | 10/05/2022 07:00 | 10/06/2022 16:00 | GARRISON: BROADVIEW 2 500KV LINE SERIES CAP GROUP 2 INCL PCB 4468 | MT-NW
76 | 22-06388 | 11563893 | 10/05/2022 07:00 | 10/05/2022 16:00 | ROCK CREEK-JOHN DAY NO 1 500KV LINE | BCHT, BCHW, NI, NOH, NWACI, PDCI, SIG, WOJD, WOM
77 | 22-01166 | 7851019 | 10/05/2022 08:00 | 10/14/2022 15:00 | BADGER CANYON-REATA NO 1 115KV LINE
78 | 22-12136 | 12154551 | 10/05/2022 08:00 | 10/05/2022 09:00 | Conkelly: 230kv Cap Group 1 Sect 3 and 4 | MT-NW
79 | 22-12184 | 12155299 | 10/05/2022 08:00 | 10/19/2022 18:00 | SCL - BOTHELL 230KV BUS 3 (DIABLO-BOTHELL 3, BOTHELL-SNO-KING 1 230KV LINE AND BOTHELL 230/115KV BANK 63) | NOEL, SOC
80 | 22-11500 | 12087723 | 10/05/2022 12:00 | 10/05/2022 14:00 | TREGO: 115KV CAP GROUP 1
81 | 22-06390 | 11563960 | 10/06/2022 07:00 | 10/07/2022 16:00 | KNIGHT-OSTRANDER NO 1 500KV LINE | BCHT, BCHW, NI, NWACI, PDCI, SIG, WOCS, WOJD, COI, WOCN
82 | 22-02483 | 11034538 | 10/06/2022 07:30 | 10/06/2022 09:00 | RAVER: PCB 4299 | NOEL, RP, SOC
83 | 22-10334 |  | 10/06/2022 08:00 | 10/08/2022 20:00 | PAC- KLAMATH FALLS-SNOW GOOSE 230KV LINE | COI, NWACI
84 | 22-05964 |  | 10/06/2022 08:00 | 10/06/2022 16:00 | PSE- HORSE RANCH: 230KV PCB 7412 (FORCES OUT HORSE RANCH TAP TO MONROE-SNOHOMISH 1&2) | BCHT, BCHW, NOEL, SOC, SIG
85 | 22-02484 | 11034543 | 10/06/2022 09:00 | 10/06/2022 11:00 | RAVER: PCB 4302 | NOEL, RP, SOC, WOCN
86 | 22-04650 | 11337774 | 10/06/2022 14:00 | 10/06/2022 15:00 | TAFT: 500KV BUS 1, PCB 4111, PCB 4122, PCB 4148 | MT-NW, WOH, GEN, MT-NW, NOH, WOH, GEN, MT-NW, WOH, GEN, MT-NW, WOH
87 | 22-11313 | 12066347 | 10/06/2022 22:00 | 10/07/2022 06:00 | SILVERADO-SAPPHO SECTION OF PORT ANGELES-SAPPHO NO 1 115KV LINE | WOCN, SOA
88 | 22-05800 | 11537529 | 10/08/2022 07:00 | 10/16/2022 17:00 | GRIZZLY-PONDEROSA SECTION OF GRIZZLY-SUMMER LAKE NO.1 500KV LINE INCLUDING GRIZZLY: PCB'S 5025 & 5028 | SIG, COI, NWACI, PDCI, BCHT, BCHW, NI, COI, PDCI, NWACI, COI, NWACI, PDCI, NWACI, WOJD, COI, NWACI, PDCI, COI, SIG, COI, NWACI, PDCI, COI, PDCI, NWACI, SIG, COI, NWACI, PDCI, BCHT, BCHW, NI
89 | 22-06512 | 12181552 | 10/08/2022 11:00 | 10/08/2022 16:00 | PONDEROSA-SAND SPRINGS SECTION OF GRIZZLY-SUMMER LAKE 1 500KV LINE
90 | 22-09596 | 11937295 | 10/10/2022 07:00 | 10/13/2022 16:00 | MCNARY: PCB 4231, BFR | NWACI, PDCI, WOM, COI
91 | 22-10521 |  | 10/10/2022 07:00 | 10/14/2022 17:00 | -PACW- FRY-OREMET SECTION OF FRY-HAZELWOOD 115KV LINE | SLAL
92 | 22-10340 |  | 10/10/2022 08:00 | 10/13/2022 20:00 | PAC- KLAMATH FALLS-SNOW GOOSE 230KV LINE | COI, NWACI
93 | 22-03187 | 11220347 | 10/11/2022 06:00 | 10/21/2022 23:00 | RAS - MUNRO: RAS AC-B CONTROLLER, RAS DC-B CONTROLLER, RAS WS-B CONTROLLER, RAS SYNCHROPHASOR-B CONTROLLER | SIG, COI, NOH, NWACI, PDCI, WOM, WOS, SIG, COI, NWACI, PDCI, WOM, WOS, BCHT, BCHW, NI, NOEL, PA, RP, SIG, SOA, SOC
94 | 22-06407 | 12182560 | 10/11/2022 07:00 | 10/20/2022 17:30 | ALVEY: 115KV SOUTH MAIN BUS INCLUDING PCBs: B-570, B-572, and B-578 | GEN, SLAL, GEN, SLAL
95 | 22-04737 | 11342254 | 10/11/2022 07:00 | 10/13/2022 16:30 | BELL: PCB 5316 | GEN, MT-NW, WOH
96 | 22-06624 | 11597412 | 10/11/2022 07:00 | 10/11/2022 16:00 | RAVER: PCB 4302 | NOEL, RP, SOC, WOCN
97 | 22-07857 | 11693780 | 10/11/2022 07:00 | 10/11/2022 16:00 | SATSOP-ABERDEEN NO 3 230KV LINE INCLUDING SATSOP: PCBS A-616 AND A-619 | LOAD, PA, SI, PA, LOAD, GEN, LOAD, PA, GEN, LOAD, PA
98 | 22-10808 | 12066038 | 10/11/2022 08:00 | 10/12/2022 11:00 | BAKEOVEN: JOHN DAY-GRIZZLY 1 500KV LINE SERIES CAP GROUP 1 INCLUDING PCB 5363 | NWACI, PDCI, COI, WOJD
99 | 22-01762 | 12069972 | 10/11/2022 08:00 | 10/12/2022 15:00 | CAPTAIN JACK: PCB 4977 | NWACI, PDCI, COI
100 | 22-09437 | 11901560 | 10/11/2022 08:00 | 10/11/2022 17:30 | CHIEF JOSEPH: PCB 4730 | NOEL, NOH, NWACI, PDCI, SOC, COI, WOCN
101 | 22-03706 | 11300484 | 10/11/2022 08:00 | 10/13/2022 15:00 | MALIN: PCB 4582 | NWACI, PDCI, COI
102 | 22-01217 | 11091486 | 10/11/2022 08:00 | 10/16/2022 17:30 | MALIN-HILLTOP NO 1 230KV LINE INCLUDING CANBY TAP (UNGROUNDED) | COI, PDCI, RATS, NWACI, COI, PDCI, RATS, NWACI, RATS, RATS, COI, PDCI, RATS, NWACI
103 | 22-12027 | 12143885 | 10/11/2022 08:00 | 10/14/2022 17:00 | PONDEROSA-PILOT BUTTE NO 1 230KV LINE | NWACI, PDCI, COI
104 | 22-07156 | 11642175 | 10/11/2022 08:15 | 10/11/2022 08:45 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI
105 | 22-07155 | 11642158 | 10/11/2022 09:15 | 10/11/2022 09:45 | GRAND COULEE: PCB 2092, GRAND COULEE: PCB 2096 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI
106 | 22-07157 | 11642156 | 10/11/2022 10:15 | 10/11/2022 10:45 | GRAND COULEE: PCB 2292, GRAND COULEE: PCB 2296 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI
107 | 22-07158 | 11642144 | 10/11/2022 11:15 | 10/11/2022 11:45 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI
108 | 22-07159 | 11642139 | 10/11/2022 12:45 | 10/11/2022 13:15 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 | GEN, NOH, COI, NWACI, PDCI, GEN, WOCN, COI, NOH, NWACI, PDCI
109 | 22-01753 | 11045596 | 10/11/2022 22:00 | 10/12/2022 06:00 | HARNEY: HARNEY ELEC COOP 115KV FEEDER 1 INCLUDING PCB B-1712 AND 115KV AUX BUS (UNGROUNDED)
110 | 22-02526 | 11064922 | 10/12/2022 08:00 | 10/12/2022 16:30 | OSTRANDER-MCLOUGHLIN NO 1 230KV LINE, INCLUDING OSTRANDER: PCB'S 4442,4445 AND 500/230KV TRANSFORMER 1 | LOAD, SIG, SOA, WOCS, COI, NWACI, PDCI
111 | 22-10811 | 12066196 | 10/12/2022 12:00 | 10/13/2022 15:00 | BAKEOVEN: JOHN DAY-GRIZZLY 2 500KV LINE SERIES CAP GROUP 2, INCLUDING PCB 5367 | NWACI, PDCI, COI, WOJD
112 | 22-01754 | 11045396 | 10/13/2022 11:00 | 11/22/2022 15:00 | HINES-HARNEY NO 1 115KV LINE INCLUDING HARNEY: PCB B-1710 AND THE 115KV AUX BUS (UNGROUNDED) | ID-NW
113 | 22-11129 | 12041374 | 10/13/2022 16:30 | 10/13/2022 17:00 | MCNARY: PCB A-420 OF THE MCNARY PH-MCNARY NO 3&4 230KV LINE | GEN
114 | 22-04703 | 11337207 | 10/14/2022 15:00 | 10/14/2022 17:00 | LOWER MONUMENTAL: 4318 TERMINAL OF LOWER MONUMENTAL PH-LOWER MONUMENTAL NO 1 500KV LINE | GEN
115 | 22-05458 | 8999942 | 10/15/2022 04:00 | 11/13/2022 21:00 | LDWP - ANNUAL FALL 2022 SIR (CELILO: 9085 TERMINAL OF CELILO-SYLMAR POLE 3 AND 9084 TERMINAL OF CELILO-SYLMAR POLE 4 1000KV LINE) | PDCI, SIG
116 | 22-09962 | 11908026 | 10/15/2022 08:00 | 11/08/2022 15:00 | CELILO: RAS DC-A CONTROLLER SCADA MASTER CKT 6196, CELILO: RAS DC-B CONTROLLER SCADA MASTER CKT 6218
117 | 22-00105 | 9534877 | 10/16/2022 08:00 | 11/17/2022 17:00 | -USBR- GRAND COULEE: PCB 5382 | NOH, WOCN, COI, NWACI, PDCI
118 | 22-02585 | 11044977 | 10/17/2022 01:00 | 10/28/2022 19:00 | GRAND COULEE: PCB 2396, PCB 2392 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI
119 | 22-06204 | 11575518 | 10/17/2022 07:00 | 10/20/2022 16:00 | BELL: PCB 5310 | GEN, MT-NW, WOH
120 | 22-09598 | 11937299 | 10/17/2022 07:00 | 10/20/2022 16:00 | MCNARY: PCB 5217, BFR | NWACI, PDCI, WOCS, WOJD, WOM, COI
121 | 22-08155 | 11996068 | 10/17/2022 07:30 | 10/20/2022 15:00 | JOHN DAY: PCB 5441, PCB 5441 SEL-352 BFR AND PCB 5441 SEL-587 BKR DIFF RELAYS | NWACI, PDCI, WOJD, WOM, WOS, COI
122 | 22-10980 | 12181559 | 10/17/2022 08:00 | 10/19/2022 15:30 | BIG EDDY: 500/230KV TIE NO 1 500KV LINE RELAYS (TIE NO1 AND ASSOCIATED BANKS & PCB'S WILL BE FORCED OUT) | GEN, NWACI, PDCI, WOJD, COI, SIG, FCRPS, BGEDY, SOA
123 | 22-01165 | 7851018 | 10/17/2022 08:00 | 10/18/2022 15:00 | BADGER CANYON-REATA NO 1 115KV LINE INCLUDING THE LESLIE RD TAP AND BADGER CANYON: 115KV AUX BUS
124 | 22-07931 | 12181580 | 10/17/2022 08:00 | 10/21/2022 15:00 | DRISCOLL: PCB A-1264 (OPEN END ALLSTON-CLATSOP-DRISCOLL TAP NO 1 230KV LINE AT DRISCOLL) | SOA, LOAD, SOA, SOA
125 | 22-03733 | 11300513 | 10/17/2022 08:00 | 10/19/2022 14:30 | LITTLE GOOSE: PCB 4626 | WOLM
126 | 22-04679 | 11341784 | 10/17/2022 08:00 | 10/27/2022 15:00 | MALIN: PCB 4182 INCLUDING 500KV CAP GROUP 3 | COI, NWACI, PDCI, COI, NWACI, PDCI
127 | 22-02009 | 11234453 | 10/17/2022 08:00 | 10/21/2022 16:30 | MAUPIN-REDMOND NO 1 230KV LINE
128 | 22-08328 | 11755636 | 10/17/2022 08:00 | 11/08/2022 15:00 | MCNARY: 345/230KV TRANSFORMER 8 | SOA, WOCS, WOM
129 | 22-08157 | 11755668 | 10/17/2022 08:00 | 10/21/2022 15:00 | MCNARY-ROSS NO 1 345KV LINE INCLUDING ROSS PCB A-142 AND MCNARY PCB A-432 | SOA, WOCS, SOA, WOCS, WOM, SOA, WOCS, WOM
130 | 22-05898 | 11540488 | 10/17/2022 08:00 | 10/18/2022 15:00 | OSTRANDER: PCB 4450 | WOCS
131 | 22-08162 | 11755644 | 10/17/2022 08:00 | 11/08/2022 15:00 | ROSS: 345/230KV TRANSFORMER 4 | SOA, WOCS, WOM
132 | 22-09615 | 11874119 | 10/17/2022 08:00 | 10/30/2022 17:00 | SUMMER LAKE: 4951/4952 TERMINAL OF , HEMINGWAY-SUMMER LAKE NO 1 500KV LINE | ID-NW, NWACI, SIG, COI
133 | 22-07976 | 11942753 | 10/18/2022 05:00 | 10/18/2022 18:00 | TACOMA-TPWR NORTHEAST NO 3 230KV LINE, INCLUDING TACOMA 230KV SOUTH MAIN BUS, AND AUX BUS | PA, RP, NOEL, SOC
134 | 22-03646 | 11313791 | 10/18/2022 06:00 | 10/21/2022 16:00 | CUSTER: 500/230KV TRANSFORMER 2 INCLUDING STATION SERVICE 2 | NOEL, SIG, SOC, NI
135 | 22-02768 | 11120682 | 10/18/2022 07:00 | 10/27/2022 17:00 | LOWER MONUMENTAL-ASHE NO 1 500KV LINE | GEN, NWACI, PDCI, SIG, WOLM, COI, GEN, NWACI, PDCI, WOLM, COI, FCRPS, NOH, GEN, NWACI, PDCI, COI, FCRPS, NOH
136 | 22-00923 | 11137273 | 10/18/2022 12:00 | 10/18/2022 15:00 | CHIEF JOSEPH PH-CHIEF JOSEPH NO 5 500KV LINE INCLUDING CHIEF JOSEPH: PCB 4588, PCB 4724 | GEN, FCRPS, NOH, BCHT, BCHW, GEN, NOH, NWACI, PDCI, WOCN, COI, NOEL, NOH, NWACI, PDCI, SOC, WOCN
137 | 22-07985 | 11971571 | 10/18/2022 18:00 | 10/19/2022 16:30 | TACOMA-TPWR NORTHEAST NO 3 230KV LINE
138 | 22-01794 | 11563220 | 10/19/2022 07:30 | 10/29/2022 15:30 | FRANKLIN: PCB B-610 INCLUDING FRANKLIN-FOSTER WELLS SECTION OF THE FRANKLIN RUBY STREET NO 1 115 KV LINE AND THE WEST AUX BUS SECTION | TCLA
139 | 22-04820 | 12181210 | 10/19/2022 08:00 | 10/20/2022 16:00 | GARRISON: 500/230KV TRANSFORMER 1 | MT-NW
140 | 22-05899 | 11540510 | 10/19/2022 08:00 | 10/20/2022 15:00 | OSTRANDER: PCB 4445 | WOCS
141 | 22-02480 | 11034552 | 10/20/2022 07:00 | 10/20/2022 09:00 | RAVER: PCB 4876 | NOEL, RP, SOC
142 | 22-02481 | 11034555 | 10/20/2022 09:00 | 10/20/2022 11:00 | RAVER: PCB 4879 | NOEL, RP, SOC
143 | 22-03828 | 11300489 | 10/20/2022 09:30 | 10/20/2022 10:30 | MALIN: PCB 4072 | NWACI, PDCI, COI
144 | 22-03827 | 11300506 | 10/20/2022 10:30 | 10/20/2022 11:30 | MALIN: PCB 4582 | NWACI, PDCI, COI
145 | 22-00928 | 11137287 | 10/20/2022 12:00 | 10/20/2022 15:00 | CHIEF JOSEPH PH-CHIEF JOSEPH NO 6 500KV LINE INCLUDING CHIEF JOSEPH: PCB 4598, PCB 4730 | GEN, FCRPS, NOH, GEN, NOEL, SOC, WOCN, GEN, NOEL, NOH, NWACI, PDCI, SOC, COI, WOCN
146 | 22-08214 | 11995397 | 10/20/2022 13:00 | 10/20/2022 15:00 | JOHN DAY: PCB 5444 | NWACI, PDCI, WOJD, WOM, WOS, COI
147 | 22-08243 | 11755980 | 10/21/2022 15:00 | 11/09/2022 08:00 | MCNARY-ROSS NO 1 345KV LINE | SOA, WOCS, WOM
148 | 22-03191 | 11220348 | 10/22/2022 06:00 | 10/23/2022 23:00 | RAS - DITTMER: RAS DC-A CONTROLLER AND MUNRO: RAS DC-B CONTROLLER | SIG, COI, NOH, NWACI, PDCI, WOM, WOS, SIG, COI, NWACI, PDCI, WOM, WOS
149 | 22-06395 | 12181596 | 10/22/2022 08:00 | 10/22/2022 15:00 | PONDEROSA-PILOT BUTTE NO 1 230KV LINE | NWACI, PDCI, COI
150 | 22-06399 | 12181600 | 10/23/2022 08:00 | 10/23/2022 15:00 | LAPINE-FORT ROCK NO 1 115KV LINE | NWACI, COI, LOAD
151 | 22-11565 | 12086822 | 10/24/2022 07:00 | 10/27/2022 16:00 | BELL: 500/230KV TRANSFORMER 1 | GEN, MT-NW, WOH
152 | 22-09604 | 11937494 | 10/24/2022 07:00 | 10/25/2022 16:00 | MCNARY: PCB 4234, BFR | NWACI, PDCI, WOM, COI
153 | 22-03652 | 11433789 | 10/24/2022 07:00 | 10/27/2022 16:00 | WAGNER LAKE TAP TO WILBUR TAP TO GRAND COULEE-CRESTON NO 1 115KV LINE | LOAD
154 | 22-10254 | 12144332 | 10/24/2022 07:30 | 10/24/2022 16:00 | MIDWAY-POTHOLES NO 1 230KV LINE INCLUDING MIDWAY 230KV AUX BUS SECTION 1 AND PCB A-60 | WOM, GEN, NOH
155 | 22-12197 |  | 10/24/2022 08:00 | 11/09/2022 15:00 | PGE - KEELER-ST MARYS NO 1 230KV LINE (KEELER: A-899 TERMINAL OF KEELER-PGE ST MARYS NO 1 230KV LINE | SOA, SIG, LOAD
156 | 22-06522 | 11596932 | 10/24/2022 08:00 | 10/28/2022 15:00 | LOWER MONUMENTAL: 500KV WEST BUS INCLUDING PCB 4263 | WOLM, WOLM
157 | 22-05900 | 11540388 | 10/24/2022 08:00 | 10/25/2022 15:00 | OSTRANDER: 500KV CAP GROUP 1 INCLUDING PCB 5135 | NWACI, PDCI, WOCS, COI, WOCS, NWACI, PDCI, WOCS, COI, NWACI, PDCI, WOCS, COI
158 | 22-01218 | 9430850 | 10/24/2022 08:00 | 10/28/2022 17:30 | REDMOND-PILOT BUTTE PACW NO 1 230KV LINE | NWACI, PDCI, COI, LOAD
159 | 22-11382 | 12082796 | 10/24/2022 08:00 | 10/27/2022 15:00 | SW48-ALCOA SECTION OF PIONEER-ALCOA NO 1 115KV LINE | SOA, GEN, LOAD
160 | 22-06514 | 11575091 | 10/25/2022 07:00 | 10/25/2022 16:00 | BUCKLEY-GRIZZLY NO 1 500KV LINE | BCHT, BCHW, NI, NWACI, PDCI, SIG, WOJD, COI
161 | 22-10941 | 12077054 | 10/25/2022 08:00 | 10/26/2022 16:00 | GARRISON: HSGS 7885 RELAY (FORCES OUT GARRISON-TAFT 1 500KV LINE) | MT-NW, SIG
162 | 22-00982 | 11455440 | 10/25/2022 08:00 | 11/17/2022 14:30 | NORTH BONNEVILLE-OUTLOOK SECTION OF NORTH BONNEVILLE-MIDWAY NO 1 230KV LINE INCLUDING ALFALFA TAP, ALFALFA: 230/34.5KV TRANSFORMER 1, PCB A-1272 AND 34.5KV PCBS L-1456 & L-1458 AND YAKAMA POWER 34.5KV FEEDER #1 SATUS TO OPEN JUMPERS AT A001-1605, FEEDER #2 HARRAH TO OPEN JUMPERS AT A139-1605, NORTH BONNEVILLE-ALFALFA SECTION OF NORTH BONNEVILLE-MIDWAY NO 1 230KV LINE, ALFALFA TAP TO NORTH BONNEVILLE-MIDWAY NO 1 230KV LINE, ALFALFA-OUTLOOK SECTION OF NORTH BONNEVILLE-MIDWAY NO 1 230KV LINE, ALFALFA: YAKAMA POWER 34.5KV FEEDER 1, ALFALFA: YAKAMA POWER 34.5KV FEEDER 2, OUTLOOK: PACIFICORP (PACW) 230KV FEEDER 1 | WOCS, WOCS, NWACI, PDCI, WOCS, COI, WOCS
163 | 22-09961 | 11907730 | 10/25/2022 09:00 | 10/26/2022 16:00 | TAFT: HSGS 7879 RELAY (FORCES OUT GARRISON-TAFT 1 500KV LINE) | MT-NW, WOH, SIG
164 | 22-07415 | 11907633 | 10/25/2022 10:15 | 10/25/2022 10:45 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 | GEN, NOH, WOCN, GEN, NOH, WOCN
165 | 22-07416 | 11907626 | 10/25/2022 11:15 | 10/25/2022 11:45 | GRAND COULEE: PCB 2092, GRAND COULEE: PCB 2096 | GEN, NOH, WOCN, GEN, NOH, WOCN
166 | 22-07417 | 11907608 | 10/25/2022 12:45 | 10/25/2022 13:15 | GRAND COULEE: PCB 2292, GRAND COULEE: PCB 2296 | GEN, NOH, WOCN, GEN, NOH, WOCN
167 | 22-07418 | 11907617 | 10/25/2022 13:45 | 10/25/2022 14:15 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 | GEN, NOH, GEN, WOCN, NOH
168 | 22-06515 | 11575216 | 10/26/2022 07:00 | 10/26/2022 16:00 | JOHN DAY-GRIZZLY 1 500KV LINE INCLUDING BAKEOVEN 500KV SERIES CAP GROUP 1, . | NWACI, PDCI, COI, WOJD, BCHT, BCHW, NI, NWACI, PDCI, SIG, WOJD
169 | 22-09427 | 11971369 | 10/26/2022 07:00 | 10/28/2022 16:00 | MCNARY: PCB 4228, BFR & SYNC CHECK RELAYS | NWACI, PDCI, WOM, COI
170 | 22-10220 | 11936730 | 10/26/2022 08:00 | 10/27/2022 15:00 | NASELLE: PCB'S B-1716 & B-1715 (OPEN ENDS HOLCOMB-NASELLE 115KV LINE AT NASELLE) | PA
171 | 22-06516 | 11575242 | 10/27/2022 07:00 | 10/28/2022 16:00 | JOHN DAY-MARION NO 1 500KV LINE | NWACI, PDCI, SIG, WOCS, WOJD, COI
172 | 22-11001 | 12071120 | 10/27/2022 08:00 | 10/27/2022 11:00 | BIG EDDY: PCB 4202 | PDCI, WOCS, WOJD, BGEDY
173 | 22-08226 | 11907792 | 10/27/2022 08:00 | 10/27/2022 15:00 | JOHN DAY: 500KV CAP GROUP 1, INCLUDING PCB 4153 | COI, NWACI, PDCI, WOJD, NWACI, PDCI, WOJD, COI
174 | 22-11002 | 12071119 | 10/27/2022 12:00 | 10/27/2022 15:00 | BIG EDDY: PCB 4205 | PDCI, WOCS, WOJD, BGEDY
175 | 22-01192 | 9965626 | 10/28/2022 06:00 | 10/28/2022 18:00 | BENTON: 115KV MAIN BUS INCLUDING BENTON-RINGOLD SECTION OF BENTON-SCOOTENEY #1 115KV LINE INCLUDING PCB B-530 | GEN, TCLA, TCLA, TCLA, GEN, LOAD, TCLA, TCLA, TCLA, TCLA, GEN, GEN, TCLA, TCLA, GEN
176 | 22-06517 | 11575255 | 10/29/2022 07:00 | 11/01/2022 16:00 | JOHN DAY-BIG EDDY NO 2 500KV LINE | NWACI, PDCI, SIG, WOJD
177 | 22-05654 | 11497947 | 10/30/2022 22:00 | 11/18/2022 17:00 | BELL: A-382 TERMINAL OF THE GRAND COULEE-BELL NO 5 230KV LINE (UNGROUNDED) | MT-NW, WOH, WOH, COI, NOH, NWACI, PDCI, WOCN, NOH, WOH, COI, NWACI, PDCI
178 | 22-01791 | 11563094 | 10/31/2022 07:00 | 11/08/2022 15:30 | FRANKLIN: PCB B-1522 INCLUDING THE GLADE-FRANKLIN SECTION OF BENTON-FRANKLIN NO 2 115KV LINE AND THE 115KV AUX BUS | TCLA
179 | 22-04979 | 11423286 | 10/31/2022 07:00 | 11/01/2022 16:00 | RAVER: PCB 4849 | NOEL, RP, SOC
180 | 22-04868 | 11368007 | 10/31/2022 07:00 | 11/03/2022 15:00 | SHELTON-T3BA'DAS SECTION OF SHELTON-FAIRMOUNT NO 2 115KV LINE
181 | 22-00919 | 11242019 | 10/31/2022 07:30 | 11/04/2022 07:30 | LOWER MONUMENTAL-HANFORD NO 1 500KV LINE INCLUDING HANFORD: PCB'S 4098 & 4095 | NOH, NWACI, PDCI, SIG, WOLM, COI, GEN, NWACI, PDCI, WOLM, COI, NOH, WOM, WOS, GEN, NWACI, PDCI, WOLM, COI, NOH, WOM, WOS
182 | 22-04696 | 11356174 | 10/31/2022 08:00 | 11/02/2022 15:00 | ASHE: PCB 5463 | NOH, NWACI, PDCI, COI, FCRPS
183 | 22-02093 | 10884869 | 10/31/2022 08:00 | 11/03/2022 15:00 | ECHO LAKE: PCB 5075 BFR | BCHT, BCHW, NOEL, SOC, WOCN, NI
184 | 22-11660 | 12100687 | 10/31/2022 08:00 | 11/03/2022 15:00 | GRAND COULEE: 6486 TERMINAL OF THE ROCKY FORD-GRAND COULEE NO 1 230KV LINE | NOH, COI, NWACI, PDCI, OKLA
185 | 22-04681 | 11341843 | 10/31/2022 08:00 | 11/10/2022 15:00 | MALIN: PCB 4184 INCLUDING 500KV CAP GROUP 4 | COI, NWACI, PDCI
186 | 22-11657 | 12100634 | 10/31/2022 08:00 | 11/03/2022 15:00 | MIDWAY: A-996 TERMINAL OF THE MIDWAY-ROCKY FORD NO 1 230KV LINE | WOM, NOH
187 | 22-08018 | 11704445 | 10/31/2022 08:30 | 11/04/2022 15:30 | LOWER MONUMENTAL PH-LOWER MONUMENTAL 1 500KV LINE INCLUDING: LOMO PCB 4316 | WOLM, GEN