## Request List
Row | Request# | CAISO# | Start | End | Main Element Impacted | Path Affected
1 | 23-00098 | 11351684 | 10/25/2023 08:00 | 10/25/2023 16:00 | JENKINS-EAST ELLENSBURG SECTION OF COLUMBIA-ELLENSBURG NO 1 115KV LINE INCLUDING SMITHSON TAP, JENKINS-SMITHSON SECTION OF COLUMBIA-ELLENSBURG NO 1 115KV LINE, SMITHSON-EAST ELLENSBURG SECTION OF COLUMBIA-ELLENSBURG NO 1 115KV LINE, SMITHSON TAP TO COLUMBIA-ELLENSBURG NO 1 115KV LINE | TCLA, TCLA, TCLA
2 | 23-00096 | 11351686 | 10/18/2023 08:00 | 10/18/2023 16:00 | SMITHSON-ELLENSBURG SECTION OF COLUMBIA-ELLENSBURG NO 1 115KV LINE, INCLUDING EAST ELLENSBURG TAP TO B-665 DISCONNECT, SMITHSON-EAST ELLENSBURG SECTION OF COLUMBIA-ELLENSBURG NO 1 115KV LINE, EAST ELLENSBURG TAP TO COLUMBIA-ELLENSBURG NO 1 115KV LINE, EAST ELLENSBURG-ELLENSBURG SECTION OF COLUMBIA-ELLENSBURG NO 1 115KV LINE | TCLA, TCLA, TCLA
3 | 23-00097 | 11351691 | 10/19/2023 08:00 | 10/24/2023 16:00 | EAST ELLENSBURG-ELLENSBURG SECTION OF COLUMBIA-ELLENSBURG NO 1 115KV LINE | TCLA
4 | 23-00099 | 11351677 | 10/26/2023 08:00 | 10/31/2023 16:00 | JENKINS-SMITHSON SECTION OF COLUMBIA-ELLENSBURG NO 1 115KV LINE | TCLA
5 | 23-00100 | 11351674 | 10/10/2023 08:00 | 10/17/2023 16:00 | SMITHSON-EAST ELLENSBURG SECTION OF COLUMBIA-ELLENSBURG NO 1 115KV LINE | TCLA
6 | 23-00087 | 11350604 | 09/22/2023 12:00 | 10/13/2023 16:00 | BENTON-GLADE SECTION OF BENTON-FRANKLIN NO 2 115KV LINE | TCLA
7 | 23-00094 | 11351304 | 09/13/2023 08:00 | 10/06/2023 16:00 | CLYMER-MOXEE SECTION OF ELLENSBURG-MOXEE NO 1 115KV LINE | TCLA
8 | 23-00049 | 10388102 | 10/31/2023 08:00 | 11/03/2023 18:30 | CANBY TAP TO MALIN-HILLTOP NO 1 230KV LINE (UNGROUNDED) | RATS, RATS, RATS, LOAD
9 | 23-00004 | 10955446 | 10/30/2023 03:00 | 11/30/2023 17:00 | -USBR- GRAND COULEE: PCB 5382 | NOH, WOCN, COI, NWACI, PDCI
10 | 23-00084 | 11345939 | 10/16/2023 07:00 | 11/09/2023 16:00 | HANFORD-WAUTOMA NO 2 500KV LINE | NOH, NWACI, PDCI, SIG, COI, NOH, NWACI, PDCI, COI, WOM, WOS, NOH, NWACI, PDCI, COI, WOM, WOS, WOCN, NOH, WOCN
11 | 23-00047 | 10030256 | 10/09/2023 08:00 | 10/13/2023 18:30 | LAPINE-CHILOQUIN NO 1 230KV LINE | COI, NWACI, PDCI, LOAD, COI, PDCI, NWACI
12 | 23-00048 | 10030258 | 10/16/2023 08:00 | 10/20/2023 18:30 | LAPINE-CHILOQUIN NO 1 230KV LINE | COI, NWACI, PDCI, LOAD, COI, PDCI, NWACI
13 | 23-00116 | 11313768 | 10/23/2023 07:00 | 10/27/2023 16:00 | IPC - MIDPOINT 544B, MIDPOINT 544D, MIDPOINT - HEMINGWAY 500 KV line, HEMINGWAY 539C, HEMINGWAY 538C | ID-NW, COI
14 | 23-00118 | 11180842 | 10/16/2023 08:00 | 10/20/2023 18:30 | BPA LaPine-Chiloquin 230 kV line | LOAD, COI, NWACI, PDCI
15 | 23-00399 | 12118076 | 08/31/2023 08:00 | 11/23/2023 18:00 | SCL Broad St - SCL Union St Tap 115kV Cable, SCL Union St - SCL Union St Tap 115kV Cable, SCL Massachusetts St - SCL Union St Tap 115kV Cable, SCL Broad St Bank 66B, SCL Broad St Bank 66A, SCL Broad St BKR 120-55, SCL Broad St BKR 120-58, SCL Union St BKR 120-65 | NOEL, SOC