## Request List
Row# | Request# | CAISO# | Start | End | Main Element Impacted | Elements Involved | Path Affected
1 | 21-01711 | 9741845 | 02/03/2021 09:00 | 02/28/2025 17:00 | -USBR- GRAND COULEE 287/230KV TRANSFORMER KX-17-A (OLYMPIA-GRAND COULEE NO 1 287KV LINE OPERATING AT 230KV) | -USBR- GRAND COULEE 287/230KV TRANSFORMER KX-17-A (OLYMPIA-GRAND COULEE NO 1 287KV LINE OPERATING AT 230KV), OLYMPIA: 287/230KV TRANSFORMER 3, GRAND COULEE: 287/230KV TRANSFORMER 1 | NOEL, PA, RP, SOC, WOCN, IROL, NOH, OKLA
2 | 22-06836 | 11597875 | 04/06/2022 12:25 | 05/31/2023 15:00 | OSTRANDER-TROUTDALE 1 500KV LINE INCLUDING TROUTDALE: 500/230KV TRANSFORMER BANK 8 | OSTRANDER-TROUTDALE NO 1 500KV LINE, OSTRANDER-TROUTDALE 1 500KV LINE INCLUDING TROUTDALE: 500/230KV TRANSFORMER BANK 8, TROUTDALE: 500/230KV TRANSFORMER 8 | SIG, SOA, WOCS, SIG, WOCS, SOA
3 | 22-06835 | 12752148 | 04/06/2022 13:00 | 05/31/2023 15:01 | TROUTDALE: A-1416 TERMINAL | TROUTDALE: PCB A-1416, TROUTDALE: A-1416 TERMINAL | WOCS
4 | 22-07667 | 11668432 | 04/21/2022 13:00 | 05/31/2023 15:00 | TROUTDALE: 500/230KV TRANSFORMER 8 | TROUTDALE: 500/230KV TRANSFORMER 8 | SIG, WOCS, SOA
5 | 22-13128 | 12651062 | 08/17/2022 08:00 | 05/31/2023 23:59 | MAPLE VALLEY: 500/230KV TRANSFORMER 2, (DERATED) | MAPLE VALLEY: 500/230KV TRANSFORMER 2, (DERATED) | IROL, NOEL, SIG, SOC, WOCN
6 | 22-17044 | 12730571 | 11/16/2022 14:00 | 11/16/2023 19:00 | (EWEB) CURRIN: PCB'S 4590 & 4584 | (EWEB) CURRIN: PCB'S 4590 & 4584, CURRIN: PCB 4590, CURRIN: PCB 4584, CURRIN-OAKWAY-WILLAMETTE 115KV LINE | NWACI, PDCI, COI
7 | 23-04603 | 13065715 | 01/31/2023 09:00 | 01/31/2024 15:00 | BUCKLEY: PCB 4967 | BUCKLEY: PCB 4967 | NWACI, WOCS, WOJD, WOM, WOS
8 | 23-01684 | 11460660 | 02/03/2023 15:30 | 10/10/2023 09:00 | PG&E - TABLE MOUNTAIN SERIES CAP 1 (ROUND MOUNTAIN-TABLE MOUNTAIN #1 500KV LINE) | PG&E - TABLE MOUNTAIN SERIES CAP 1 (ROUND MOUNTAIN-TABLE MOUNTAIN #1 500KV LINE) | COI, NWACI
9 | 23-04491 |  | 02/04/2023 07:00 | 04/04/2023 16:00 | -PSE- BANGOR-FOSS CORNER 115KV LINE | -PSE- BANGOR-FOSS CORNER 115KV LINE
10 | 23-03222 | 11461724 | 02/10/2023 18:30 | 10/19/2023 09:00 | PG&E- TABLE MOUNTAIN: ROUND MOUNTAIN 500KV LINE SERIES CAP GROUP 2 | PG&E- TABLE MOUNTAIN: ROUND MOUNTAIN 500KV LINE SERIES CAP GROUP 2 | NWACI, COI
11 | 23-04501 | 13052825 | 02/12/2023 04:00 | 04/09/2023 20:00 | LADWP- VICTORVILLE-RINALDI 1 500KV LINE | LADWP- VICTORVILLE-RINALDI 1 500KV LINE | PDCI
12 | 23-00402 | 12143727 | 03/06/2023 08:00 | 04/06/2023 15:00 | MIDWAY: 115KV EAST MAIN BUS INCLUDING MIDWAY 115KV AUX BUS, PCB B-146 AND MIDWAY-RATTLESNAKE SECTION OF MIDWAY-MOXEE NO 1 115KV LINE | MIDWAY: PCB B-146, MIDWAY: 115KV EAST MAIN BUS INCLUDING MIDWAY 115KV AUX BUS, PCB B-146 AND MIDWAY-RATTLESNAKE SECTION OF MIDWAY-MOXEE NO 1 115KV LINE, MIDWAY: 115KV AUX BUS | TCLA, LOAD
13 | 23-03109 | 13001388 | 03/06/2023 08:00 | 04/12/2023 15:00 | BETTAS ROAD: 230kV EAST BUS INCLUDING PCB A-3046 AND 230KV SPAN FROM DEAD END STRUCTURE TO KITTITAS PUD BB1-1 DISCONNECT | BETTAS ROAD: 230KV EAST BUS, BETTAS ROAD: 230kV EAST BUS INCLUDING PCB A-3046 AND 230KV SPAN FROM DEAD END STRUCTURE TO KITTITAS PUD BB1-1 DISCONNECT, BETTAS ROAD: PCB A-3046 | NOEL, SOC, WOCN
14 | 23-01402 | 12691536 | 03/13/2023 06:00 | 04/27/2023 16:00 | -USBR- HUNGRY HORSE: BUS 1 | HUNGRY HORSE PH: PCB 2182, -USBR- HUNGRY HORSE: BUS 1 , HUNGRY HORSE PH: PCB 2382 | WOH
15 | 23-05354 |  | 03/13/2023 06:00 | 08/18/2023 17:00 | -PACW- PACW KNOTT-PGE NORTHERN SECTION OF THE KNOTT-ST JOHNS 57KV LINE | -PACW- PACW KNOTT-PGE NORTHERN SECTION OF THE KNOTT-ST JOHNS 57KV LINE | SOA
16 | 23-02910 |  | 03/16/2023 16:00 | 04/10/2023 07:30 | 451B: 115KV STRAIN BUS INCLUDING, B-1407 AND B-1409 LINE SECTIONALIZING DISCONNECTS | 451B: 115KV STRAIN BUS INCLUDING, B-1407 AND B-1409 LINE SECTIONALIZING DISCONNECTS
17 | 23-05309 | 13131236 | 03/20/2023 08:00 | 04/07/2023 15:00 | MALIN: 500KV REACTOR 4, INCLUDING LBD 11L4 | MALIN: 500KV REACTOR 4, INCLUDING LBD 11L4 | COI, NWACI
18 | 23-04279 | 13037076 | 03/20/2023 15:30 | 05/12/2023 15:00 | JOHN DAY: PCB 4128, INCLUDING MOD 4127 | JOHN DAY: PCB 4128, INCLUDING MOD 4127 | NWACI, WOJD, WOS
19 | 23-00011 | 11242268 | 03/20/2023 17:30 | 05/11/2023 07:30 | HANFORD: PCB 4095 INCLUDING MODS 4094 & 4096 | HANFORD: PCB 4095 INCLUDING MODS 4094 & 4096, HANFORD: MOD 4094, HANFORD: MOD 4096 | NWACI, PDCI, WOLM, COI, NOH, WOM
20 | 23-00318 | 12495520 | 03/27/2023 06:30 | 04/06/2023 17:00 | THE DALLES PH: 230/13.2KV BANK 8 | THE DALLES PH: 230/13.2KV BANK 8
21 | 22-01168 | 9556188 | 03/27/2023 06:30 | 04/16/2023 23:00 | GRAND COULEE: PCB 2192, PCB 2196 | GRAND COULEE: PCB 2192, PCB 2196, GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 | GEN, NOH, WOCN
22 | 23-00529 | 12236138 | 03/27/2023 08:00 | 04/21/2023 07:30 | HANFORD-WAUTOMA NO 1 500KV LINE | HANFORD-WAUTOMA NO 1 500KV LINE | NOH, SIG
23 | 23-00382 | 12182225 | 03/27/2023 08:00 | 04/06/2023 16:00 | LOWER GRANITE: PCB 4776, BFR | LOWER GRANITE: PCB 4776, LOWER GRANITE: PCB 4776 RELAYS, BFR | MT-NW, WOH, WOLM, GEN
24 | 23-02149 | 12852710 | 03/27/2023 08:00 | 04/06/2023 14:00 | T3BA'DAS-FAIRMOUNT SECTION OF SHELTON-FAIRMOUNT NO 2 115KV LINE | T3BA'DAS-FAIRMOUNT SECTION OF SHELTON-FAIRMOUNT NO 2 115KV LINE | PA
25 | 23-02149 | 12852710 | 03/27/2023 08:00 | 04/06/2023 14:00 | T3BA'DAS-FAIRMOUNT SECTION OF SHELTON-FAIRMOUNT NO 2 115KV LINE | T3BA'DAS-FAIRMOUNT SECTION OF SHELTON-FAIRMOUNT NO 2 115KV LINE | PA
26 | 23-01879 | 12815352 | 03/27/2023 08:00 | 04/07/2023 15:00 | LOWER MONUMENTAL: PCB 4600, INCLUDING 500KV REACTOR 1 | LOWER MONUMENTAL: PCB 4600, LOWER MONUMENTAL: 500KV REACTOR 1, INCLUDING 500KV REACTOR 1 | WOLM
27 | 23-01810 | 12842866 | 03/27/2023 16:35 | 04/13/2023 08:30 | LONGVIEW: PCB A-1386 INCLUDING LONGVIEW-ALLSTON #3 230KV LINE | LONGVIEW: PCB A-1386 INCLUDING LONGVIEW-ALLSTON #3 230KV LINE, LONGVIEW: PCB A-1386, LONGVIEW-ALLSTON NO 3 230KV LINE, ALLSTON: PCB A-1357 | SOA
28 | 23-00150 | 11706397 | 03/28/2023 07:00 | 04/03/2023 17:00 | GRAND COULEE-SCHULTZ NO 1 500KV LINE | COLUMBIA: GRAND COULEE-SCHULTZ 1 500KV LINE SERIES CAP GROUP 1, GRAND COULEE-SCHULTZ NO 1 500KV LINE, SCHULTZ: PCB 5154, SCHULTZ: PCB 5157, GRAND COULEE: PCB 2196, GRAND COULEE: PCB 9092, COLUMBIA: PCB 4694 | IROL, NOEL, NOH, SOC, WOCN, GEN, SIG, FCRPS
29 | 23-00153 | 11706405 | 03/28/2023 07:00 | 04/03/2023 17:00 | GRAND COULEE-SCHULTZ NO 2 500KV LINE | COLUMBIA: GRAND COULEE-SCHULTZ 2 500KV LINE SERIES CAP GROUP 2, GRAND COULEE-SCHULTZ NO 2 500KV LINE, SCHULTZ: PCB 5148, SCHULTZ: PCB 5151, GRAND COULEE: PCB 9192, GRAND COULEE: PCB 2296 | IROL, NOEL, NOH, SOC, WOCN, GEN, FCRPS, SIG
30 | 23-00368 | 12107228 | 03/31/2023 22:00 | 04/01/2023 07:00 | GRANDVIEW-SNIPES SECTION OF THE GRANDVIEW-REDMOUNTAIN NO 1 115KV LINE INCLUDING THE PROSSER TAP | PROSSER: BENTON CO PUD 115KV FEEDER 1, GRANDVIEW-SNIPES SECTION OF THE GRANDVIEW-REDMOUNTAIN NO 1 115KV LINE INCLUDING THE PROSSER TAP, PROSSER: BENTON CO PUD 115KV FEEDER 2, PROSSER: BENTON REA 12.5KV FEEDER 1 BY BENTON CO PUD, RIVERFRONT: BENTON CO PUD 115KV FEEDER 1, GRANDVIEW-PROSSER SECTION OF GRANDVIEW-RED MOUNTAIN NO 1 115KV LINE, PROSSER-SNIPES SECTION OF GRANDVIEW-RED MOUNTAIN NO 1 115KV LINE | GEN, TCLA, LOAD, NWACI
31 | 23-03591 | 12975483 | 04/01/2023 08:00 | 04/20/2023 18:00 | -SCL-, MASSACHUSETTS ST: 230/115KV TRANSFORMER 17 | SCL Massachusetts St BKR 13-BK17, -SCL-, MASSACHUSETTS ST: 230/115KV TRANSFORMER 17 | NOEL, SOC, LOAD
32 | 23-00313 | 12118700 | 04/03/2023 05:00 | 04/21/2023 17:00 | CHIEF JOSEPH: A-602 TERMINAL OF CHIEF JOSEPH PH-CHIEF JOSEPH 4 230KV LINE | CHIEF JOSEPH PH-CHIEF JOSEPH NO 4 230KV LINE, CHIEF JOSEPH: A-602 TERMINAL OF CHIEF JOSEPH PH-CHIEF JOSEPH 4 230KV LINE | GEN, NOH, FCRPS
33 | 23-00321 | 12495533 | 04/03/2023 06:30 | 04/13/2023 17:00 | THE DALLES PH: 230/13.2KV BANK 5 | THE DALLES PH: 230/13.2KV BANK 5
34 | 23-00322 | 12011686 | 04/03/2023 06:30 | 04/03/2023 07:00 | BIG EDDY: PCB A-824 OF THE DALLES PH-BIG EDDY NO 4 230KV LINE | THE DALLES PH-BIG EDDY NO 4 230KV LINE, BIG EDDY: PCB A-824 OF THE DALLES PH-BIG EDDY NO 4 230KV LINE | GEN, FCRPS
35 | 23-01681 | 12735694 | 04/03/2023 06:30 | 04/18/2023 17:00 | GRAND COULEE: PCB 5286 | GRAND COULEE: PCB 5286 | NOH, WOCN, COI, NWACI, PDCI
36 | 23-03867 | 13037519 | 04/03/2023 07:00 | 04/14/2023 16:00 | LANE: WILLOW CREEK-LANE #2 115KV LINE INCLUDING PCB B-1621 AND THE 115KV AUX BUS | LANE: EWEB (EUGENE OR) 115KV FEEDER 2, LANE: WILLOW CREEK-LANE #2 115KV LINE INCLUDING PCB B-1621 AND THE 115KV AUX BUS, WILLOW CREEK-LANE 115KV LINE, LANE: PCB B-1621, LANE: 115KV AUX BUS | EWEB
37 | 23-04595 | 13065750 | 04/03/2023 07:00 | 05/01/2023 09:00 | LOOKOUT POINT: B-566 TERMINAL OF THE LOOKOUT POINT PH-LOOKOUT POINT NO 1 115KV LINE | LOOKOUT POINT: B-566 TERMINAL OF THE LOOKOUT POINT PH-LOOKOUT POINT NO 1 115KV LINE, LOOKOUT POINT PH-LOOKOUT POINT NO 1 115KV LINE, LOOKOUT POINT: PCB B-566 | GEN, EWEB
38 | 23-01817 | 12825692 | 04/03/2023 07:00 | 04/03/2023 09:00 | COLUMBIA: GRAND COULEE-SCHULTZ 2 500KV LINE SERIES CAP GROUP 2 INCLUDING PCB 4693 | COLUMBIA: GRAND COULEE-SCHULTZ 2 500KV LINE SERIES CAP GROUP 2 INCLUDING PCB 4693, COLUMBIA: GRAND COULEE-SCHULTZ 2 500KV LINE SERIES CAP GROUP 2, COLUMBIA: PCB 4693 | IROL, NOEL, NOH, NWACI, PDCI, SOC, WOCN, COI
39 | 23-02699 | 12888769 | 04/03/2023 07:00 | 04/21/2023 11:00 | BROADVIEW-GARRISON NO 2 500KV LINE, INCLUDING GARRISON PCB'S 4409, 4412 | BROADVIEW-GARRISON NO 2 500KV LINE, GARRISON: 500KV REACTOR 2, GARRISON: BROADVIEW 2 500KV LINE SERIES CAP GROUP 2, INCLUDING GARRISON PCB'S 4409, 4412, GARRISON: PCB 4409, GARRISON: PCB 4412 | MT-NW, GEN
40 | 23-02959 | 12939338 | 04/03/2023 07:00 | 04/03/2023 11:00 | CONKELLEY: 230KV CAP GROUP 1 SECTION 3 | CONKELLEY: 230KV CAP GROUP 1 SECTION 3, CONKELLEY: LBD A-1573 | MT-NW, FLAT
41 | 23-02975 | 12971269 | 04/03/2023 07:00 | 04/03/2023 16:00 | SATSOP: PCB A-625 | SATSOP: PCB A-625 | GEN, LOAD, PA
42 | 23-04161 | 13027814 | 04/03/2023 07:00 | 04/05/2023 16:00 | OLYMPIA: 230/115KV TRANSFORMER 1 INCLUDING PCB'S A-218 AND B-682 | OLYMPIA: 230/115KV TRANSFORMER 1, OLYMPIA: 230/115KV TRANSFORMER 1 INCLUDING PCB'S A-218 AND B-682, OLYMPIA: PCB A-218, OLYMPIA: PCB B-682 | NOEL, PA, RP, WOCN, SOC
43 | 22-12274 | 12192488 | 04/03/2023 08:00 | 04/28/2023 16:00 | GRIZZLY: PCB 5040 BFR | GRIZZLY: PCB 5040, GRIZZLY: PCB 5040 BFR | NWACI, WOJD, COI, GRZN
44 | 23-02431 | 12975186 | 04/03/2023 08:00 | 04/21/2023 15:00 | PROSSER-SNIPES SECTION OF GRANDVIEW-RED MOUNTAIN NO 1 115KV LINE INCLUDING B-696 AND B-697 DISCONNECTS | PROSSER-SNIPES SECTION OF GRANDVIEW-RED MOUNTAIN NO 1 115KV LINE, PROSSER-SNIPES SECTION OF GRANDVIEW-RED MOUNTAIN NO 1 115KV LINE INCLUDING B-696 AND B-697 DISCONNECTS | GEN, TCLA, LOAD
45 | 23-04446 | 13130008 | 04/03/2023 08:00 | 04/03/2023 16:00 | CONKELLEY: 230KV CAP GROUP 2 SECTIONS 1 AND 2 INCLUDING LBDS A-1575 AND A-1576 | CONKELLEY: LBD A-1576, CONKELLEY: 230KV CAP GROUP 2 SECTIONS 1 AND 2 INCLUDING LBDS A-1575 AND A-1576, CONKELLEY: LBD A-1575, CONKELLEY: 230KV CAP GROUP 2 SECTION 1, CONKELLEY: 230KV CAP GROUP 2 SECTION 2 | MT-NW, FLAT
46 | 23-01700 | 12735585 | 04/03/2023 08:00 | 04/03/2023 15:00 | BOARDMAN: 115KV MAIN BUS | BOARDMAN: 115KV MAIN BUS, BOARDMAN: PCB B-1102, BOARDMAN: PCB B-265, BOARDMAN: PCB B-313, BOARDMAN: PCB B-279, BOARDMAN: PCB B-281, BOARDMAN: PCB B-283, BOARDMAN: UMATILLA E COOP 115KV FEEDER 2 TO PORT OF MORROW, BOARDMAN: UMATILLA E COOP 115KV FEEDER 1, BOARDMAN: 115/69KV TRANSFORMER 2, BOARDMAN-IONE NO 1 69KV LINE, BOARDMAN: CBEC (69KV IONE LINE) JEM METERS, BOARDMAN: UEC (115KV) JEM METERS, BOARDMAN: RAS HNBT-A GEN DROP HORN BUTTE WIND CKT 7B45, BOARDMAN: RAS HNBT-B GEN DROP HORN BUTTE WIND CKT 7B44, BOARDMAN-ALKALI NO 1 115KV LINE | GEN, LOAD, NWACI, WOM
47 | 23-05001 | 13095451 | 04/03/2023 08:00 | 04/27/2023 08:00 | SCL Bothell Bank 62, SCL Bothell BKR 120-BK62 | SCL Bothell Bank 62, SCL Bothell BKR 120-BK62
48 | 23-01435 | 12672724 | 04/03/2023 08:00 | 04/06/2023 16:00 | SANTIAM-TOLEDO NO 1 230KV LINE INCLUDING WREN TAP, WREN SUB, AND THE CPI 69KV FEEDER #1 | WREN: 230/69KV TRANSFORMER 2, SANTIAM-TOLEDO NO 1 230KV LINE INCLUDING WREN TAP, WREN SUB, AND THE CPI 69KV FEEDER #1, WREN: 69KV PCB L-856, WREN: LBD A-1604, WREN: CONSUMERS POWER 69KV FEEDER 1, TOLEDO: PCB A-1472, WREN-TOLEDO SECTION OF SANTIAM-TOLEDO NO 1 230KV LINE, WREN: A-295 LSD, WREN: LBD A-296, SANTIAM-WREN SECTION OF SANTIAM-TOLEDO NO 1 230KV LINE, SANTIAM: PCB A-524 | SWORE, LOAD
49 | 23-05313 | 13146359 | 04/03/2023 08:00 | 04/03/2023 16:00 | BCH - KELLY LAKE-CHEEKYE 500KV LINE (5L42) | BCH - KELLY LAKE-CHEEKYE 500KV LINE (5L42)
50 | 23-00072 | 12595264 | 04/03/2023 08:00 | 04/20/2023 12:00 | HATWAI: 500/230KV TRANSFORMER 1 | HATWAI: 500/230KV TRANSFORMER 1, HATWAI: PCB 4700, HATWAI: PCB 4710 | ID-NW, MT-NW, NOH, WOH, WOLM
51 | 23-04038 | 13034385 | 04/03/2023 08:00 | 04/06/2023 15:00 | ASHE: 230KV CAP GROUP 1 RELAYS INCLUDING PCB A-894 BFR | ASHE: 230KV CAP GROUP 1 RELAYS INCLUDING PCB A-894 BFR, ASHE: PCB A-894, ASHE: 230KV CAP GROUP 1 | NOH, TCLA
52 | 23-04062 | 13012444 | 04/03/2023 08:00 | 04/03/2023 09:00 | BONNERS FERRY-SMITH CREEK NO 1 115KV LINE INCLUDING THE MOYIE SPRINGS-BONNERS FERRY SECTION OF THE LIBBY-BONNERS FERRY NO 1 115KV LINE | BONNERS FERRY-SMITH CREEK NO 1 115KV LINE INCLUDING THE MOYIE SPRINGS-BONNERS FERRY SECTION OF THE LIBBY-BONNERS FERRY NO 1 115KV LINE, MOYIE: BONNERS FERRY ID 115KV FEEDER 1, NORTH BENCH: BONNERS FERRY ID 13.8KV FEEDER 1, NORTH BENCH: NORTHERN LIGHTS 13.8KV FEEDER 1, YAAK-MOYIE SPRINGS SECTION OF LIBBY-BONNERS FERRY NO 1 115KV LINE, MOYIE SPRINGS TAP TO LIBBY-BONNERS FERRY NO 1 115KV LINE, MOYIE: 115/13.8KV TRANSFORMER 1, NORTHERN LIGHTS MT. HALL TAP TO THE BONNERS FERRY-SMITH CREEK NO 1 115KV LINE, MOYIE SPRINGS-BONNERS FERRY SECTION OF LIBBY-BONNERS FERRY NO 1 115KV LINE, BONNERS FERRY-SMTH SMITH CREEK NO 1 115KV LINE, BONNERS FERRY: NORTHERN LIGHTS 115KV FEEDER 1 TO SMITH CREEK | LOAD
53 | 23-04643 | 13072241 | 04/03/2023 08:30 | 04/05/2023 15:00 | QUENETT CREEK: PCB A-1917 | QUENETT CREEK: PCB A-1917
54 | 23-03745 | 12976419 | 04/03/2023 08:30 | 04/06/2023 14:30 | SUMMER LAKE: 4953/4954 TERMINALS AND MALIN: 4577/4579 TERMINALS OF SUMMER LAKE-MALIN NO 1 500KV LINE | SUMMER LAKE-MALIN NO 1 500KV LINE, SUMMER LAKE: 4953/4954 TERMINALS AND MALIN: 4577/4579 TERMINALS OF SUMMER LAKE-MALIN NO 1 500KV LINE, SUMMER LAKE: PCB 4957, SUMMER LAKE: PCB 4959, MALIN: PCB 4576, MALIN: PCB 4591, SYCAN: SUMMER LAKE-MALIN 1 500KV LINE SERIES CAP GROUP 3 | BCHT, BCHW, NI, NWACI, SIG, COI, ID-NW
55 | 23-00857 | 13160525 | 04/03/2023 08:30 | 04/06/2023 14:30 | CAPTAIN JACK: PCB 4986 | CAPTAIN JACK: PCB 4986 | NWACI, COI
56 | 23-03785 | 13001046 | 04/03/2023 09:00 | 04/14/2023 15:00 | MOYIE SPRINGS-BONNERS FERRY SECTION OF LIBBY-BONNERS FERRY NO 1 115KV LINE, INCLUDING THE BONNERS FERRY: 115KV BUS AND PCB'S B-1278 AND B-1276 | MOYIE SPRINGS-BONNERS FERRY SECTION OF LIBBY-BONNERS FERRY NO 1 115KV LINE, MOYIE SPRINGS-BONNERS FERRY SECTION OF LIBBY-BONNERS FERRY NO 1 115KV LINE, INCLUDING THE BONNERS FERRY: 115KV BUS AND PCB'S B-1278 AND B-1276, SAMUELS-BONNERS FERRY SECTION OF SAND CREEK-BONNERS FERRY NO 1&2 115KV LINE, BONNERS FERRY: BONNERS FERRY ID 13.8KV FEEDER 1, BONNERS FERRY: NORTHERN LIGHTS 13.8KV FEEDER 1, BONNERS FERRY-SMTH SMITH CREEK NO 1 115KV LINE, BONNERS FERRY: 115KV CAP GROUP 1, BONNERS FERRY: 115KV CAP GROUP 2 SECTION 1, BONNERS FERRY: 115/13.8KV TRANSFORMER 1, BONNERS FERRY: 115/13.8KV TRANSFORMER 2, BONNERS FERRY: 115KV BUS, BONNERS FERRY: PCB B-1278, BONNERS FERRY: PCB B-1276 | LOAD
57 | 23-01821 | 12825699 | 04/03/2023 09:30 | 04/03/2023 11:30 | COLUMBIA: GRAND COULEE-SCHULTZ 1 500KV LINE SERIES CAP GROUP 1 INCLUDING PCB 4694 | COLUMBIA: GRAND COULEE-SCHULTZ 1 500KV LINE SERIES CAP GROUP 1 INCLUDING PCB 4694, COLUMBIA: GRAND COULEE-SCHULTZ 1 500KV LINE SERIES CAP GROUP 1, COLUMBIA: PCB 4694 | IROL, NOEL, NOH, NWACI, PDCI, SOC, WOCN, COI
58 | 23-04350 |  | 04/03/2023 11:00 | 04/06/2023 15:00 | SAMUELS-BONNERS FERRY SECTION OF SAND CREEK-BONNERS FERRY NO 1&2 115KV LINE | SAMUELS-BONNERS FERRY SECTION OF SAND CREEK-BONNERS FERRY NO 1&2 115KV LINE
59 | 23-02960 | 12939351 | 04/03/2023 12:00 | 04/03/2023 15:00 | CONKELLEY: 230KV CAP GROUP 1 SECTION 4 | CONKELLEY: 230KV CAP GROUP 1 SECTION 4, CONKELLEY: LBD A-1574 | MT-NW, FLAT
60 | 22-01225 | 9562507 | 04/04/2023 06:30 | 04/04/2023 15:30 | CARLTON: 115KV MAIN BUS | CARLTON: 115KV MAIN BUS, CARLTON: PCB B-127, CARLTON: PCB B-129, CARLTON: PCB B-131, CARLTON TAP TO FOREST GROVE-MCMINNVILLE NO 1 115KV LINE, CARLTON-WINDISHAR SECTION OF CARLTON-MCMINNVILLE NO 1 115KV LINE | LOAD, SOA
61 | 23-01429 | 12814788 | 04/04/2023 07:00 | 04/04/2023 17:00 | ALLSTON: 500KV NORTH BUS INCLUDING PCB'S 4470, 4500, AND 4687 | ALLSTON: 500KV NORTH BUS INCLUDING PCB'S 4470, 4500, AND 4687, ALLSTON: 500KV NORTH BUS, ALLSTON: PCB 4470, ALLSTON: PCB 4500, ALLSTON: PCB 4687 | PA, SOA
62 | 23-02786 | 13109615 | 04/04/2023 07:00 | 04/04/2023 10:00 | SCHULTZ: ECHO LAKE 1 500KV LINE SERIES CAP GROUP 1, INCLUDING PCB 5142 | SCHULTZ: PCB 5142, SCHULTZ: ECHO LAKE 1 500KV LINE SERIES CAP GROUP 1, INCLUDING PCB 5142 | WOCN, IROL, NOEL, SOC
63 | 23-04326 | 13033951 | 04/04/2023 07:00 | 04/06/2023 16:00 | WAPA - OLINDA-TRACY 500KV LINE | WAPA - OLINDA-TRACY 500KV LINE
64 | 23-02885 | 13114889 | 04/04/2023 08:00 | 04/04/2023 15:00 | FAIRMOUNT: PCB B-1382 | FAIRMOUNT: PCB B-1382, FAIRMOUNT: 115KV CAP GROUP 1 SECTION 1, FAIRMOUNT: 115KV CAP GROUP 1 SECTION 2, FAIRMOUNT: 115KV CAP GROUP 1 SECTION 3, FAIRMOUNT: 115KV CAP GROUP 1 SECTION 4
65 | 23-00528 | 12252175 | 04/04/2023 08:00 | 04/28/2023 15:00 | BOARDMAN: 230/115KV TRANSFORMER 1 | BOARDMAN: 230/115KV TRANSFORMER 1, BOARDMAN-ALKALI NO 1 115KV LINE, BOARDMAN: UMATILLA E COOP 115KV FEEDER 1, BOARDMAN: UMATILLA E COOP 115KV FEEDER 2 TO PORT OF MORROW, BOARDMAN-IONE NO 1 69KV LINE, BOARDMAN: 115/69KV TRANSFORMER 2, BOARDMAN: PCB A-803, BOARDMAN: PCB B-279 | GEN, LOAD, WOM, NWACI
66 | 23-04012 | 13059364 | 04/04/2023 08:00 | 04/04/2023 15:00 | COSMOPOLIS: PCB B-1326 | COSMOPOLIS: PCB B-1326, ABERDEEN TAP-COSMOPOLIS SECTION OF SATSOP PARK-COSMOPOLIS NO 1 115KV LINE | PA, RP
67 | 23-00237 | 12118506 | 04/04/2023 08:00 | 04/04/2023 15:00 | OSTRANDER: PCB 4448 | OSTRANDER: PCB 4448 | WOCS
68 | 23-04574 | 13065441 | 04/04/2023 08:00 | 04/04/2023 17:00 | SICKLER: PCB 4334 | SICKLER: PCB 4334 | BCHT, BCHW, CI, GEN, NOH, WOCN
69 | 23-04444 | 13130046 | 04/04/2023 08:00 | 04/04/2023 16:00 | CONKELLEY: 230KV CAP GROUP 1 SECTION 3 AND 4 INCLUDING LBDS A-1573 AND A-1574 | CONKELLEY: LBD A-1574, CONKELLEY: 230KV CAP GROUP 1 SECTION 3 AND 4 INCLUDING LBDS A-1573 AND A-1574, CONKELLEY: LBD A-1573, CONKELLEY: 230KV CAP GROUP 1 SECTION 3, CONKELLEY: 230KV CAP GROUP 1 SECTION 4 | MT-NW, FLAT
70 | 23-02787 | 12884791 | 04/04/2023 10:00 | 04/04/2023 13:00 | SCHULTZ: RAVER 1 500KV LINE SERIES CAP GROUP 1 | SCHULTZ: RAVER 1 500KV LINE SERIES CAP GROUP 1, SCHULTZ: PCB 5163 | IROL, NOEL, NWACI, PDCI, SOC, WOCN, COI, SIG
71 | 23-00462 | 12289653 | 04/04/2023 22:00 | 05/16/2023 19:00 | GRAND COULEE: 500/230KV CSY TIE BANK, INCLUDING 500KV PCB'S 8692,1996 & 230KV PCB 6582 | GRAND COULEE: PCB 1996, GRAND COULEE: 500/230KV CSY TIE BANK, INCLUDING 500KV PCB'S 8692,1996 & 230KV PCB 6582, GRAND COULEE: PCB 8692, GRAND COULEE: PCB 6582 | GEN, NOH, WOCN, PDCI, SIG, COI, FCRPS, NWACI
72 | 23-00154 | 11756890 | 04/05/2023 07:00 | 04/06/2023 17:00 | GRAND COULEE-BELL NO 6 500KV LINE | GRAND COULEE-BELL NO 6 500KV LINE, GRAND COULEE: PCB 8596, GRAND COULEE: 500KV REACTOR 1, BELL: PCB 5313, BELL: PCB 5316, GRAND COULEE: PCB 1896, GRAND COULEE: PCB 8592 | GEN, MT-NW, SIG, WOH, NOH, WOCN
73 | 23-04447 | 13130055 | 04/05/2023 08:00 | 04/06/2023 15:00 | CONKELLEY: PCB A-1288 | CONKELLEY: PCB A-1288, CONKELLEY: 230KV CAP GROUP 2 SECTION 1, CONKELLEY: 230KV CAP GROUP 2 SECTION 2, CONKELLEY: LBD A-1575, CONKELLEY: LBD A-1576 | MT-NW, FLAT
74 | 23-04166 | 13027823 | 04/05/2023 08:00 | 04/05/2023 16:00 | OLYMPIA: PCB A-216 | OLYMPIA: PCB A-216 | NOEL, PA, RP, SOC, WOCN
75 | 23-04165 | 13027820 | 04/05/2023 08:00 | 04/05/2023 16:00 | OLYMPIA: PCB B-686 | OLYMPIA: PCB B-686 | SOA
76 | 23-04155 |  | 04/05/2023 08:00 | 04/05/2023 15:00 | COLVILLE-KETTLE FALLS SECTION OF COLVILLE-REPUBLIC NO 1 115KV LINE, THIS IS A SAMPLE FORM. NOT REAL. | COLVILLE-KETTLE FALLS SECTION OF COLVILLE-REPUBLIC NO 1 115KV LINE, THIS IS A SAMPLE FORM. NOT REAL.
77 | 23-05314 | 13146368 | 04/05/2023 08:00 | 04/06/2023 16:00 | BCH - KELLY LAKE-CHEEKYE 500KV LINE (5L42) | BCH - KELLY LAKE-CHEEKYE 500KV LINE (5L42)
78 | 23-02886 | 13114894 | 04/05/2023 08:00 | 04/05/2023 15:00 | FAIRMOUNT: PCB B-1384 | FAIRMOUNT: PCB B-1384
79 | 23-02682 | 12875067 | 04/05/2023 08:30 | 04/05/2023 16:00 | TIMBER: TIMBER TAP INCLUDING THE 115/34.5KV XFMR #1, PCB B-1138 AND WEST OREGON ELECTRIC'S 34.5KV FEEDER #1 | TIMBER: 115/34.5KV TRANSFORMER 1, TIMBER: TIMBER TAP INCLUDING THE 115/34.5KV XFMR #1, PCB B-1138 AND WEST OREGON ELECTRIC'S 34.5KV FEEDER #1, TIMBER TAP TO FOREST GROVE-TILLAMOOK NO 1 115KV LINE | SOA
80 | 23-00828 | 12690883 | 04/05/2023 08:30 | 04/05/2023 16:00 | PEARL: PCB 5455 | PEARL: PCB 5455 | SOA
81 | 23-00511 | 12293499 | 04/05/2023 10:00 | 04/05/2023 11:00 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 | GEN, NOH, WOCN
82 | 23-00888 | 12538126 | 04/05/2023 11:00 | 04/05/2023 12:00 | GRAND COULEE: PCB 2092, GRAND COULEE: PCB 2096 | GRAND COULEE: PCB 2092, GRAND COULEE: PCB 2096 | GEN, NOH, WOCN
83 | 23-00514 | 12293531 | 04/05/2023 12:30 | 04/05/2023 13:30 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 | GEN, NOH, WOCN
84 | 23-00515 | 12293558 | 04/05/2023 13:30 | 04/05/2023 14:30 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 | GEN, NOH, WOCN
85 | 23-01137 | 12593779 | 04/06/2023 07:00 | 04/06/2023 15:30 | COVINGTON: PCB A-850 BFR | COVINGTON: PCB A-850 BFR, COVINGTON: PCB A-850 | NOEL, SOC
86 | 23-00373 | 12123844 | 04/06/2023 07:30 | 04/06/2023 15:00 | ALCOA: PCB B-224 | ALCOA: PCB B-224 | SOA, GEN, LOAD
87 | 23-00867 | 13048329 | 04/06/2023 08:00 | 04/06/2023 16:00 | SALEM: PORTLAND GEN ELEC 115KV FEEDER 1 | SALEM: PORTLAND GEN ELEC 115KV FEEDER 1, SALEM: PCB B-62 | SLAL
88 | 23-00320 |  | 04/06/2023 16:30 | 04/06/2023 17:00 | THE DALLES PH-BIG EDDY NO 5 230KV LINE | THE DALLES PH-BIG EDDY NO 5 230KV LINE | GEN, FCRPS
89 | 23-00464 |  | 04/10/2023 03:30 | 04/13/2023 16:00 | DAVIS CREEK TAP OF THE (PACW) MILE HI-ALTURAS 115KV LINE INCLUDING DAVIS CREEK: 115/12.5KV TRANSFORMER 1 | DAVIS CREEK TAP OF THE (PACW) MILE HI-ALTURAS 115KV LINE INCLUDING DAVIS CREEK: 115/12.5KV TRANSFORMER 1, DAVIS CREEK: SURPRISE VALLEY 12.5KV FEEDER 1 BY PACIFICORP (PACW)
90 | 23-05041 |  | 04/10/2023 04:00 | 05/14/2023 20:00 | LADWP- ADELANTO-TOLUCA 1 500KV LINE | LADWP- ADELANTO-TOLUCA 1 500KV LINE | PDCI
91 | 23-01938 | 12852732 | 04/10/2023 07:00 | 04/14/2023 14:00 | SPAR CANYON: 230KV BYPASS BUS INCLUDING SS XFMR, PCB A-887, AND 230KV REACTOR #2 | SPAR CANYON: A-157 BYPASS DISC, SPAR CANYON: 230KV BYPASS BUS INCLUDING SS XFMR, PCB A-887, AND 230KV REACTOR #2, SPAR CANYON: A-137 BYPASS DISC, SPAR CANYON: A-185 BYPASS DISC
92 | 23-00156 | 11694133 | 04/10/2023 07:00 | 04/10/2023 17:00 | OLYMPIA-GRAND COULEE NO 1 287KV LINE | OLYMPIA-GRAND COULEE NO 1 287KV LINE, OLYMPIA: PCB A-206, GRAND COULEE: PCB 6886, GRAND COULEE: 287/230KV TRANSFORMER 1, OLYMPIA: 287/230KV TRANSFORMER 3 | NOEL, NOH, RP, SOC, WOCN, IROL, NOEL, PA, RP, SOC, WOCN, NOH, WOCN, COI, NWACI, PDCI, NOH, OKLA, NOEL, PA, RP, SOC, WOCN, IROL
93 | 23-05293 |  | 04/10/2023 07:00 | 04/13/2023 16:00 | -NWE- RATTLESNAKE: 230/161KV BANK 3 | -NWE- RATTLESNAKE: 230/161KV BANK 3 | MT-NW
94 | 23-02912 | 12922120 | 04/10/2023 07:30 | 04/11/2023 15:00 | WHITE BLUFFS-451-B NO 1 115KV LINE INCUDING 451-B 1407 DISC | WHITE BLUFFS: PCB B-263, WHITE BLUFFS-451-B NO 1 115KV LINE INCUDING 451-B 1407 DISC, DOE 451B: B-1407 LINE SECTIONALIZING DISC, DOE 451B: PCB B-1413, WHITE BLUFFS-451B NO 1 115KV LINE | GEN, TCLA, LOAD
95 | 23-05503 | 13160322 | 04/10/2023 07:30 | 04/10/2023 09:00 | OSTRANDER: 500KV CAP GROUP 3 INCLUDING PCB 5097 | OSTRANDER: 500KV CAP GROUP 3, OSTRANDER: 500KV CAP GROUP 3 INCLUDING PCB 5097, OSTRANDER: PCB 5097 | WOCS
96 | 23-00403 | 12143754 | 04/10/2023 08:00 | 04/21/2023 15:00 | RATTLESNAKE-MOXEE SECTION OF MIDWAY-MOXEE NO 1 115KV LINE | RATTLESNAKE-MOXEE SECTION OF MIDWAY-MOXEE NO 1 115KV LINE | TCLA
97 | 23-00213 | 12690973 | 04/10/2023 08:00 | 04/10/2023 16:00 | GRIZZLY: PCB 4720, INCLUDING 500KV REACTOR 2 | GRIZZLY: PCB 4720, GRIZZLY: 500KV REACTOR 2, INCLUDING 500KV REACTOR 2 | COI, NWACI, PDCI
98 | 23-02143 | 13160646 | 04/10/2023 08:00 | 04/10/2023 09:00 | NORTH BONNEVILLE: 115KV CAP GROUP 1 SECTION 1 INCLUDING PCB B-1960 | NORTH BONNEVILLE: 115KV CAP GROUP 1 SECTION 1 INCLUDING PCB B-1960
99 | 23-01880 | 12815430 | 04/10/2023 08:00 | 04/11/2023 15:00 | LOWER MONUMENTAL: PCB 4290 | LOWER MONUMENTAL: PCB 4290 | WOLM
100 | 23-05261 | 13130566 | 04/10/2023 08:00 | 04/11/2023 15:00 | PORT ORFORD-GEISEL MONUMENT SECTION OF BANDON-ROGUE NO 1 115KV LINE | PORT ORFORD-GEISEL MONUMENT SECTION OF BANDON-ROGUE NO 1 115KV LINE
101 | 23-00678 |  | 04/10/2023 08:00 | 04/10/2023 10:30 | LA GRANDE: 230KV CAP GROUP 1 INCLUDING PCB A-267 | LA GRANDE: 230KV CAP GROUP 1 INCLUDING PCB A-267, LA GRANDE: PCB A-267 | ID-NW, NWACI
102 | 23-00859 | 12454457 | 04/10/2023 08:00 | 04/13/2023 17:00 | BIG EDDY-CHEMAWA NO 1 230KV LINE | BIG EDDY-CHEMAWA NO 1 230KV LINE, BIG EDDY: PCB A-822, CHEMAWA: PCB A-670 | NWACI, PDCI, WOCS, COI, WOJD
103 | 23-05505 | 13160326 | 04/10/2023 09:00 | 04/10/2023 10:30 | OSTRANDER: 500KV CAP GROUP 1 INCLUDING PCB 5135 | OSTRANDER: 500KV CAP GROUP 1, OSTRANDER: 500KV CAP GROUP 1 INCLUDING PCB 5135, OSTRANDER: PCB 5135 | WOCS
104 | 23-00062 | 10922641 | 04/10/2023 09:00 | 04/13/2023 16:00 | MCMINNVILLE: PCB B-666, WALNUT CITY-MCMINNVILLE SECTION OF FOREST GROVE-MCMINNVILLE NO 1 115KV LINE | MCMINNVILLE: PCB B-666, WALNUT CITY-MCMINNVILLE SECTION OF FOREST GROVE-MCMINNVILLE NO 1 115KV LINE
105 | 23-02144 | 12815373 | 04/10/2023 09:00 | 04/10/2023 10:00 | NORTH BONNEVILLE: B-1961 PCB INCLUDING 115KV CAP GROUP 1 SECTION 2 | NORTH BONNEVILLE: B-1961 PCB INCLUDING 115KV CAP GROUP 1 SECTION 2
106 | 23-04185 | 13059293 | 04/10/2023 09:00 | 04/10/2023 12:00 | ABERDEEN: 230/115KV TRANSFORMER 5 | ABERDEEN: 230/115KV TRANSFORMER 5, SATSOP-ABERDEEN NO 3 230KV LINE | PA, LOAD, SI
107 | 23-05507 | 13160363 | 04/10/2023 10:30 | 04/10/2023 12:00 | OSTRANDER: 500KV CAP GROUP 2 INCLUDING PCB 5138 | OSTRANDER: 500KV CAP GROUP 2, OSTRANDER: 500KV CAP GROUP 2 INCLUDING PCB 5138, OSTRANDER: PCB 5138 | WOCS
108 | 23-04121 | 13017005 | 04/10/2023 12:00 | 04/10/2023 14:00 | TROUTDALE: 230KV CAP GROUP 8 SECTIONS 1,2,3 INCLUDING PCB A-293 AND LBD'S A-327, A-326, AND 230KV REACTIVE BUS | TROUTDALE: 230KV CAP GROUP 8 SECTION 1, TROUTDALE: 230KV CAP GROUP 8 SECTIONS 1,2,3 INCLUDING PCB A-293 AND LBD'S A-327, A-326, AND 230KV REACTIVE BUS, TROUTDALE: 230KV CAP GROUP 8 SECTION 2, TROUTDALE: 230KV CAP GROUP 8 SECTION 3, TROUTDALE: PCB A-293, TROUTDALE: LBD A-326, TROUTDALE: LBD A-327 | WOCS
109 | 23-00844 | 12691367 | 04/11/2023 06:30 | 04/11/2023 09:00 | MCNARY; 230KV CAP GROUP #1 SECT 1 INCLUDING PCB A-3024 | MCNARY; 230KV CAP GROUP #1 SECT 1 INCLUDING PCB A-3024, MCNARY: PCB A-3024
110 | 23-00157 | 11756938 | 04/11/2023 07:00 | 04/11/2023 17:00 | SICKLER-SCHULTZ NO 1 500KV LINE | SICKLER-SCHULTZ NO 1 500KV LINE, SICKLER: PCB 4336, SICKLER: PCB 4334, SCHULTZ: PCB 5129, SCHULTZ: PCB 5132 | IROL, NI, NOH, WOCN, CI, GEN, BCHT, BCHW
111 | 23-02700 | 12884666 | 04/11/2023 07:00 | 04/11/2023 15:00 | BELL-COLBERT SECTION OF BELL-ADDY NO 1 115KV LINE INCLUDING THE MEAD TAP | MEAD TAP TO BELL-ADDY NO 1 115KV LINE, BELL-COLBERT SECTION OF BELL-ADDY NO 1 115KV LINE INCLUDING THE MEAD TAP, BELL-MEAD SECTION OF BELL-ADDY NO 1 115KV LINE, MEAD-COLBERT SECTION OF BELL-ADDY NO 1 115KV LINE, BELL: PCB B-346
112 | 23-01351 | 12810257 | 04/11/2023 07:30 | 04/11/2023 16:00 | HANFORD: 500Kv CAP GROUP 1 INCLUDING PCBS 4085, 4005, AND 4003 | HANFORD: 500KV CAP GROUP 1, HANFORD: 500Kv CAP GROUP 1 INCLUDING PCBS 4085, 4005, AND 4003, HANFORD: PCB 4085, HANFORD: PCB 4003, HANFORD: PCB 4005 | COI, NOH, PDCI, WOM, WOS, NWACI
113 | 23-03259 | 12953034 | 04/11/2023 08:00 | 04/11/2023 15:00 | ALCOA: 115KV CAP GROUP 1 | ALCOA: 115KV CAP GROUP 1
114 | 23-01785 | 12814470 | 04/11/2023 08:00 | 04/11/2023 10:00 | ROSS: PCB A-134 INCLUDING LBD'S A-23, A-25, A-27 AND 230KV CAP GROUP 2 SECTIONS 1, 2, AND 3. | ROSS: PCB A-134, ROSS: PCB A-134 INCLUDING LBD'S A-23, A-25, A-27 AND 230KV CAP GROUP 2 SECTIONS 1, 2, AND 3., ROSS: LBD A-23, ROSS: LBD A-25, ROSS: LBD A-27, ROSS: 230KV CAP GROUP 2 SECTION 1, ROSS: 230KV CAP GROUP 2 SECTION 2, ROSS: 230KV CAP GROUP 2 SECTION 3 | SOA
115 | 23-00870 |  | 04/11/2023 08:00 | 04/11/2023 15:00 | CHEMAWA: PCB B-110 | CHEMAWA: PCB B-110
116 | 23-04005 | 13017275 | 04/11/2023 09:00 | 04/12/2023 15:00 | NORTH BONNEVILLE: PCB A-13 | NORTH BONNEVILLE: PCB A-13 | WOCS
117 | 23-04334 |  | 04/11/2023 09:15 | 04/12/2023 16:00 | WAPA - TRACY 500KV SOUTH BUS | WAPA - TRACY 500KV SOUTH BUS
118 | 23-00847 | 12454621 | 04/11/2023 09:30 | 04/11/2023 11:00 | MCNARY: 230KV CAP GROUP #1 SECT 2 INCLUDING PCB A-3025 | MCNARY: 230KV CAP GROUP #1 SECT 2 INCLUDING PCB A-3025, MCNARY: 230KV CAP GROUP 1 SECTION 2 | LOAD
119 | 23-00525 |  | 04/11/2023 12:00 | 04/11/2023 15:30 | OSTRANDER: MOD 4429, OSTRANDER: MOD 4435, OSTRANDER: MOD A-452 | OSTRANDER: MOD 4429, OSTRANDER: MOD 4435, OSTRANDER: MOD A-452
120 | 23-04693 | 13082334 | 04/11/2023 13:00 | 04/13/2023 10:00 | LANE: PCB A-1454 | LANE: PCB A-1454 | EWEB, SCORC
121 | 23-02914 |  | 04/11/2023 15:00 | 04/13/2023 15:00 | CGS BACKUP BANK - 451B SECTION OF, BENTON-451B NO 1 115KV LINE, INCLUDING HEW 451 B-1409 DISC AND 115KV STRAIN BUS TO B-1407 DISC. | CGS BACKUP BANK - 451B SECTION OF, CGS BACKUP BANK-451B SECTION OF BENTON-451B NO 1 115KV LINE, BENTON-451B NO 1 115KV LINE, CGS BACKUP BANK: B-158 LINE DISCONNECT, INCLUDING HEW 451 B-1409 DISC AND 115KV STRAIN BUS TO B-1407 DISC., DOE 451B: PCB B-1424, DOE 451B: B-1409 LINE SECTIONALIZING DISC | TCLA, GEN, LOAD
122 | 23-04314 | 13043754 | 04/12/2023 05:30 | 04/12/2023 18:00 | ALVEY: 230KV NORTH MAIN BUS, INCLUDING PCBS A-660, A-658, A-656, A-654, A-652, AND A-248 | ALVEY: 500/230KV TRANSFORMER 5, ALVEY: 230KV NORTH MAIN BUS, INCLUDING PCBS A-660, A-658, A-656, A-654, A-652, AND A-248, ALVEY: 230/115KV TRANSFORMER 4, ALVEY-DIXONVILLE NO 1 230KV LINE, ALVEY: PCB A-660, ALVEY: PCB A-658, ALVEY: PCB A-656, ALVEY: PCB A-654, ALVEY: PCB A-652, ALVEY: PCB A-248, ALVEY: PCB A-332 | NWACI, COI, SCORC, SWORE, PDCI
123 | 23-01941 | 12852910 | 04/12/2023 07:00 | 04/14/2023 14:00 | SPAR CANYON: LOST RIVER-SPAR CANYON #1 230KV LINE INCLUDING SPAR CANYON: 230KV MAIN BUS | SPAR CANYON: 230KV MAIN BUS, SPAR CANYON: LOST RIVER-SPAR CANYON #1 230KV LINE INCLUDING SPAR CANYON: 230KV MAIN BUS, LOST RIVER-SPAR CANYON NO 1 230KV LINE, SPAR CANYON: SALMON RIVER COOP 230KV FEEDER 1, SPAR CANYON-ROUND VALLEY NO 1 230KV LINE, ROUND VALLEY: SALMON RIVER COOP 69KV FEEDER 1, ROUND VALLEY: 230/69KV TRANSFORMER 1, LOST RIVER: PCB A-1403 | GEN, LOAD
124 | 23-00850 |  | 04/12/2023 07:00 | 04/12/2023 08:00 | IONE: 69KV CAP GROUP 1 INCLUDING LBD L-913 | IONE: 69KV CAP GROUP 1 INCLUDING LBD L-913
125 | 23-01856 | 12815191 | 04/12/2023 08:00 | 04/13/2023 15:00 | MIDWAY: 230/115KV TRANSFORMER 3 INCLUDING PCB'S B-154 AND L-1034 AND THE 115KV AUX BUS | MIDWAY: 230/13.8KV BOOSTER TRANSFORMER 3, MIDWAY: 230/115KV TRANSFORMER 3 INCLUDING PCB'S B-154 AND L-1034 AND THE 115KV AUX BUS, MIDWAY: PCB B-154, MIDWAY: PCB A-110, MIDWAY: 13.8KV L-1034 STATION SERVICE BUS DISC, MIDWAY: 230/115KV TRANSFORMER 3, MIDWAY: 115KV AUX BUS, MIDWAY: 13.8KV PCB L-1034 | WOM, TCLA
126 | 23-00871 | 12538697 | 04/12/2023 08:00 | 04/12/2023 15:00 | CHEMAWA: PCB B-112 | CHEMAWA: PCB B-112
127 | 23-03170 | 13071142 | 04/12/2023 08:00 | 04/13/2023 15:00 | NASELLE: PCB B-1715 | NASELLE: PCB B-1715
128 | 23-01881 | 12815436 | 04/12/2023 08:00 | 04/13/2023 15:00 | LOWER MONUMENTAL: PCB 4624 | LOWER MONUMENTAL: PCB 4624 | WOLM
129 | 23-00082 | 12691383 | 04/12/2023 08:00 | 04/15/2023 19:00 | REDMOND-PILOT BUTTE PACW NO 1 230KV LINE | REDMOND-PILOT BUTTE PACW NO 1 230KV LINE | LOAD, COR
130 | 23-01128 | 12559952 | 04/12/2023 11:00 | 04/12/2023 12:00 | MORROW FLAT: 115KV CAP GROUP 1 INCLUDING PCB B-2251 | MORROW FLAT: 115KV CAP GRP 1, MORROW FLAT: 115KV CAP GROUP 1 INCLUDING PCB B-2251, MORROW FLAT: PCB B-2251 | WOM
131 | 23-03864 | 13005625 | 04/12/2023 15:00 | 05/02/2023 15:00 | BETTAS ROAD: 230KV EAST BUS INCLUDING PCB'S A-3046 & A-3043, THE COLUMBIA-BETTAS ROAD NO 1 230KV LINE AND THE KITTITAS PUD BETTAS ROAD 230KV LINE TO THE BB1-1 DISCONNECT | BETTAS ROAD: 230KV EAST BUS, BETTAS ROAD: 230KV EAST BUS INCLUDING PCB'S A-3046 & A-3043, THE COLUMBIA-BETTAS ROAD NO 1 230KV LINE AND THE KITTITAS PUD BETTAS ROAD 230KV LINE TO THE BB1-1 DISCONNECT, BETTAS ROAD: PCB A-3046, BETTAS ROAD-COLUMBIA NO 1 230KV LINE, BETTAS ROAD: PCB A-3043 | NOEL, CI, NOH, SOC, WOCN, IROL
132 | 23-02117 | 12814588 | 04/13/2023 06:00 | 04/13/2023 16:00 | KELLER TAP: B-700 AND B-684 TERMINALS OF THE GRAND COULEE - KELLER B700 SECTION OF THE GRAND COULEE-OKANOGAN #2 115KV LINE | GRAND COULEE-KELLER SECTION OF GRAND COULEE-OKANOGAN NO 2 115KV LINE, KELLER TAP: B-700 AND B-684 TERMINALS OF THE GRAND COULEE - KELLER B700 SECTION OF THE GRAND COULEE-OKANOGAN #2 115KV LINE , KELLER TAP TO GRAND COULEE-OKANOGAN NO 2 115KV LINE, GRAND COULEE: PCB 1472, GRAND COULEE: 115KV AUX BUS SECTION 1, KELLER: FERRY CO PUD 34.5KV FEEDER 1, KELLER: 115/34.5KV TRANSFORMER 1 | LOAD
133 | 23-01129 | 12691084 | 04/13/2023 08:00 | 04/13/2023 09:30 | SLATT: 500KV CAP GROUP 1 INCLUDING PCB 5330 | SLATT: 500KV CAP GROUP 1 INCLUDING PCB 5330, SLATT: 500KV CAP GROUP 1, SLATT: PCB 5330 | COI, PDCI, WOS, NWACI, WOJD
134 | 23-00993 | 12690947 | 04/13/2023 08:00 | 04/13/2023 12:00 | JOHN DAY: PCB 4140 | JOHN DAY: PCB 4140 | NWACI, PDCI, WOJD, COI
135 | 23-05347 | 13160220 | 04/13/2023 08:00 | 04/13/2023 14:00 | KEELER: PCB A-862 | KEELER: PCB A-862 | SOA
136 | 23-04863 | 13094630 | 04/13/2023 08:00 | 04/13/2023 15:00 | MAPLE VALLEY: PCB A-1108 | MAPLE VALLEY: PCB A-1108 | NOEL, SOC
137 | 23-00872 | 12538714 | 04/13/2023 08:00 | 04/13/2023 15:00 | CHEMAWA: PCB B-114 | CHEMAWA: PCB B-114
138 | 23-01841 | 12846447 | 04/13/2023 08:35 | 04/13/2023 16:30 | LONGVIEW: 230KV NORTH MAIN BUS INCLUDING PCB A-1386 | LONGVIEW: 230KV NORTH MAIN BUS INCLUDING PCB A-1386, LONGVIEW: PCB A-1374, LONGVIEW: PCB A-1375, LONGVIEW: PCB A-1378, LONGVIEW: PCB A-1380, LONGVIEW: PCB A-1386, LONGVIEW: PCB A-1058 (230KV MAIN BUS SECTIONALIZING), LONGVIEW: 230KV NORTH MAIN BUS, LEXINGTON-LONGVIEW NO 2 230KV LINE, ALLSTON: PCB A-1357 | SOA
139 | 23-01368 | 12690777 | 04/13/2023 09:00 | 04/13/2023 10:00 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 | GEN, NOH, WOCN
140 | 23-04335 |  | 04/13/2023 09:15 | 04/14/2023 16:00 | WAPA - TRACY 500KV NORTH BUS | WAPA - TRACY 500KV NORTH BUS | COI
141 | 23-01130 | 12691099 | 04/13/2023 09:30 | 04/13/2023 11:00 | SLATT: 230KV CAP GROUP 2 SECTION 1 INCLUDING PCB A-1796 | SLATT: 230KV CAP GROUP 2 SECTION 1 INCLUDING PCB A-1796, SLATT: 230KV CAP GROUP 2 SECTION 1, SLATT: PCB A-1796 | GEN, NWACI, PDCI, WOJD, COI
142 | 23-04727 |  | 04/13/2023 10:00 | 04/13/2023 14:00 | -PACW- TALBOT: CBS 1W45 AND 1W46 | WALLA WALLA (PAC)-TALBOT 230KV LINE, -PACW- TALBOT: CBS 1W45 AND 1W46 | WOH
143 | 23-01369 | 12690929 | 04/13/2023 10:00 | 04/13/2023 11:00 | GRAND COULEE: PCB 2092, GRAND COULEE: PCB 2096 | GRAND COULEE: PCB 2092, GRAND COULEE: PCB 2096 | GEN, NOH, WOCN
144 | 22-15346 | 13094245 | 04/13/2023 11:00 | 04/13/2023 13:00 | MARION: PCB 4374 | MARION: PCB 4374 | NWACI
145 | 23-01371 | 12691159 | 04/13/2023 11:00 | 04/13/2023 12:00 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 | GEN, NOH, WOCN
146 | 23-01131 | 12691118 | 04/13/2023 11:30 | 04/13/2023 13:00 | SLATT: 230KV CAP GROUP 2 SECTION 2 INCLUDING PCB A-1798 | SLATT: 230KV CAP GROUP 2 SECTION 2 INCLUDING PCB A-1798, SLATT: 230KV CAP GROUP 2 SECTION 2, SLATT: PCB A-1798 | GEN, NWACI, PDCI, WOJD, COI
147 | 23-00994 | 12690952 | 04/13/2023 12:00 | 04/13/2023 15:00 | JOHN DAY: PCB 4137 | JOHN DAY: PCB 4137 | NWACI, PDCI, WOJD, COI
148 | 23-02664 | 12862475 | 04/13/2023 12:30 | 04/13/2023 13:15 | COSMOPOLIS: 115KV CAP GROUP 1 INCLUDING PCB B-1335 | COSMOPOLIS: PCB B-1335, COSMOPOLIS: 115KV CAP GROUP 1 INCLUDING PCB B-1335, COSMOPOLIS: 115KV CAP GROUP 1
149 | 23-01373 | 12691166 | 04/13/2023 12:30 | 04/13/2023 13:30 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 | GEN, NOH, WOCN
150 | 23-01132 | 12691126 | 04/13/2023 13:00 | 04/13/2023 14:30 | SLATT: 230KV CAP GROUP 3 SECTION 1 INCLUDING PCB A-1799 | SLATT: 230KV CAP GROUP 3 SECTION 1 INCLUDING PCB A-1799, SLATT: 230KV CAP GROUP 3 SECTION 1, SLATT: PCB A-1799 | COI, NWACI, PDCI, WOJD
151 | 22-15426 | 13094242 | 04/13/2023 13:00 | 04/14/2023 15:00 | MARION: PCB 4377 | MARION: PCB 4377 | NWACI
152 | 23-00323 | 12011687 | 04/13/2023 16:30 | 04/13/2023 17:00 | BIG EDDY: PCB A-824 OF THE DALLES PH-BIG EDDY NO 4 230KV LINE | BIG EDDY: PCB A-824 OF THE DALLES PH-BIG EDDY NO 4 230KV LINE | GEN, FCRPS
153 | 23-01133 | 12584037 | 04/14/2023 07:30 | 04/14/2023 09:00 | JONES CANYON: 230KV CAP GROUP 1 SECTION 1 INCLUDING PCB A-1688 | JONES CANYON: 230KV CAP GROUP 1 SECTION 1 INCLUDING PCB A-1688, JONES CANYON: 230KV CAP GROUP 1 SECTION 1, JONES CANYON: PCB A-1688 | WOCS
154 | 23-05004 | 13095202 | 04/14/2023 08:00 | 04/17/2023 18:00 | SCL Duwamish - SCL Creston 230kV Line | SCL Duwamish - SCL Creston 230kV Line, MAPLE VALLEY-DUWAMISH NO 1 230KV LINE | NOEL, SOC
155 | 23-05014 | 13164753 | 04/14/2023 08:00 | 04/17/2023 18:00 | MAPLE VALLEY: A-1106 TERMINAL OF , MAPLE VALLEY-DUWAMISH NO 1 230KV LINE | MAPLE VALLEY: A-1106 TERMINAL OF , MAPLE VALLEY-DUWAMISH NO 1 230KV LINE | NOEL, SOC
156 | 23-00160 | 11688371 | 04/14/2023 08:00 | 04/14/2023 15:00 | ICE HARBOR-FRANKLIN NO 2 115KV LINE INCLUDING THE SACAJAWEA TAP | MARTINDALE-FRANKLIN SECTION OF ICE HARBOR-FRANKLIN NO 2 115KV LINE, ICE HARBOR-FRANKLIN NO 2 115KV LINE INCLUDING THE SACAJAWEA TAP, SACAJAWEA TAP TO ICE HARBOR-FRANKLIN NO 2 115KV LINE | TCLA, TCLA, GEN, TCLA, FCRPS, LOAD
157 | 23-00159 | 11685399 | 04/14/2023 08:00 | 04/14/2023 15:00 | ICE HARBOR-FRANKLIN NO 1 115KV LINE | ICE HARBOR-FRANKLIN NO 1 115KV LINE, FRANKLIN: PCB B-1528 | GEN, TCLA
158 | 23-01134 | 12584045 | 04/14/2023 09:30 | 04/14/2023 11:00 | JONES CANYON: 230KV CAP GROUP 1 SECTION 2 INCLUDING PCB A-1689 | JONES CANYON: 230KV CAP GROUP 1 SECTION 2 INCLUDING PCB A-1689, JONES CANYON: 230KV CAP GROUP 1 SECTION 2, JONES CANYON: PCB A-1689 | WOCS
159 | 23-04067 |  | 04/14/2023 15:00 | 04/14/2023 16:00 | BONNERS FERRY-SMTH SMITH CREEK NO 1 115KV LINE, MOYIE SPRINGS-BONNERS FERRY SECTION OF LIBBY-BONNERS FERRY NO 1 115KV LINE | MOYIE: BONNERS FERRY ID 115KV FEEDER 1, BONNERS FERRY-SMTH SMITH CREEK NO 1 115KV LINE, NORTH BENCH: BONNERS FERRY ID 13.8KV FEEDER 1, MOYIE SPRINGS-BONNERS FERRY SECTION OF LIBBY-BONNERS FERRY NO 1 115KV LINE, NORTH BENCH: NORTHERN LIGHTS 13.8KV FEEDER 1, NLI - MT HALL TAP
160 | 23-00354 | 12014388 | 04/17/2023 06:30 | 04/17/2023 07:00 | BIG EDDY: PCB B-1050 OF THE DALLES PH-BIG EDDY NO 2 115KV LINE | BIG EDDY: 115/13.2KV TRANSFORMER 8, BIG EDDY: PCB B-1050 OF THE DALLES PH-BIG EDDY NO 2 115KV LINE | GEN, FCRPS
161 | 23-00328 | 12495548 | 04/17/2023 06:30 | 04/27/2023 17:00 | THE DALLES PH: 115/13.2KV BANK 2 | THE DALLES PH: 115/13.2KV BANK 2
162 | 23-01682 | 12736001 | 04/17/2023 06:30 | 04/19/2023 17:00 | -USBR- GRAND COULEE- BELL #3 230KV LINE INCLUDING GRAND COULEE PCB 5286 AND 230KV AUX BUS SECTION 1 | -USBR- GRAND COULEE- BELL #3 230KV LINE INCLUDING GRAND COULEE PCB 5286 AND 230KV AUX BUS SECTION 1, GRAND COULEE: PCB 5286, GRAND COULEE-BELL NO 3 230KV LINE, GRAND COULEE: 230KV AUX BUS SECTION 1 | NOH, WOCN, COI, NWACI, PDCI, WOH
163 | 23-01947 | 12853185 | 04/17/2023 07:00 | 04/28/2023 14:00 | SPAR CANYON: PCB A-185 | SPAR CANYON: PCB A-185 | LOAD, SEIL
164 | 23-03875 | 13108905 | 04/17/2023 07:00 | 04/21/2023 16:00 | LANE:115KV NORTH MAIN BUS TO INCLUDE PCB B-1620 | LANE:115KV NORTH MAIN BUS TO INCLUDE PCB B-1620 , LANE: 115KV NORTH MAIN BUS, LANE: 115KV CAP GROUP 1, LANE: 230/115KV TRANSFORMER 2, WILLOW CREEK-LANE 115KV LINE, DANEBO-LANE 115KV LINE | LOAD, EWEB
165 | 22-14993 | 12724487 | 04/17/2023 07:00 | 04/17/2023 16:00 | TAFT: PCB 4028 | TAFT: PCB 4028 | MT-NW, NOH, WOH
166 | 23-02387 | 12846978 | 04/17/2023 07:00 | 04/17/2023 08:30 | SHELTON: 115KV CAP GROUP 1 SECTIONS 1 & 2 INCLUDING PCB B-1130 | SHELTON: 115KV CAP GROUP 1 SECTIONS 1 & 2 INCLUDING PCB B-1130, SHELTON: 115KV CAP GROUP 1 SECTION 1, SHELTON: 115KV CAP GROUP 1 SECTION 2, SHELTON: PCB B-1130
167 | 23-00161 | 11756959 | 04/17/2023 07:00 | 04/18/2023 17:00 | WAUTOMA-KNIGHT NO 1 500KV LINE | WAUTOMA-KNIGHT NO 1 500KV LINE, WAUTOMA: PCB 5247, WAUTOMA: PCB 5250, KNIGHT: PCB 5492, KNIGHT: PCB 5489 | BCHT, BCHW, NI, NOH, SIG, WOCN, WOCS, WOJD
168 | 23-01217 | 12667458 | 04/17/2023 07:30 | 04/20/2023 16:00 | ALLSTON-DRISCOLL NO 1 230KV LINE | ALLSTON-DRISCOLL NO 1 230KV LINE | LOAD, SOA
169 | 23-04046 | 13034320 | 04/17/2023 08:00 | 04/20/2023 15:00 | ASHE: 230KV CAP GROUP 2 RELAYS INCLUDING PCB A-892 BFR | ASHE: 230KV CAP GROUP 2 RELAYS INCLUDING PCB A-892 BFR, ASHE: PCB A-892, ASHE: 230KV CAP GROUP 2 | NOH, TCLA
170 | 23-00781 | 12537220 | 04/17/2023 08:00 | 04/17/2023 16:00 | MARION: 500KV CAP GROUP 1 INCLUDING PCB 4331 | MARION: 500KV CAP GROUP 1, MARION: 500KV CAP GROUP 1 INCLUDING PCB 4331, MARION: PCB 4331 | COI, PDCI, WOCS, NWACI
171 | 23-05268 | 13134400 | 04/17/2023 08:00 | 04/20/2023 15:00 | SNO-KING: 230/115KV TRANSFORMER 1, INCLUDING PCB'S A-1204, B-1586 AND L-1432 | SNO-KING: 230/115KV TRANSFORMER 1, SNO-KING: PCB A-1204, SNO-KING: PCB B-1586, INCLUDING PCB'S A-1204, B-1586 AND L-1432, SNO-KING: 13.8KV PCB L-1432 | LOAD, NOEL, SOC, BCHT, BCHW
172 | 23-03846 | 13037969 | 04/17/2023 08:00 | 04/20/2023 15:00 | ASHE: PCB 4907 INCLUDING 500KV REACTOR 1 | ASHE: PCB 4907, ASHE: PCB 4907 INCLUDING 500KV REACTOR 1, ASHE: 500KV REACTOR 1 | FCRPS, NOH, NWACI
173 | 23-03490 | 13011035 | 04/17/2023 08:00 | 04/20/2023 15:00 | MINIDOKA PH-CANAL TAP SECTION OF THE MINIDOKA PH-UNITY NO 1 138KV LINE | MINIDOKA PH-CANAL TAP SECTION OF THE MINIDOKA PH-UNITY NO 1 138KV LINE, MINIDOKA PH-CANAL SECTION OF MINIDOKA PH-UNITY NO 1 138KV LINE, MINIDOKA PH: PCB 2372 | SEIL
174 | 23-04634 | 13081957 | 04/17/2023 08:00 | 04/17/2023 16:30 | TWO MILE-LANGLOIS SECTION OF BANDON-ROGUE NO 1 115KV LINE | TWO MILE-LANGLOIS SECTION OF BANDON-ROGUE NO 1 115KV LINE
175 | 23-00823 | 12798143 | 04/17/2023 08:00 | 04/18/2023 12:00 | MONMOUTH: PCB B-604 | MONMOUTH: PCB B-604, MONMOUTH-SOUTH SECTION OF SALEM-ALBANY NO 2 115KV LINE
176 | 23-03381 | 13042672 | 04/17/2023 08:00 | 04/20/2023 15:00 | OLYMPIA-ST CLAIR NO 1 230KV LINE | OLYMPIA-ST CLAIR NO 1 230KV LINE | RP
177 | 23-01728 |  | 04/17/2023 08:00 | 04/19/2023 15:00 | BELL: A-558 TERMINAL OF THE GRAND COULEE-BELL#3 230KV LINE | BELL: A-558 TERMINAL OF THE GRAND COULEE-BELL#3 230KV LINE , BELL: PCB A-558 | MT-NW, WOH
178 | 23-02388 | 12847053 | 04/17/2023 08:30 | 04/17/2023 10:00 | SHELTON: 230KV CAP GROUP 2 INCLUDING PCB A-984 | SHELTON: 230KV CAP GROUP 2 INCLUDING PCB A-984, SHELTON: 230KV CAP GROUP 2, SHELTON: PCB A-984 | PA, RP
179 | 23-03519 | 12975935 | 04/17/2023 08:30 | 04/17/2023 17:00 | LONGVIEW: 230KV SOUTH MAIN BUS INCLUDING PCB A-100 | LONGVIEW: 230KV SOUTH MAIN BUS, LONGVIEW: 230KV SOUTH MAIN BUS INCLUDING PCB A-100, LONGVIEW: PCB A-98, LONGVIEW: PCB A-640, LONGVIEW: PCB A-100, LONGVIEW: PCB A-104, LONGVIEW: PCB A-106, LONGVIEW: PCB A-1960, LONGVIEW-ALLSTON NO 1 230KV LINE, LONGVIEW-ALLSTON NO 2 230KV LINE, LONGVIEW: 230/69KV TRANSFORMER 1, LONGVIEW: 230/115KV TRANSFORMER 3 | SOA, PA, LOAD
180 | 22-10183 | 12036167 | 04/17/2023 09:00 | 04/17/2023 18:00 | BEST LANE TAP TO BRASADA-HARNEY NO 1 115KV LINE | BEST LANE TAP TO BRASADA-HARNEY NO 1 115KV LINE, BEST LANE TAP SECT. OF BRASADA-HARNEY NO.1, 115KV LINE, HAMPTON-BEST LANE SECTION OF BRASADA-HARNEY NO 1 115KV LINE, BEST LANE-RILEY SECTION OF BRASADA-HARNEY NO 1 115KV LINE | NWACI, ID-NW
181 | 23-00824 |  | 04/17/2023 12:00 | 04/18/2023 16:00 | MONMOUTH: 115/12.5KV TRANSFORMER 1 | MONMOUTH: 115/12.5KV TRANSFORMER 1, MONMOUTH: B-609 TRANSFORMER BUS DISC | SLAL
182 | 23-03525 | 12976427 | 04/17/2023 17:01 | 05/04/2023 08:30 | LONGVIEW-ALLSTON #1 230KV LINE INCLUDING LONGVIEW: PCB A-100, A-100 M/B DISC, AND 230KV SOUTH AUX BUS | LONGVIEW-ALLSTON #1 230KV LINE INCLUDING LONGVIEW: PCB A-100, A-100 M/B DISC, AND 230KV SOUTH AUX BUS, LONGVIEW-ALLSTON NO 1 230KV LINE, LONGVIEW: PCB A-100, LONGVIEW: 230KV SOUTH AUX BUS, LONGVIEW: PCB A-642, ALLSTON: PCB A-1362 | SOA
183 | 23-00597 | 12690729 | 04/18/2023 06:30 | 04/18/2023 19:00 | ECHO LAKE-MONROE NO 1 500KV LINE, ECHO LAKE: PCB 5111, ECHO LAKE: PCB 5114, MONROE: PCB 4522, MONROE: PCB 4526, SNO-KING: PCB 4815, SNO-KING: 500/230KV TRANSFORMER 4 | ECHO LAKE-MONROE NO 1 500KV LINE, ECHO LAKE-SNO-KING SECTION OF ECHO LAKE-MONROE NO 1 500KV LINE, SNO-KING-MONROE SECTION OF ECHO LAKE-MONROE NO 1 500KV LINE, ECHO LAKE: PCB 5111, SNO-KING TAP TO ECHO LAKE-MONROE NO 1 500KV LINE, ECHO LAKE: PCB 5114, MONROE: PCB 4522, MONROE: PCB 4526, SNO-KING: PCB 4815, SNO-KING: 500/230KV TRANSFORMER 4 | IROL, NI, NOEL, SIG, SOC, WOCN, COI, NWACI, PDCI, BCHT, BCHW, LOAD
184 | 23-00726 | 12380736 | 04/18/2023 07:00 | 04/18/2023 09:00 | COLVILLE: 115KV CAP GROUP 1 SECTIONS 1, 2, & 3 INCLUDING PCB'S B-1769, B-1771, B-1773, & B-1780 | COLVILLE: 115KV CAP GROUP 1 SECTIONS 1, 2, & 3 INCLUDING PCB'S B-1769, B-1771, B-1773, & B-1780, COLVILLE: 115KV CAP GROUP 1 SECTION 1, COLVILLE: 115KV CAP GROUP 1 SECTION 2, COLVILLE: 115KV CAP GROUP 1 SECTION 3, COLVILLE: PCB B-1769, COLVILLE: PCB B-1771, COLVILLE: PCB B-1773, COLVILLE: PCB B-1780
185 | 22-14994 | 12691204 | 04/18/2023 07:00 | 04/18/2023 16:00 | TAFT: PCB 4125 | TAFT: PCB 4125 | MT-NW, WOH
186 | 23-02405 | 12847678 | 04/18/2023 07:00 | 04/18/2023 15:00 | OLYMPIA: 230KV CAP GROUP 2 SECTION 1 AND 2 INCLUDING LBD A-223, LBD A-225 AND 230KV REACTIVE BUS | OLYMPIA: 230KV CAP GROUP 2 SECTION 1 AND 2 INCLUDING LBD A-223, LBD A-225 AND 230KV REACTIVE BUS, OLYMPIA: 230KV CAP GROUP 2 SECTION 1, OLYMPIA: 230KV CAP GROUP 2 SECTION 2, OLYMPIA: LBD A-223, OLYMPIA: LBD A-225 | NOEL, SOC, WOCN
187 | 23-02392 | 12847675 | 04/18/2023 07:00 | 04/18/2023 15:00 | OLYMPIA: 115KV CAP GROUP 3 | OLYMPIA: 115KV CAP GROUP 3
188 | 23-01447 | 12690344 | 04/18/2023 07:30 | 04/18/2023 16:00 | ALVEY: PCB 5091 | ALVEY: PCB 5091
189 | 23-01924 | 12884440 | 04/18/2023 08:00 | 04/18/2023 15:00 | SCHULTZ: PCB 5129, BFR | SCHULTZ: PCB 5129, BFR | WOCN
190 | 23-04452 | 13093904 | 04/18/2023 08:00 | 04/18/2023 15:00 | LIBBY: PCB A-1589 | LIBBY: PCB A-1589 | MT-NW
191 | 23-02394 | 12948998 | 04/18/2023 08:00 | 04/18/2023 15:00 | PORT ANGELES: 115KV CAP GROUP 1 SECTIONS 1 & 2 INCLUDING PCB B-648 AND LBD'S B-645 AND B-1883 | PORT ANGELES: LBD B-1883, PORT ANGELES: 115KV CAP GROUP 1 SECTIONS 1 & 2 INCLUDING PCB B-648 AND LBD'S B-645 AND B-1883, PORT ANGELES: LBD B-645, PORT ANGELES: PCB B-648, PORT ANGELES: 115KV CAP GROUP 1 SECTION 1, PORT ANGELES: 115KV CAP GROUP 1 SECTION 2 | WOCN
192 | 23-02964 | 13010398 | 04/18/2023 08:30 | 04/18/2023 15:00 | LANE: PCB A-1458, AND 230KV CAP GROUP 2 | LANE: 230KV CAP GROUP 2, LANE: PCB A-1458, AND 230KV CAP GROUP 2 | EWEB, SCORC, NWACI
193 | 23-04006 | 13038291 | 04/18/2023 09:00 | 04/19/2023 15:00 | NORTH BONNEVILLE: PCB A-10 | NORTH BONNEVILLE: PCB A-10 | WOCS
194 | 22-10180 | 12076115 | 04/18/2023 09:00 | 04/18/2023 18:00 | STARVATION RIDGE TAP TO BRASADA-HARNEY NO 1 115KV LINE | STARVATION RIDGE TAP TO BRASADA-HARNEY NO 1 115KV LINE, RILEY-STARVATION RIDGE SECTION OF BRASADA-HARNEY NO 1 115KV LINE, STARVATION RIDGE-HARNEY SECTION OF BRASADA-HARNEY NO 1 115KV LINE | ID-NW, NWACI/PDCI
195 | 23-00727 | 12380710 | 04/18/2023 10:30 | 04/18/2023 11:30 | ADDY: 230KV CAP GROUP 1 INCLUDING PCB A-147 | ADDY: 230KV CAP GROUP 1, ADDY: 230KV CAP GROUP 1 INCLUDING PCB A-147, ADDY: PCB A-147 | SOB
196 | 23-03526 | 12975923 | 04/18/2023 12:00 | 04/18/2023 14:00 | SNO-KING: 500/230KV TRANSFORMER 4 | SNO-KING: 500/230KV TRANSFORMER 4, SNO-KING: PCB 4815 | LOAD, NOEL, SIG, SOC, IROL, WOCN, BCHT, BCHW, NI
197 | 23-00716 | 12379309 | 04/18/2023 12:00 | 04/18/2023 15:00 | DEER PARK: 115KV CAP GROUP 1 INCLUDING PCB B-1913 | DEER PARK: 115KV CAP GROUP 1 INCLUDING PCB B-1913, DEER PARK: PCB B-1913
198 | 23-00717 | 12690388 | 04/19/2023 07:00 | 04/19/2023 13:00 | BELL: TAFT 1 500KV LINE SERIES CAP GROUP 1 INCLUDING PCB 5320 | BELL: TAFT 1 500KV LINE SERIES CAP GROUP 1 INCLUDING PCB 5320, BELL: TAFT 1 500KV LINE SERIES CAP GROUP 1, BELL: PCB 5320 | WOH, MT-NW
199 | 23-00718 | 12379595 | 04/19/2023 07:00 | 04/19/2023 09:00 | BELL: 230KV CAP GROUP 10 SECTIONS 1 AND 2 INCLUDING LBDS A-925 AND A-926 | BELL: 230KV CAP GROUP 10 SECTION 1, BELL: 230KV CAP GROUP 10 SECTIONS 1 AND 2 INCLUDING LBDS A-925 AND A-926, BELL: 230KV CAP GROUP 10 SECTION 2, BELL: LBD A-925, BELL: LBD A-926, BELL: PCB A-368 | MT-NW, WOH
200 | 22-14995 | 12691269 | 04/19/2023 07:00 | 04/19/2023 16:00 | TAFT: PCB 4145, INCLUDING 500KV REACTOR 1 | TAFT: PCB 4145, TAFT: 500KV REACTOR 1, INCLUDING 500KV REACTOR 1 | MT-NW, WOH
201 | 23-01448 | 12691282 | 04/19/2023 07:30 | 04/19/2023 16:00 | ALVEY: PCB 5099 INCLUDING 500KV REACTOR #2 | ALVEY: 500KV REACTOR 2, ALVEY: PCB 5099 INCLUDING 500KV REACTOR #2, ALVEY: PCB 5099 | COI, NWACI, PDCI, SLAL
202 | 23-01864 | 12792344 | 04/19/2023 08:00 | 04/22/2023 18:00 | BRASADA-CHRISTMAS VALLEY SECT. OF BRASADA-HARNEY NO.1, 115KV LINE | BRASADA-CHRISTMAS VALLEY SECT. OF BRASADA-HARNEY NO.1, 115KV LINE, CHRISTMAS VALLEY-HAMPTON SECTION OF BRASADA-HARNEY NO 1 115KV LINE, CHRISTMAS VALLEY TAP TO BRASADA-HARNEY NO 1 115KV LINE | ID-NW, NWACI
203 | 23-02775 | 12884464 | 04/19/2023 08:00 | 04/19/2023 15:00 | SCHULTZ: PCB 5132, BFR | SCHULTZ: PCB 5132, BFR | WOCN
204 | 23-00719 | 12379756 | 04/19/2023 09:00 | 04/19/2023 11:00 | BELL: 230KV CAP GROUP 9 SECTIONS 1, 2, AND 3 INCLUDING PCBS A-931, A-932, AND A-933 | BELL: PCB A-931, BELL: 230KV CAP GROUP 9 SECTIONS 1, 2, AND 3 INCLUDING PCBS A-931, A-932, AND A-933, BELL: PCB A-932, BELL: PCB A-933, BELL: 230KV CAP GROUP 9 SECTION 1, BELL: 230KV CAP GROUP 9 SECTION 2, BELL: 230KV CAP GROUP 9 SECTION 3, BELL: 230KV CAP GROUP 9 REACTIVE BUS, BELL: PCB A-378 | MT-NW, WOH
205 | 23-01430 | 12691294 | 04/19/2023 09:00 | 04/19/2023 16:00 | SLATT-BUCKLEY NO 1 500KV LINE | SLATT-BUCKLEY NO 1 500KV LINE, SLATT: BUCKLEY 1 500KV LINE SERIES CAP GROUP 1 | NWACI, PDCI, SIG, WOJD, WOM, WOS, COI
206 | 23-01527 | 12690348 | 04/19/2023 09:00 | 04/19/2023 16:00 | ASHE-MARION NO 2 500KV LINE | ASHE-MARION NO 2 500KV LINE | BCHT, BCHW, NI, NWACI, PDCI, SIG, WOCS, WOJD, WOM, COI
207 | 23-00720 | 12379762 | 04/19/2023 11:00 | 04/19/2023 13:00 | BELL: 230KV CAP GROUP 1 | BELL: 230KV CAP GROUP 1, BELL: PCB A-556 | MT-NW, WOH
208 | 23-01686 | 12735737 | 04/20/2023 06:30 | 05/12/2023 17:00 | GRAND COULEE: PCB 5782 | GRAND COULEE: PCB 5782 | NOH, WOCN, COI, NWACI, PDCI
209 | 23-00429 | 12691354 | 04/20/2023 07:00 | 04/22/2023 16:00 | MALIN-HILLTOP NO 1 230KV LINE INCLUDING CANBY TAP | HILLTOP: PCB A-1529, MALIN-HILLTOP NO 1 230KV LINE INCLUDING CANBY TAP, HILLTOP: PCB A-1525, CANBY: PCB A-1391, CANBY TAP TO MALIN-HILLTOP NO 1 230KV LINE, MALIN-HILLTOP NO 1 230KV LINE, MALIN: CB 1L11, MALIN: CB 1L12 | RATS, NWACI, SWORE, COI
210 | 23-01273 | 12690615 | 04/20/2023 08:00 | 04/20/2023 11:00 | ECHO LAKE: PCB 5072 | ECHO LAKE: PCB 5072, ECHO LAKE: PCB 5111 | BCHT, BCHW, NOEL, SOC, NI, WOCN
211 | 23-02777 | 12884568 | 04/20/2023 08:00 | 04/20/2023 15:00 | SCHULTZ: PCB 5179, BFR | SCHULTZ: PCB 5179, BFR | NOH, WOCN
212 | 23-00745 | 12408619 | 04/20/2023 08:00 | 04/20/2023 12:00 | TRENTWOOD: 115KV CAP GROUP 1 SECTIONS 1 AND 2 INCLUDING PCB'S B-1937 AND B-1938 AND 115KV REACTIVE BUS | TRENTWOOD: 115KV CAP GROUP 1 SECTION 1, TRENTWOOD: 115KV CAP GROUP 1 SECTIONS 1 AND 2 INCLUDING PCB'S B-1937 AND B-1938 AND 115KV REACTIVE BUS, TRENTWOOD: 115KV CAP GROUP 1 SECTION 2, TRENTWOOD: PCB B-1937, TRENTWOOD: PCB B-1938, TRENTWOOD: 115KV REACTIVE BUS | LOAD
213 | 23-02347 | 12841304 | 04/20/2023 11:00 | 04/20/2023 14:00 | ECHO LAKE: PCB 5121 | ECHO LAKE: PCB 5121 | BCHT, BCHW, NOEL, SOC, WOCN, NI
214 | 23-05018 | 13164917 | 04/21/2023 08:00 | 04/25/2023 15:00 | MAPLE VALLEY: A-1134 TERMINAL OF , MAPLE VALLEY-MASSACHUSETTS NO 1 230KV LINE | MAPLE VALLEY: A-1134 TERMINAL OF , MAPLE VALLEY-MASSACHUSETTS NO 1 230KV LINE | NOEL, SOC
215 | 23-05013 | 13095422 | 04/21/2023 08:00 | 04/25/2023 18:00 | SCL - TALBOT HILL-SOUTH 230KV LINE | SCL - TALBOT HILL-SOUTH 230KV LINE, MAPLE VALLEY-MASSACHUSETTS NO 1 230KV LINE | NOEL, SOC
216 | 23-05008 | 13095212 | 04/21/2023 08:00 | 04/23/2023 18:00 | Talbot Hill - SCL South 230kV Line | Talbot Hill - SCL South 230kV Line | SOC, NOEL
217 | 23-00370 | 12794215 | 04/21/2023 21:00 | 04/22/2023 07:00 | GRANDVIEW-SNIPES SECTION OF THE GRANDVIEW-REDMOUNTAIN NO 1 115KV LINE INCLUDING THE PROSSER TAP | PROSSER: BENTON CO PUD 115KV FEEDER 1, GRANDVIEW-SNIPES SECTION OF THE GRANDVIEW-REDMOUNTAIN NO 1 115KV LINE INCLUDING THE PROSSER TAP, PROSSER: BENTON CO PUD 115KV FEEDER 2, PROSSER: BENTON REA 12.5KV FEEDER 1 BY BENTON CO PUD, RIVERFRONT: BENTON CO PUD 115KV FEEDER 1, GRANDVIEW-PROSSER SECTION OF GRANDVIEW-RED MOUNTAIN NO 1 115KV LINE, PROSSER-SNIPES SECTION OF GRANDVIEW-RED MOUNTAIN NO 1 115KV LINE | GEN, TCLA, LOAD
218 | 23-00079 | 11292157 | 04/22/2023 07:00 | 04/22/2023 13:00 | -USBR- GRAND COULEE: PCB 6782 | -USBR- GRAND COULEE: PCB 6782 | NOH, WOCN, COI, NWACI, PDCI
219 | 23-01828 |  | 04/24/2023 07:00 | 04/24/2023 14:00 | GOSHEN: GOSHEN-DRUMMOND #1 161KV LINE INCLUDING GOSHEN 161KV WEST M/B, 161/115KV XFMR #1, PCB B-828, PCB B-1346, AND DRUMMOND 161/115KV XFMR #4 | GOSHEN-DRUMMOND NO 1 161KV LINE, GOSHEN: GOSHEN-DRUMMOND #1 161KV LINE INCLUDING GOSHEN 161KV WEST M/B, 161/115KV XFMR #1, PCB B-828, PCB B-1346, AND DRUMMOND 161/115KV XFMR #4, DRUMMOND: 161/115KV TRANSFORMER 4, GOSHEN: 161/115KV TRANSFORMER 1, GOSHEN: 161/115KV TRANSFORMER 2, GOSHEN: PCB B-828, GOSHEN: PCB B-1346, GOSHEN: 161KV MAIN BUS, GOSHEN: 115KV MAIN BUS, CATTLE CREEK-GOSHEN NO 1 115KV LINE | GEN, LOAD, SEIL
220 | 23-05080 | 13126620 | 04/24/2023 07:00 | 05/10/2023 16:00 | LANE: 115KV SOUTH MAIN BUS INCLUDING PCB'S B-1614, B-1612, B-1610 AND B-1608 | LANE: 115KV SOUTH MAIN BUS, LANE: 115KV SOUTH MAIN BUS INCLUDING PCB'S B-1614, B-1612, B-1610 AND B-1608 , LANE: 115KV AUX BUS, LANE: 115KV CENTER MAIN BUS, EUGENE-LANE NO 1 115KV LINE, LANE: 230/115KV TRANSFORMER 1, LANE-RAINBOW VALLEY SECTION OF LANE-WENDSON NO 1 115KV LINE | LOAD, EWEB, SCORC
221 | 23-00276 | 12394681 | 04/24/2023 07:00 | 04/28/2023 16:30 | SATSOP: 500/230KV TRANSFORMER 1, (FORCES OUT THE PAUL-SATSOP 1 500KV LINE) | SATSOP: 500/230KV TRANSFORMER 1, PAUL-SATSOP NO 1 500KV LINE, (FORCES OUT THE PAUL-SATSOP 1 500KV LINE) | PA, RP, LOAD, SI, SIG
222 | 23-01170 | 12690377 | 04/24/2023 07:00 | 04/27/2023 16:00 | BELL: PCB 5313 | BELL: PCB 5313 | MT-NW, WOH
223 | 23-03848 |  | 04/24/2023 07:00 | 04/24/2023 08:00 | SAND CREEK: 115KV CAP GROUP 1 INCLUDING 115KV REACTIVE BUS | SAND CREEK: 115KV CAP GROUP 1 SECTION 1, SAND CREEK: 115KV CAP GROUP 1 INCLUDING 115KV REACTIVE BUS, SAND CREEK: 115KV CAP GROUP 1 SECTION 2, SAND CREEK: 115KV CAP GROUP 1 SECTION 3
224 | 23-01829 | 12857982 | 04/24/2023 08:00 | 04/24/2023 13:00 | CATTLE CREEK-GOSHEN NO 1 115KV LINE | GOSHEN: PCB B-705, CATTLE CREEK-GOSHEN NO 1 115KV LINE, CATTLE CREEK SW STA: PCB B-2095, CATTLE CREEK SW STA: PCB B-2107 | SEIL, GEN
225 | 23-01847 | 13043170 | 04/24/2023 08:00 | 04/27/2023 15:00 | SNIPES-CHANDLER SECTION OF GRANDVIEW-RED MOUNTAIN NO 1 115KV LINE | SNIPES-CHANDLER SECTION OF GRANDVIEW-RED MOUNTAIN NO 1 115KV LINE | TCLA, LOAD
226 | 23-00530 | 12570534 | 04/24/2023 08:00 | 05/26/2023 16:00 | HANFORD-WAUTOMA NO 2 500KV LINE | HANFORD-WAUTOMA NO 2 500KV LINE | NOH, NWACI, PDCI, SIG, COI
227 | 23-01549 | 12691325 | 04/24/2023 08:00 | 04/26/2023 15:00 | LOWER GRANITE: PCB 4775, INCLUDING 500KV SOUTH BUS | LOWER GRANITE: PCB 4775, LOWER GRANITE: 500KV SOUTH BUS, INCLUDING 500KV SOUTH BUS | MT-NW, WOH, WOLM, GEN
228 | 23-03382 | 13059058 | 04/24/2023 08:00 | 04/27/2023 15:00 | SHELTON-KITSAP NO 4 230KV LINE | SHELTON-KITSAP NO 4 230KV LINE, KITSAP: PCB B-945, KITSAP: 230/115KV TRANSFORMER 2 | RP, PA, LOAD, WOCN
229 | 23-00204 | 12105329 | 04/24/2023 08:00 | 04/25/2023 16:30 | FREDERICKSON-SOUTH TACOMA NO 1 230KV LINE INCLUDING SOUTH TACOMA: PCB A-1092 AND PCB A-1098 | SOUTH TACOMA: PCB A-1092, FREDERICKSON-SOUTH TACOMA NO 1 230KV LINE INCLUDING SOUTH TACOMA: PCB A-1092 AND PCB A-1098, SOUTH TACOMA: PCB A-1098, FREDERICKSON-SOUTH TACOMA NO 1 230KV LINE | GEN, NOEL, SOC, RP
230 | 23-01263 | 12623352 | 04/24/2023 08:00 | 04/26/2023 15:00 | MARION-ALVEY NO 1 500KV LINE, INCLUDING MARION 1 500KV SERIES CAP GROUP 1 | MARION-ALVEY NO 1 500KV LINE, ALVEY: MARION 1 500KV LINE SERIES CAP GROUP 1, INCLUDING MARION 1 500KV SERIES CAP GROUP 1 | BCHT, BCHW, NI, NWACI, SIG, COI, SCORC
231 | 23-03847 | 13037980 | 04/24/2023 08:00 | 04/27/2023 15:00 | ASHE: PCB 4909 INCLUDING 500KV REACTOR 2 | ASHE: PCB 4909 INCLUDING 500KV REACTOR 2, ASHE: PCB 4909, ASHE: 500KV REACTOR 2 | FCRPS, NOH, NWACI
232 | 23-04284 |  | 04/24/2023 08:00 | 05/05/2023 15:00 | -PGE- MURRAYHILL- SHERWOOD NO 1 & 2 230KV LINES | -PGE- MURRAYHILL- SHERWOOD NO 1 & 2 230KV LINES, MURRAY HILL (PGE)-SHERWOOD NO 1 230KV LINE, MURRAY HILL (PGE)-SHERWOOD NO 2 230KV LINE | SOA
233 | 23-00336 | 12118791 | 04/24/2023 08:00 | 04/27/2023 17:00 | CHIEF JOSEPH: PCB A-578 | CHIEF JOSEPH: PCB A-578, BFR | WOCN
234 | 23-01225 |  | 04/24/2023 08:00 | 04/27/2023 15:00 | KEELER: PGE ST MARYS NO 1 LINE RELAYS | KEELER: PGE ST MARYS NO 1 LINE RELAYS
235 | 23-00248 | 12977171 | 04/24/2023 09:00 | 04/26/2023 15:00 | HARNEY: PCB B-1727 INCLUDING 115KV REACTIVE GROUP 1 CAP SECTION 2 | HARNEY: PCB B-1727, HARNEY: PCB B-1727 INCLUDING 115KV REACTIVE GROUP 1 CAP SECTION 2, HARNEY: 115KV REACTIVE GROUP 1 CAP SECTION 2 | NWACI
236 | 23-04791 |  | 04/24/2023 09:30 | 04/28/2023 14:00 | -PACW- ISTHMUS: 23/115KV T-3351 TRANSFORMER | -PACW- ISTHMUS: 23/115KV T-3351 TRANSFORMER
237 | 23-04613 |  | 04/24/2023 09:30 | 04/28/2023 14:00 | -PACW- FAIRVIEW- PACW ISTHMUS NO 1 230KV LINE | -PACW- FAIRVIEW- PACW ISTHMUS NO 1 230KV LINE | NWACI, SOA
238 | 23-03849 | 13006158 | 04/24/2023 11:00 | 04/24/2023 12:00 | BONNERS FERRY: 115KV CAP GROUP 1 INCLUDING PCB B-1776 AND THE 115KV CAP GROUP 2 SECTION 1 INCLUDING PCB B-1777 | BONNERS FERRY: 115KV CAP GROUP 1, BONNERS FERRY: 115KV CAP GROUP 1 INCLUDING PCB B-1776 AND THE 115KV CAP GROUP 2 SECTION 1 INCLUDING PCB B-1777, BONNERS FERRY: 115KV CAP GROUP 2 SECTION 1, BONNERS FERRY: PCB B-1776, BONNERS FERRY: PCB B-1777
239 | 23-02735 | 12888833 | 04/24/2023 12:00 | 05/12/2023 11:00 | GARRISON-TAFT NO 2 500KV LINE, INCLUDING GARRISON PCB'S 4360, 4463 | GARRISON-TAFT NO 2 500KV LINE, GARRISON: PCB 4360, GARRISON: PCB 4463, INCLUDING GARRISON PCB'S 4360, 4463, GARRISON: TAFT 2 500KV LINE SERIES CAP GROUP 2 | MT-NW, SIG
240 | 23-03200 | 12976687 | 04/24/2023 21:00 | 04/25/2023 01:30 | LIBBY-TRUMBULL CREEK SECTION OF THE LIBBY-CONKELLEY #1 230KV LINE INCLUDING HASKILL TAP | HASKILL: FLATHEAD E COOP 230KV FEEDER 1, LIBBY-TRUMBULL CREEK SECTION OF THE LIBBY-CONKELLEY #1 230KV LINE INCLUDING HASKILL TAP, HASKILL-TRUMBULL CREEK SECTION OF LIBBY-CONKELLEY NO 1 230KV LINE, LIBBY-HASKILL SECTION OF LIBBY-CONKELLEY NO 1 230KV LINE, HASKILL TAP TO LIBBY-CONKELLEY NO 1 230KV LINE | MT-NW, GEN
241 | 23-02811 | 13028989 | 04/25/2023 07:00 | 04/26/2023 16:00 | BELLINGHAM: PSE #1 115KV LINE CONTROL RELAY INCLUDING PCB B-932 | BELLINGHAM: PSE #1 115KV LINE CONTROL RELAY INCLUDING PCB B-932, BELLINGHAM: PCB B-932 | SOC
242 | 23-01831 |  | 04/25/2023 07:00 | 04/25/2023 14:00 | GOSHEN: GOSHEN-DRUMMOND #1 161KV LINE INCLUDING GOSHEN 161KV WEST M/B, 161/115KV XFMR #1, PCB B-828, PCB B-1346, AND DRUMMOND 161/115KV XFMR #4 | GOSHEN-DRUMMOND NO 1 161KV LINE, GOSHEN: GOSHEN-DRUMMOND #1 161KV LINE INCLUDING GOSHEN 161KV WEST M/B, 161/115KV XFMR #1, PCB B-828, PCB B-1346, AND DRUMMOND 161/115KV XFMR #4, DRUMMOND: 161/115KV TRANSFORMER 4, GOSHEN: 161/115KV TRANSFORMER 1, GOSHEN: 161/115KV TRANSFORMER 2, GOSHEN: PCB B-828, GOSHEN: PCB B-1346, GOSHEN: 161KV MAIN BUS, GOSHEN: 115KV MAIN BUS, CATTLE CREEK-GOSHEN NO 1 115KV LINE | GEN, LOAD, SEIL
243 | 23-03201 | 12976705 | 04/25/2023 07:00 | 04/27/2023 14:00 | LIBBY-HASKILL SECTION OF LIBBY-CONKELLEY NO 1 230KV LINE INCLUDING THE A-274 LINE SECTIONALIZING DISCONNECT | HASKILL: A-274 LINE SECTIONALIZING DISC, LIBBY-HASKILL SECTION OF LIBBY-CONKELLEY NO 1 230KV LINE INCLUDING THE A-274 LINE SECTIONALIZING DISCONNECT, LIBBY-HASKILL SECTION OF LIBBY-CONKELLEY NO 1 230KV LINE | MT-NW, GEN
244 | 23-01424 | 13081986 | 04/25/2023 07:00 | 04/26/2023 17:00 | LEXINGTON: 115KV MAIN BUS INCLUDING PCB'S B-1464, B-1465, B-1466, B-1468, B-1470, B-1471, & B-1472 | LEXINGTON-SHAWNEE 115KV LINE, LEXINGTON: 115KV MAIN BUS INCLUDING PCB'S B-1464, B-1465, B-1466, B-1468, B-1470, B-1471, & B-1472, LEXINGTON-WEST KELSO 115KV LINE, LEXINGTON: 230/115KV TRANSFORMER 1, LEXINGTON: COWLITZ CO PUD 115KV FEEDER 4 (GARDNERS CORNER), LEXINGTON: PCB B-1464, LEXINGTON: PCB B-1465, LEXINGTON: PCB B-1466, LEXINGTON: PCB B-1468, LEXINGTON: PCB B-1470, LEXINGTON: PCB B-1471, LEXINGTON: PCB B-1472, LEXINGTON: 115KV MAIN BUS, BAKERS CORNER: PCB 115T2, BAKERS CORNER TAP TO LEXINGTON-LONGVIEW NO 1 115KV LINE | SOA, LOAD, PA, RP
245 | 23-03213 |  | 04/25/2023 07:30 | 04/25/2023 16:30 | CUSTER: MOD A-1251, MOD A-1253, MOD A-1255 | CUSTER: MOD A-1251, MOD A-1253, MOD A-1255
246 | 23-03850 | 13001132 | 04/25/2023 08:00 | 04/25/2023 09:00 | SANDPOINT: 115KV CAP GROUP 1 INCLUDING PCB B-817 | SANDPOINT: 115KV CAP GROUP 1 INCLUDING PCB B-817, SANDPOINT: 115KV CAP GROUP 1, SANDPOINT: PCB B-817
247 | 23-01830 | 12858126 | 04/25/2023 08:00 | 04/25/2023 13:00 | CATTLE CREEK-GOSHEN NO 1 115KV LINE | GOSHEN: PCB B-705, CATTLE CREEK-GOSHEN NO 1 115KV LINE, CATTLE CREEK SW STA: PCB B-2095, CATTLE CREEK SW STA: PCB B-2107 | SEIL, GEN
248 | 23-05315 | 13146393 | 04/25/2023 08:00 | 04/27/2023 16:00 | BCH - NICOLA-INGLEDOW 500KV LINE (5L81) | BCH - NICOLA-INGLEDOW 500KV LINE (5L81) | NI
249 | 23-05292 | 13130793 | 04/25/2023 12:00 | 04/25/2023 15:00 | CUSICK: 230KV CAP GROUP 1 | CUSICK: 230KV CAP GROUP 1, CUSICK: LBD A-169 | SOB
250 | 22-14567 | 12465455 | 04/26/2023 06:00 | 04/26/2023 14:00 | SWAN VALLEY - TETON #2 115KV LINE INCLUDING SWAN VALLEY PCB B-1675 AND 115KV AUX BUS | SWAN VALLEY: PCB B-1675, SWAN VALLEY - TETON #2 115KV LINE INCLUDING SWAN VALLEY PCB B-1675 AND 115KV AUX BUS, SWAN VALLEY: 115KV AUX BUS, SWAN VALLEY-TETON NO 2 115KV LINE, TETON: PCB B-1670 | SEIL, GEN
251 | 23-05508 | 13160642 | 04/27/2023 08:00 | 04/27/2023 15:00 | KEELER: PCB A-899 | KEELER: PCB A-899 | SOA, SIG
252 | 23-05274 | 13141408 | 04/27/2023 08:00 | 04/27/2023 12:00 | TRENTWOOD: PCB B-1935 INCLUDING 115KV CAP GROUP 1 SECTIONS 1 AND 2, PCB B-1937, PCB B-1938 AND 115KV REACTIVE BUS | TRENTWOOD: 115KV CAP GROUP 1 SECTION 2, TRENTWOOD: PCB B-1935 INCLUDING 115KV CAP GROUP 1 SECTIONS 1 AND 2, PCB B-1937, PCB B-1938 AND 115KV REACTIVE BUS, TRENTWOOD: 115KV CAP GROUP 1 SECTION 1, TRENTWOOD: PCB B-1937, TRENTWOOD: PCB B-1938, TRENTWOOD: 115KV REACTIVE BUS, TRENTWOOD: PCB B-1935 | LOAD
253 | 23-05214 | 13095446 | 04/27/2023 08:00 | 04/28/2023 18:00 | SCL - BOTHELL: 240KV BUS 2 (BOTHEL-SAMMAMISH, DIABLO-BOTHELL AND BANK 62) | SCL - BOTHELL: 240KV BUS 2 (BOTHEL-SAMMAMISH, DIABLO-BOTHELL AND BANK 62) | SOC, NOEL
254 | 23-01336 | 12690663 | 04/27/2023 08:00 | 04/27/2023 16:00 | GRIZZLY-PGE ROUND BUTTE NO 1 500KV LINE | GRIZZLY-PGE ROUND BUTTE NO 1 500KV LINE | NWACI, PDCI, SIG, COI
255 | 23-01374 | 12690752 | 04/27/2023 09:00 | 04/27/2023 10:00 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 | GEN, NOH, WOCN
256 | 23-01375 | 12690801 | 04/27/2023 10:00 | 04/27/2023 11:00 | GRAND COULEE: PCB 2092, GRAND COULEE: PCB 2096 | GRAND COULEE: PCB 2092, GRAND COULEE: PCB 2096 | GEN, NOH, WOCN
257 | 23-01376 | 12690942 | 04/27/2023 11:00 | 04/27/2023 12:00 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 | GEN, NOH, WOCN
258 | 23-04210 | 13032081 | 04/27/2023 12:00 | 04/27/2023 13:00 | ROSS: PCB A-24 | ROSS: PCB A-24 | SOA
259 | 23-01377 | 12691317 | 04/27/2023 13:30 | 04/27/2023 14:30 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 | GEN, NOH, WOCN
260 | 23-01002 | 12495566 | 04/27/2023 14:00 | 04/27/2023 15:00 | BIG EDDY: PCB B-1050 OF THE DALLES PH-BIG EDDY NO 2 115KV LINE | BIG EDDY: 115/13.2KV TRANSFORMER 8, BIG EDDY: PCB B-1050 OF THE DALLES PH-BIG EDDY NO 2 115KV LINE, THE DALLES PH-BIG EDDY NO 2 115KV LINE | GEN, FCRPS
261 | 23-01379 | 12691326 | 04/27/2023 14:30 | 04/27/2023 15:30 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 | GEN, NOH, WOCN
262 | 23-03202 | 12976954 | 04/27/2023 21:00 | 04/28/2023 01:30 | LIBBY-TRUMBULL CREEK SECTION OF THE LIBBY-CONKELLEY #1 230KV LINE INCLUDING HASKILL TAP | HASKILL: FLATHEAD E COOP 230KV FEEDER 1, LIBBY-TRUMBULL CREEK SECTION OF THE LIBBY-CONKELLEY #1 230KV LINE INCLUDING HASKILL TAP, HASKILL-TRUMBULL CREEK SECTION OF LIBBY-CONKELLEY NO 1 230KV LINE, HASKILL TAP TO LIBBY-CONKELLEY NO 1 230KV LINE, LIBBY-HASKILL SECTION OF LIBBY-CONKELLEY NO 1 230KV LINE | MT-NW, GEN
263 | 23-01849 | 13038595 | 04/28/2023 08:00 | 04/29/2023 15:00 | CHANDLER-ACORD SECTION OF GRANDVIEW-RED MOUNTAIN NO 1 115KV LINE | CHANDLER-ACORD SECTION OF GRANDVIEW-RED MOUNTAIN NO 1 115KV LINE | GEN, TCLA, LOAD
264 | 23-01345 | 12690748 | 04/28/2023 08:00 | 04/28/2023 16:00 | JOHN DAY-GRIZZLY NO 1 500KV LINE, BAKEOVEN: JOHN DAY-GRIZZLY 1 500KV LINE SERIES CAP GROUP 1 | JOHN DAY-GRIZZLY NO 1 500KV LINE, BAKEOVEN: JOHN DAY-GRIZZLY 1 500KV LINE SERIES CAP GROUP 1 | BCHT, BCHW, NI, NWACI, PDCI, SIG, WOJD, COI
265 | 23-05215 | 13095515 | 04/28/2023 18:01 | 04/29/2023 18:00 | SCL - BOTHELL: 120KV BUS B (240/120KV BANK 62, BOTHELL-NORTH & BOTHELL-SHORELINE 120KV LINES) | SCL - BOTHELL: 120KV BUS B (240/120KV BANK 62, BOTHELL-NORTH & BOTHELL-SHORELINE 120KV LINES) | SOC, NOEL