## Request List
Row | Request# | CAISO# | Start | End | Main Element Impacted | Path Affected
1 | 21-01711 | 9741845 | 02/03/2021 09:00 | 02/28/2023 17:00 | -USBR- GRAND COULEE 287/230KV TRANSFORMER KX-17-A (OLYMPIA-GRAND COULEE NO 1 287KV LINE OPERATING AT 230KV) | NOEL, PA, RP, SOC, WOCN, IROL, NOH, OKLA
2 | 21-01581 |  | 04/30/2021 16:15 | 03/31/2023 18:00 | BCH - BURRARD SYNCHRONOUS CONDENSER STATION G2 | BCHT, BCHW, NI
3 | 21-01767 | 10359382 | 06/30/2021 10:00 | 02/03/2023 16:00 | PAUL: 4805 TERMINAL OF PAUL-PSE TONO NO 1 500KV LINE | LOAD, RP, SIG, PA
4 | 22-07563 | 12651099 | 06/01/2022 00:01 | 05/31/2023 23:59 | COVINGTON: 500/230KV TRANSFORMER 4, DERATED | NOEL, RP, SIG, SOC, NI, WOCN
5 | 22-07562 | 12651113 | 06/01/2022 00:01 | 05/31/2023 23:59 | COVINGTON: 500/230KV TRANSFORMER 5, DERATED | NOEL, RP, SIG, SOC, NI, WOCN
6 | 22-13128 | 12651062 | 08/17/2022 08:00 | 05/31/2023 23:59 | MAPLE VALLEY: 500/230KV TRANSFORMER 2, (DERATED) | IROL, NOEL, SIG, SOC, WOCN
7 | 22-15672 | 12565152 | 10/24/2022 08:00 | 03/24/2023 16:00 | -CLARK PUD- 115KV PIONEER-CLARK SECTION OF PIONEER-ALCOA NO 1 115KV LINE
8 | 22-16303 | 12637747 | 10/31/2022 00:00 | 03/17/2023 23:59 | ABERDEEN TAP TO SATSOP PARK-COSMOPOLIS NO 1 115KV LINE, -DERATE- | PA, RP
9 | 22-16301 | 12637406 | 10/31/2022 00:00 | 03/17/2023 23:59 | MARTIN CREEK-DRAIN NO 1 115KV LINE, -DERATE- | EWEB, SLAL
10 | 22-16300 | 12637365 | 10/31/2022 00:00 | 03/17/2023 23:59 | OAKRIDGE-LOOKOUT POINT SECTION OF HILLS CREEK-LOOKOUT POINT NO 1 115KV LINE, -DERATE-
11 | 22-15846 | 12589097 | 10/31/2022 00:00 | 03/31/2023 23:59 | SATSOP PARK-ABERDEEN TAP SECTION OF SATSOP PARK-COSMOPOLIS NO 1 115KV LINE, -DERATE- | PA
12 | 22-15848 | 12589036 | 10/31/2022 00:00 | 03/31/2023 23:59 | SOUTH ELMA-SATSOP PARK NO 1 115KV LINE, -DERATE- | LOAD, PA, SOA
13 | 22-15952 | 12589118 | 11/01/2022 00:00 | 03/31/2023 23:59 | ABERDEEN TAP-COSMOPOLIS SECTION OF SATSOP PARK-COSMOPOLIS NO 1 115KV LINE, -DERATE- | PA, RP
14 | 22-16316 | 12660845 | 11/01/2022 00:00 | 03/17/2023 23:59 | BOUNDARY-SACHEEN NO 1 230KV LINE, -DERATE-
15 | 22-16315 | 12638803 | 11/01/2022 00:00 | 03/17/2023 23:59 | DAY MT SPOKANE-BELL SECTION OF SACHEEN-BELL NO 1 230KV LINE, -DERATE- | SOB
16 | 22-16262 | 12632314 | 11/01/2022 00:00 | 03/31/2023 23:59 | OLYMPIA-SOUTH ELMA NO 1 115KV LINE, -DERATE- | LOAD, SI, PA, RP
17 | 22-16314 | 12638795 | 11/01/2022 00:00 | 03/17/2023 23:59 | SACHEEN-DAY MT SPOKANE SECTION OF SACHEEN-BELL NO 1 230KV LINE, -DERATE- | SOB
18 | 22-16468 | 12662365 | 11/02/2022 15:00 | 03/17/2023 23:58 | ABERDEEN: 230/115KV TRANSFORMER 4, -DERATE- | PA, LOAD
19 | 22-16471 | 12662371 | 11/02/2022 15:00 | 03/17/2023 23:58 | ABERDEEN: 230/115KV TRANSFORMER 5, -DERATE- | PA, LOAD
20 | 22-16463 | 12662288 | 11/02/2022 15:00 | 03/17/2023 23:58 | BENTON-RINGOLD SECTION OF BENTON-SCOOTENEY NO 1 115KV LINE, -DERATE- | TCLA
21 | 22-16460 | 12662216 | 11/02/2022 15:00 | 03/17/2023 23:58 | CONNELL-SCOOTENEY SECTION OF BENTON-SCOOTENEY NO 1 115KV LINE, -DERATE- | TCLA
22 | 22-16466 | 12662359 | 11/02/2022 15:00 | 03/17/2023 23:58 | DIXON-RATTLESNAKE SECTION OF HOT SPRINGS-RATTLESNAKE NO 1 230KV LINE | MT-NW
23 | 22-16461 | 12662227 | 11/02/2022 15:00 | 03/17/2023 23:58 | MESA-CONNELL SECTION OF BENTON-SCOOTENEY NO 1 115KV LINE, -DERATE- | TCLA
24 | 22-16462 | 12662245 | 11/02/2022 15:00 | 03/17/2023 23:58 | RINGOLD-MESA SECTION OF BENTON-SCOOTENEY NO 1 115KV LINE, -DERATE- | TCLA
25 | 23-01570 | 12684663 | 01/02/2023 16:00 | 02/25/2023 15:00 | JOHN DAY: PCB 4134, INCLUDING MOD 4133 | NWACI, PDCI, WOJD, COI
26 | 23-00057 | 11238963 | 01/09/2023 18:00 | 03/02/2023 07:30 | HANFORD: PCB 4083 INCLUDING MODS 4082 & 4084 | NOH, NWACI, PDCI, WOM, WOS
27 | 22-06014 | 11537545 | 01/16/2023 08:00 | 03/03/2023 17:00 | GRIZZLY: 500KV REACTOR 3 INCLUDING PCB 4038 | COI, NWACI, PDCI, COI, PDCI, NWACI
28 | 23-00104 |  | 01/16/2023 09:00 | 02/17/2023 19:00 | -IPC- HINES-WEST JOHN DAY(IPC) LINE
29 | 23-01125 | 12532739 | 01/23/2023 08:00 | 02/03/2023 16:00 | -PGE- MURRAYHILL- SHERWOOD NO 1 & 2 230KV LINES | SOA
30 | 23-00536 | 12289754 | 01/30/2023 07:00 | 02/02/2023 16:00 | GARRISON: BROADVIEW 1 500KV LINE SERIES CAP GROUP 1 INCLUDING PCB 4469 | MT-NW
31 | 23-01057 | 12522022 | 01/30/2023 08:00 | 02/03/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
32 | 23-00382 | 12182225 | 01/30/2023 08:00 | 02/02/2023 16:00 | LOWER GRANITE: PCB 4776 | MT-NW, WOH, WOLM, GEN
33 | 22-07006 | 11705524 | 01/30/2023 08:30 | 02/03/2023 15:00 | LOWER MONUMENTAL 500KV WEST BUS INCLUDING LOWER MONUMENTAL PH #1 500KV LINE STUB BUS AND MOD 4343 | GEN, WOLM
34 | 23-01107 | 12570115 | 01/30/2023 14:00 | 02/23/2023 08:30 | LONGVIEW: PCB A-106 INCLUDING 230/115KV TRANSFORMER #3 AND 230KV SOUTH AUX BUS | SOA, PA, LOAD
35 | 23-00922 | 12522022 | 02/01/2023 07:00 | 02/01/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
36 | 23-01073 | 12555627 | 02/01/2023 07:30 | 02/02/2023 15:00 | MARION: PCB 4946 | NWACI, PDCI, COI
37 | 23-00289 | 12118978 | 02/01/2023 08:00 | 02/01/2023 16:00 | WAUTOMA: 500KV REACTOR 1, INCLUDING PCB 5236 | COI, NWACI
38 | 23-00923 | 12522022 | 02/02/2023 07:00 | 02/02/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
39 | 23-00799 | 12425655 | 02/02/2023 08:00 | 02/02/2023 16:00 | SANTIAM: 230KV REACTIVE GROUP 1 REACTOR 1 INCLUDING PCB A-504 | COI, PDCI, NWACI
40 | 23-00492 | 12220299 | 02/02/2023 10:15 | 02/02/2023 10:45 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 | GEN, NOH, WOCN
41 | 23-00493 | 12220312 | 02/02/2023 11:15 | 02/02/2023 11:45 | GRAND COULEE: PCB 2092, GRAND COULEE: PCB 2096 | GEN, NOH, WOCN
42 | 23-00883 | 12555637 | 02/02/2023 12:45 | 02/02/2023 13:15 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 | GEN, NOH, WOCN
43 | 23-00495 | 12220321 | 02/02/2023 13:45 | 02/02/2023 14:15 | GRAND COULEE: PCB 2292, GRAND COULEE: PCB 2296 | GEN, NOH, WOCN
44 | 23-00496 | 12220329 | 02/02/2023 14:45 | 02/02/2023 15:15 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 | GEN, NOH, WOCN
45 | 23-00924 | 12522022 | 02/03/2023 07:00 | 02/03/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
46 | 23-00537 | 12289768 | 02/06/2023 07:00 | 02/09/2023 16:00 | GARRISON: 500KV REACTOR 5 INCLUDING PCB 4362 | MT-NW
47 | 23-00925 | 12525487 | 02/06/2023 07:00 | 02/06/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
48 | 23-00452 | 12212811 | 02/06/2023 07:00 | 02/09/2023 16:00 | MCNARY: PCB 5199 BFR & BKR DIFFERNTIAL RELAYS | WOM, WOS, COI, NWACI, PDCI
49 | 23-00409 | 12150171 | 02/06/2023 07:00 | 02/09/2023 15:00 | RAVER: PCB 4314 | NOEL, RP, SOC, WOCN
50 | 23-01341 | 12638938 | 02/06/2023 07:00 | 02/06/2023 07:30 | THE DALLES PH-BIG EDDY NO 6 230KV LINE | GEN, FCRPS
51 | 23-00614 | 12347289 | 02/06/2023 08:00 | 02/16/2023 15:00 | BELL: PCB 5313, BFR | MT-NW, WOH
52 | 23-00614 | 12347289 | 02/06/2023 08:00 | 02/16/2023 15:00 | BELL: PCB 5313, BFR | MT-NW, WOH
53 | 23-01062 | 12525487 | 02/06/2023 08:00 | 02/10/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
54 | 23-00383 | 12191949 | 02/06/2023 08:00 | 02/09/2023 16:00 | LOWER GRANITE: PCB 4775, BFR | MT-NW, WOH, WOLM, GEN
55 | 23-00392 |  | 02/06/2023 08:00 | 03/20/2023 18:00 | SCL - BROAD ST 115KV BUS 2 (BROAD ST-UNION TAP , MASSACHUSETTS ST-UNION TAP, UNION ST-UNION ST TAP 115KV CALBES & BROAD ST BANKS 66A & B) | SOC, NOEL
56 | 23-00926 | 12525487 | 02/07/2023 07:00 | 02/07/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
57 | 23-00927 | 12525487 | 02/08/2023 07:00 | 02/08/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
58 | 23-00749 | 12604441 | 02/08/2023 08:00 | 02/08/2023 15:00 | ASHE: PCB A-892 including Cap Grp 2 | COI, NOH, PDCI, TCLA, NWACI
59 | 23-00928 | 12525487 | 02/09/2023 07:00 | 02/09/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
60 | 23-00366 | 12101554 | 02/09/2023 09:00 | 02/09/2023 10:30 | JOHN DAY: PCB 4191 | NWACI, PDCI, WOJD, WOM, COI
61 | 23-00367 | 12101567 | 02/09/2023 10:30 | 02/09/2023 12:00 | JOHN DAY: PCB 4194 | NOH, NWACI, PDCI, WOJD, COI
62 | 23-00929 | 12525487 | 02/10/2023 07:00 | 02/10/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
63 | 22-01168 | 9556188 | 02/13/2023 06:30 | 03/05/2023 23:00 | GRAND COULEE: PCB 2192, PCB 2196 | GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI
64 | 23-00930 | 12525527 | 02/13/2023 07:00 | 02/13/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
65 | 23-00410 | 12150250 | 02/13/2023 07:00 | 02/14/2023 16:00 | RAVER: PCB 4914 | NOEL, RP, SOC
66 | 23-01063 | 12525527 | 02/13/2023 08:00 | 02/17/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
67 | 22-10920 | 12118026 | 02/13/2023 08:00 | 02/14/2023 15:00 | ROCK CREEK: PCB 5288, BFR | RKCR
68 | 23-00857 | 12622634 | 02/13/2023 08:30 | 02/16/2023 14:30 | CAPTAIN JACK: PCB 4986 | NWACI, PDCI, COI
69 | 23-00931 | 12525527 | 02/14/2023 07:00 | 02/14/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
70 | 23-00932 | 12525527 | 02/15/2023 07:00 | 02/15/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
71 | 22-10923 | 12118029 | 02/15/2023 08:00 | 02/16/2023 15:00 | ROCK CREEK: PCB 5294, BFR | RKCR
72 | 23-01203 | 12593867 | 02/16/2023 07:00 | 02/16/2023 10:00 | GARRISON: PCB 4415 | MT-NW
73 | 23-00933 | 12525527 | 02/16/2023 07:00 | 02/16/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
74 | 23-01204 | 12593870 | 02/16/2023 10:00 | 02/16/2023 15:00 | GARRISON: PCB 4418 | MT-NW
75 | 23-00497 | 12231943 | 02/16/2023 10:15 | 02/16/2023 10:45 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 | GEN, NOH, WOCN
76 | 22-15346 | 12532935 | 02/16/2023 11:00 | 02/16/2023 13:00 | MARION: PCB 4374 | NWACI, PDCI, COI
77 | 23-00498 | 12231948 | 02/16/2023 11:15 | 02/16/2023 11:45 | GRAND COULEE: PCB 2092, GRAND COULEE: PCB 2096 | GEN, NOH, WOCN
78 | 23-01343 | 12638964 | 02/16/2023 12:00 | 02/16/2023 12:30 | THE DALLES PH-BIG EDDY NO 6 230KV LINE | GEN, FCRPS
79 | 23-00884 | 12569980 | 02/16/2023 12:45 | 02/16/2023 13:15 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 | GEN, NOH, WOCN
80 | 22-15426 | 12650589 | 02/16/2023 13:00 | 02/16/2023 15:00 | MARION: PCB 4377 | NWACI, PDCI, COI
81 | 23-00500 | 12231956 | 02/16/2023 13:45 | 02/16/2023 14:15 | GRAND COULEE: PCB 2292, GRAND COULEE: PCB 2296 | GEN, NOH, WOCN
82 | 23-00501 | 12232006 | 02/16/2023 14:45 | 02/16/2023 15:15 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 | GEN, NOH, WOCN
83 | 23-00934 | 12525527 | 02/17/2023 07:00 | 02/17/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
84 | 23-00103 |  | 02/18/2023 09:00 | 03/31/2023 18:30 | -IPC- QUARTZ-WEST JOHN DAY(IPC) LINE
85 | 23-00935 | 12525570 | 02/20/2023 07:00 | 02/20/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
86 | 23-00615 | 12347620 | 02/20/2023 08:00 | 03/02/2023 15:00 | BELL: PCB 5316, BFR | MT-NW, WOH
87 | 23-00615 | 12347620 | 02/20/2023 08:00 | 03/02/2023 15:00 | BELL: PCB 5316, BFR | MT-NW, WOH
88 | 23-00615 | 12347620 | 02/20/2023 08:00 | 03/02/2023 15:00 | BELL: PCB 5316, BFR | MT-NW, WOH
89 | 23-01064 | 12525570 | 02/20/2023 08:00 | 02/24/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
90 | 23-00687 | 12413295 | 02/20/2023 08:00 | 02/21/2023 16:00 | VANTAGE: PCB 5339, BFR | NOH
91 | 23-00936 | 12525570 | 02/21/2023 07:00 | 02/21/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
92 | 22-13271 | 12288587 | 02/21/2023 08:00 | 02/21/2023 16:00 | COWLITZ: PCB B-344 INCLUDING THE 7TH AVENUE-COWLTIZ NO 1 115KV LINE | LOAD, SOA
93 | 23-00937 | 12525570 | 02/22/2023 07:00 | 02/22/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
94 | 22-11723 | 12533035 | 02/22/2023 07:00 | 02/22/2023 16:00 | WHITE BLUFFS-451B NO 1 115KV LINE INCLUDING WHITE BLUFFS: 115KV AUXILIARY BUS AND PCBs B-215, B-263, B-1362 AND 115KV CAP GROUP NO 1 | GEN, TCLA, LOAD
95 | 23-00689 | 12413303 | 02/22/2023 08:00 | 02/23/2023 16:00 | VANTAGE: PCB 5345, BFR | NOH
96 | 22-13710 | 12533038 | 02/23/2023 07:00 | 02/23/2023 16:00 | BENTON-WHITE BLUFFS NO 1 AND THE WHITE BLUFFS-SAND HILL CRANE SECTION OF THE WHITE BLUFFS-RICHLAND NO 1 115KV LINES INCLUDING THE WHITE BLUFFS 115KV AUXILIARY BUS AND WHITE BLUFFS PCBs B-271 AND B-1911 | TCLA
97 | 23-01205 | 12593920 | 02/23/2023 07:00 | 02/23/2023 10:00 | GARRISON: PCB 4463 | MT-NW
98 | 23-00938 | 12525570 | 02/23/2023 07:00 | 02/23/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
99 | 23-01164 | 12662352 | 02/23/2023 08:30 | 02/23/2023 17:00 | LONGVIEW: 230KV SOUTH MAIN BUS INCLUDING PCB'S A-106 AND A-98 | SOA, PA, LOAD
100 | 23-01206 | 12593883 | 02/23/2023 10:00 | 02/23/2023 15:00 | GARRISON: PCB 4360 | MT-NW
101 | 23-00939 | 12525570 | 02/24/2023 07:00 | 02/24/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
102 | 23-01571 | 12684681 | 02/25/2023 08:00 | 02/25/2023 15:00 | JOHN DAY-GRIZZLY NO 2 500KV LINE, INCLUDING JOHN DAY PCB 4134 AND BAKEOVEN: 500KV SERIES CAP GROUP 2 - UNGROUNDED | BCHT, BCHW, NI, NWACI, PDCI, SIG, WOJD, COI
103 | 23-00940 | 12525767 | 02/27/2023 07:00 | 02/27/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
104 | 23-01540 | 12666585 | 02/27/2023 07:00 | 02/27/2023 17:00 | LEXINGTON: PCB B-1468 INCLUDING THE 115KV AUX BUS AND THE LEXINGTON-PACIFIC WAY SECTION OF THE LEXINGTON-LONGVIEW NO 1 115KV LINE | LOAD, SOA
105 | 23-00477 | 12220033 | 02/27/2023 07:00 | 02/28/2023 16:00 | PAUL: PCB 4810 | PA, RP
106 | 23-00416 | 12150227 | 02/27/2023 07:00 | 03/02/2023 16:00 | RAVER: PCB 4876 | NOEL, RP, SOC
107 | 23-01465 | 12662660 | 02/27/2023 07:30 | 03/23/2023 08:30 | LONGVIEW: PCB A-98 INCLUDING LONGVIEW-CHEMICAL #1 230KV LINE AND 230KV SOUTH AUX BUS | SOA
108 | 23-01074 | 12570188 | 02/27/2023 07:30 | 02/28/2023 15:00 | MARION: PCB 4383 | NWACI, PDCI, COI
109 | 23-00266 | 12105207 | 02/27/2023 08:00 | 03/02/2023 15:00 | CHIEF JOSEPH: PCB 4728 BFR | NOEL, NOH, NWACI, PDCI, SOC, WOCN, COI
110 | 23-01066 | 12525767 | 02/27/2023 08:00 | 03/03/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
111 | 23-00225 | 11873003 | 02/27/2023 08:00 | 03/01/2023 15:00 | HILLTOP: PCB A-1539 INCLUDING 230KV REACTOR 1 | COI, PDCI, RATS, NWACI
112 | 23-00384 | 12192013 | 02/27/2023 08:00 | 03/02/2023 16:00 | LOWER GRANITE: PCB 4772, BFR | GEN, MT-NW, WOH, WOLM
113 | 23-00829 | 12460906 | 02/27/2023 08:00 | 03/02/2023 16:00 | PEARL: 230KV MAIN BUS SECTIONALIZING PCB A-1192 | SOA
114 | 23-00690 | 12413308 | 02/27/2023 08:00 | 02/28/2023 16:00 | VANTAGE: PCB 5342, BFR | NOH
115 | 23-00941 | 12525767 | 02/28/2023 07:00 | 02/28/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
116 | 23-00942 | 12525767 | 03/01/2023 07:00 | 03/01/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
117 | 23-00691 | 12570333 | 03/01/2023 08:00 | 03/02/2023 16:00 | VANTAGE: PCB 5351, BFR | NOH
118 | 23-00546 | 12269462 | 03/01/2023 21:00 | 03/02/2023 06:00 | Ringold to B-301 section of the Benton Scooteney No 1 115 Kv line including Mesa Tap and Mesa 115Kv and 13.8 kv Busses | TCLA
119 | 23-00943 | 12525767 | 03/02/2023 07:00 | 03/02/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
120 | 23-00058 | 11238985 | 03/02/2023 07:30 | 03/02/2023 16:00 | GRAND COULEE-HANFORD NO 1 500KV LINE, INCLUDING HANFORD PCB 4083 | NOH, NWACI, PDCI, WOM, WOS, BCHT, BCHW, GEN, NI, SIG, COI, WOCN
121 | 23-00596 | 12346005 | 03/02/2023 08:00 | 03/02/2023 15:00 | BELL-AVA BEACON NO 5 230KV LINE INCLUDING BELL PCB A-570 | WOH, MT-NW
122 | 23-01080 | 12570175 | 03/02/2023 08:00 | 03/02/2023 10:00 | MARION: PCB 4386 | NWACI, PDCI, WOCS, COI
123 | 23-00795 | 12489468 | 03/02/2023 08:00 | 03/02/2023 16:00 | SANTIAM: 230KV EAST MAIN BUS | COI, PDCI, NWACI, GEN, FCRPS, WOCS, SWORE, SIG
124 | 23-01124 | 12570184 | 03/02/2023 10:00 | 03/02/2023 12:00 | MARION: PCB 4389 | NWACI, PDCI, WOCS, COI
125 | 23-00502 | 12232085 | 03/02/2023 10:15 | 03/02/2023 10:45 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 | GEN, NOH, WOCN
126 | 23-00503 | 12232259 | 03/02/2023 11:15 | 03/02/2023 11:45 | GRAND COULEE: PCB 2092, GRAND COULEE: PCB 2096 | GEN, NOH, WOCN
127 | 23-00504 | 12289796 | 03/02/2023 12:45 | 03/02/2023 13:15 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 | GEN, NOH, WOCN
128 | 23-00505 | 12289968 | 03/02/2023 13:45 | 03/02/2023 14:15 | GRAND COULEE: PCB 2292, GRAND COULEE: PCB 2296 | GEN, NOH, WOCN
129 | 23-00506 | 12290117 | 03/02/2023 14:45 | 03/02/2023 15:15 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 | GEN, NOH, WOCN
130 | 23-00885 | 12570341 | 03/02/2023 15:45 | 03/02/2023 16:15 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 | GEN, NOH, WOCN
131 | 23-00944 | 12525767 | 03/03/2023 07:00 | 03/03/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
132 | 23-00059 | 11239058 | 03/03/2023 07:30 | 03/03/2023 16:00 | HANFORD: 500KV SOUTH BUS INCLUDING PCB 4083 | COI, NOH, NWACI, PDCI, WOS, WOM
133 | 23-00075 | 11220278 | 03/04/2023 07:00 | 03/05/2023 23:59 | RAS - DITTMER: RAS AC-A CONTROLLER, MUNRO: RAS AC-B CONTROLLER, RAS SYNCHROPHASOR-A CONTROLLER, RAS SYNCHROPHASOR-B CONTROLLER, MALIN FACRI A AND B | SIG, COI, NOH, NWACI, PDCI, WOM, WOS, SIG, COI, NOH, NWACI, PDCI, WOM, WOS
134 | 23-00775 | 12536976 | 03/06/2023 06:30 | 03/10/2023 17:30 | WAUTOMA: 500KV EAST BUS INCLUDING 500KV REACTOR 1 AND PCB 5236 | WOCN, NWACI, COI
135 | 23-00945 | 12525803 | 03/06/2023 07:00 | 03/06/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
136 | 23-00526 | 12231513 | 03/06/2023 07:00 | 03/07/2023 16:00 | RAVER: PCB 4293 | NOEL, RP, SOC, WOCN
137 | 23-01075 | 12570350 | 03/06/2023 07:30 | 03/07/2023 15:00 | MARION: PCB 4368 | NWACI, PDCI, WOCS, COI
138 | 23-00434 | 12156053 | 03/06/2023 08:00 | 03/08/2023 15:00 | BIG EDDY: PCB 4860 | NWACI, PDCI, WOJD, COI, BGEDY
139 | 23-00226 | 12105220 | 03/06/2023 08:00 | 03/09/2023 15:00 | CAPTAIN JACK: OLINDA 1 500KV LINE SERIES CAP GROUP 1 | NWACI, PDCI, COI
140 | 22-12274 | 12192488 | 03/06/2023 08:00 | 03/31/2023 16:00 | GRIZZLY: PCB 5040 | NWACI, WOJD, COI
141 | 23-01067 | 12525803 | 03/06/2023 08:00 | 03/10/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
142 | 22-12601 | 12212487 | 03/06/2023 08:00 | 03/09/2023 15:00 | KEELER: PCB 4394 | SOA
143 | 23-00386 | 12191969 | 03/06/2023 08:00 | 03/09/2023 16:00 | LOWER GRANITE: PCB 4770 | GEN, MT-NW, NOH, WOH, WOLM
144 | 23-00402 | 12143727 | 03/06/2023 08:00 | 04/06/2023 15:00 | MIDWAY: 115KV EAST MAIN BUS INCLUDING MIDWAY 115KV AUX BUS, PCB B-146 AND MIDWAY-RATTLESNAKE SECTION OF MIDWAY-MOXEE NO 1 115KV LINE | TCLA, LOAD
145 | 23-00802 | 12570453 | 03/06/2023 08:00 | 03/09/2023 16:00 | PEARL: PCB 4283 | SOA
146 | 23-00762 | 12650724 | 03/07/2023 07:00 | 03/07/2023 16:00 | ASHE: 500KV NORTH BUS INCLUDING PCBS 4940, 4888, 4901 | NWACI, WOCS, WOJD, WOM, COI, FCRPS, GEN, WOS, PDCI, NOH, WOLM
147 | 23-00344 | 12118360 | 03/07/2023 07:00 | 03/09/2023 16:00 | CAPTAIN JACK: PCB 4990 | NWACI, PDCI, COI
148 | 23-00946 | 12525803 | 03/07/2023 07:00 | 03/07/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
149 | 23-00456 | 12193450 | 03/07/2023 07:00 | 03/08/2023 15:30 | MONROE: PCB 4672, BFR AND DIFFERENTIAL RELAYS | BCHT, BCHW, NOEL, SOC, NI, WOCN
150 | 23-00764 | 12650869 | 03/08/2023 07:00 | 03/09/2023 16:00 | ASHE: 500KV SOUTH BUS, INCLUDING PCB'S 4937,4885,5463,4898,5324, 4909 & REACTOR #2 | NOH, NWACI, PDCI, COI, FCRPS, GEN
151 | 23-00947 | 12525803 | 03/08/2023 07:00 | 03/08/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
152 | 23-00480 | 12220059 | 03/08/2023 07:00 | 03/09/2023 16:00 | PAUL: PCB 4536 | RP, WOCS, SOA
153 | 23-00729 | 12537950 | 03/08/2023 07:30 | 03/08/2023 12:00 | CENTRAL FERRY: 500KV CAP GROUP 1, INCLUDING PCB 5430 | WOLM, WOH
154 | 23-01077 | 12570472 | 03/08/2023 07:30 | 03/09/2023 15:00 | MARION: PCB 4331 | NWACI, PDCI, COI, WOCS
155 | 23-00207 | 12118140 | 03/08/2023 09:00 | 03/09/2023 16:00 | FORT ROCK: GRIZZLY-CAPTAIN JACK 1 500KV LINE SERIES CAP GROUP 1 INCLUDING PCB 4265 | COI, NWACI, PDCI
156 | 23-00948 | 12525803 | 03/09/2023 07:00 | 03/09/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
157 | 23-00949 | 12525803 | 03/10/2023 07:00 | 03/10/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
158 | 23-01402 | 12691536 | 03/13/2023 06:00 | 05/25/2023 16:00 | HUNGRY HORSE PH: PCB 2182, HUNGRY HORSE PH: PCB 2382 | WOH
159 | 23-00231 | 11925518 | 03/13/2023 07:00 | 03/24/2023 14:00 | HAY MILL-ROE'S CORNER SECTION OF HEYBURN-ADELAIDE NO 1 138KV LINE | SEIL
160 | 22-14984 | 12594229 | 03/13/2023 07:00 | 03/17/2023 15:00 | LANE: 500/230KV TRANSFORMER 3 | NWACI, PDCI, SIG, COI
161 | 23-01215 | 12604369 | 03/13/2023 08:00 | 03/13/2023 10:00 | ASHE: 230KV CAP GROUP 1 | COI, NOH, PDCI, TCLA, NWACI
162 | 23-00736 | 12537427 | 03/13/2023 08:00 | 03/14/2023 15:00 | BELL: PCB 5301, BFR AND DIFFERENTIAL RELAY | MT-NW, WOH
163 | 23-01344 | 12667411 | 03/13/2023 08:00 | 03/31/2023 17:00 | GRANDVIEW-PROSSER SECTION OF GRANDVIEW-RED MOUNTAIN NO 1 115KV LINE | GEN, TCLA, LOAD
164 | 23-01068 | 12525849 | 03/13/2023 08:00 | 03/17/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
165 | 23-00950 | 12525849 | 03/13/2023 08:00 | 03/13/2023 16:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
166 | 23-00444 | 12182239 | 03/13/2023 08:00 | 03/15/2023 15:00 | JOHN DAY: PCB 4167 | JDAY, NWACI, WOCS, WOJD, COI
167 | 23-00105 | 11412380 | 03/13/2023 08:00 | 04/07/2023 16:00 | SANTIAM: PCB A-516 TERMINAL OF THE SANTIAM-PGE BETHEL NO 1 230KV LINE | COI, PDCI, NWACI, NWACI, PDCI, WOCS, COI, LOAD
168 | 23-00208 | 12118091 | 03/13/2023 09:00 | 03/16/2023 16:00 | FORT ROCK: GRIZZLY-SUMMER LAKE 1 500KV LINE SERIES CAP GROUP 3 INCLUDING PCB 5062 | COI, NWACI, PDCI
169 | 23-01216 | 12604373 | 03/13/2023 10:00 | 03/13/2023 12:00 | ASHE: 230KV CAP GROUP 2 | COI, NOH, PDCI, TCLA, NWACI
170 | 23-01051 | 12560155 | 03/13/2023 12:00 | 03/13/2023 15:00 | WHITE BLUFFS: 115KV CAP GROUP 1 | LOAD
171 | 23-01053 | 12570485 | 03/14/2023 07:30 | 03/14/2023 11:00 | HANFORD: 500KV CAP GROUP 1 | COI, NOH, PDCI, WOM, WOS, NWACI
172 | 23-00951 | 12525849 | 03/14/2023 08:00 | 03/14/2023 16:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
173 | 23-01272 | 12618666 | 03/14/2023 12:00 | 03/14/2023 14:00 | BENTON: 115KV CAP GROUP 1 | TCLA
174 | 23-00339 | 12117820 | 03/15/2023 07:00 | 03/16/2023 16:00 | CAPTAIN JACK: OLINDA 1 500KV LINE SERIES CAP GROUP 1, INCLUDING PCB'S 4971 & 4972 | NWACI, PDCI, COI
175 | 23-00265 | 12538047 | 03/15/2023 07:00 | 03/16/2023 16:00 | CRESTON: 115KV STRAIN BUS INCLUDING PCB B-437, PCB L-668, 115/34.5KV TRANSFORMER 1, THE CRESTON-EGYPT SECTION OF CRESTON-BELL NO 1 115KV LINE AND WILBUR-CRESTON SECTION OF GRAND COULEE-CRESTON NO 1 115KV LINE | LOAD
176 | 23-00737 | 12537431 | 03/15/2023 08:00 | 03/16/2023 15:00 | BELL: PCB 5304, BFR AND DIFFERENTIAL RELAY | MT-NW, WOH
177 | 23-00692 | 12538028 | 03/15/2023 08:00 | 03/15/2023 16:00 | CENTRAL FERRY: PCB 5388 | GEN, WOLM
178 | 23-00952 | 12525849 | 03/15/2023 08:00 | 03/15/2023 16:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
179 | 23-01056 | 12638456 | 03/16/2023 07:00 | 03/16/2023 09:00 | GRANDVIEW: 115KV CAP GROUP 1 | TCLA
180 | 23-00953 | 12525849 | 03/16/2023 08:00 | 03/16/2023 16:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
181 | 23-00507 | 12293387 | 03/16/2023 10:15 | 03/16/2023 10:45 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 | GEN, NOH, WOCN
182 | 23-00508 | 12293395 | 03/16/2023 11:15 | 03/16/2023 11:45 | GRAND COULEE: PCB 2092, GRAND COULEE: PCB 2096 | GEN, NOH, WOCN
183 | 23-00509 | 12293430 | 03/16/2023 12:30 | 03/16/2023 13:30 | GRAND COULEE: PCB 2292, GRAND COULEE: PCB 2296 | GEN, NOH, WOCN
184 | 23-00510 | 12293489 | 03/16/2023 13:45 | 03/16/2023 14:15 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 | GEN, NOH, WOCN
185 | 23-00886 | 12538133 | 03/16/2023 14:45 | 03/16/2023 15:15 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 | GEN, NOH, WOCN
186 | 23-00887 | 12570509 | 03/16/2023 15:45 | 03/16/2023 16:15 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 | GEN, NOH, WOCN
187 | 23-00954 | 12525849 | 03/17/2023 08:00 | 03/17/2023 16:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
188 | 23-00073 | 11220280 | 03/18/2023 07:00 | 03/19/2023 23:59 | RAS - DITTMER: RAS AC-A CONTROLLER, MUNRO: RAS AC-B CONTROLLER, RAS SYNCHROPHASOR-A CONTROLLER, RAS SYNCHROPHASOR-B CONTROLLER, MALIN FACRI A AND B | SIG, COI, NOH, NWACI, PDCI, WOM, WOS, SIG, COI, NOH, NWACI, PDCI, WOM, WOS
189 | 23-00206 | 11752207 | 03/20/2023 06:00 | 03/20/2023 17:00 | BELL: 230KV MAIN BUS SECT 4 INCLUDING 230KV MAIN BUS RING SECT AND PCBS A-377, A-571, A-573, A-574, AND A-577 | MT-NW, WOH, MT-NW, WOH, MT-NW, WOH, MT-NW, WOH, MT-NW, WOH, MT-NW, WOH, MT-NW, WOH, WOH
190 | 23-00014 | 11242211 | 03/20/2023 06:30 | 03/20/2023 12:00 | HANFORD-WAUTOMA NO 1 500KV LINE, INCLUDING HANFORD: PCB 4095 | NOH, NWACI, PDCI, SIG, COI, WOLM, WOM
191 | 23-00812 | 12638988 | 03/20/2023 08:00 | 03/20/2023 16:00 | CHEMAWA: PCB A-672 INCLUDING 230KV CAP GROUP 2 SECTION 1 | WOCS
192 | 23-00777 | 12649424 | 03/20/2023 08:00 | 03/22/2023 15:00 | COLVILLE: PCB B-1769 INCLUDING 115KV CAP GROUP 1 SECTIONS 1, 2, & 3 AND PCB'S B-1771, B-1773, & B-1780
193 | 23-01069 | 12525880 | 03/20/2023 08:00 | 03/24/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
194 | 23-00955 | 12525880 | 03/20/2023 08:00 | 03/20/2023 16:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
195 | 22-09483 | 12263920 | 03/20/2023 08:00 | 03/23/2023 17:00 | LAPINE: 230KV REACTOR 1 INCLUDING PCB A-1491 | COR
196 | 23-00010 | 11242214 | 03/20/2023 12:00 | 03/20/2023 17:30 | LOWER MONUMENTAL-HANFORD NO 1 500KV LINE, INCLUDING HANFORD: PCB 4095 | NOH, NWACI, PDCI, SIG, WOLM, COI, WOM
197 | 23-00011 | 11242268 | 03/20/2023 17:30 | 05/11/2023 07:30 | HANFORD: PCB 4095 INCLUDING MODS 4094 & 4096 | NWACI, PDCI, WOLM, COI, NOH, WOM
198 | 23-00152 | 11706375 | 03/21/2023 07:00 | 03/22/2023 17:00 | ASHE-HANFORD NO 1 500KV LINE | NOH, NWACI, PDCI, SIG, COI, NWACI, PDCI, COI, FCRPS, NWACI, PDCI, COI, FCRPS, NOH, NOH, NWACI, PDCI, COI, WOM, WOS, NWACI, PDCI, COI, NOH, WOM, WOS
199 | 23-00772 | 12538099 | 03/21/2023 07:00 | 03/22/2023 16:00 | CUSTER: 500KV REACTOR 1 INCLUDING PCB 4274 | NOEL, SOC, BCHT, BCHW, NI
200 | 23-00813 | 12638982 | 03/21/2023 08:00 | 03/21/2023 16:00 | CHEMAWA: PCB A-673 INCLUDING 230KV CAP GROUP 2 SECTION 2 | WOCS
201 | 23-00956 | 12525880 | 03/21/2023 08:00 | 03/21/2023 16:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
202 | 23-00340 | 12117971 | 03/21/2023 08:00 | 03/23/2023 16:00 | MALIN: PG&E ROUND MOUNTAIN 1 500KV LINE SERIES CAP GROUP, INCLUDING PCB'S 4188 & 4189 | COI, NWACI, PDCI
203 | 23-00394 | 12117839 | 03/21/2023 08:00 | 04/30/2023 18:00 | SCL - BROAD ST 115KV BUS 1 (UNIVERSITY-BROAD ST 115KV LINE AND BROAD ST BANKS 65A & B) | SOC, NOEL
204 | 23-00957 | 12525880 | 03/22/2023 08:00 | 03/22/2023 16:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
205 | 23-00778 | 12650797 | 03/23/2023 07:00 | 03/23/2023 15:00 | COLVILLE: 115KV MAIN BUS INCLUDING PCB'S B-1766, B-1768, B-1770, B-1769, B-1771, B-1773, & B-1780 AND 115KV CAP GROUP 1 SECTIONS 1, 2, & 3 | LOAD, SOB
206 | 23-00958 | 12525880 | 03/23/2023 08:00 | 03/23/2023 16:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
207 | 23-01511 | 12666211 | 03/23/2023 08:30 | 03/23/2023 16:00 | LONGVIEW: 230KV SOUTH MAIN BUS INCLUDING PCB A-98 | SOA, PA, LOAD
208 | 23-00151 | 11706378 | 03/24/2023 07:00 | 03/27/2023 17:00 | GRAND COULEE-HANFORD NO 1 500KV LINE | BCHT, BCHW, GEN, NI, NOH, SIG, COI, NWACI, PDCI, WOCN, NOH, NWACI, PDCI, WOM, WOS, NOH, NWACI, PDCI, COI, WOM, WOS, GEN, NOH, WOCN, COI, NWACI, PDCI, NOH, WOCN, COI, NWACI, PDCI
209 | 23-00959 | 12525880 | 03/24/2023 08:00 | 03/24/2023 16:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
210 | 23-00074 | 11220281 | 03/25/2023 07:00 | 03/26/2023 23:59 | RAS - DITTMER: RAS AC-A CONTROLLER, MUNRO: RAS AC-B CONTROLLER, RAS SYNCHROPHASOR-A CONTROLLER, RAS SYNCHROPHASOR-B CONTROLLER, MALIN FACRI A AND B (ALTERNATE TEST DATE) | SIG, COI, NOH, NWACI, PDCI, WOM, WOS, SIG, COI, NOH, NWACI, PDCI, WOM, WOS
211 | 23-00275 | 12118410 | 03/27/2023 08:00 | 03/30/2023 15:00 | CHIEF JOSEPH: PCB 4598, BFR | NOEL, SOC, WOCN
212 | 23-00530 | 12570534 | 03/27/2023 08:00 | 04/21/2023 16:00 | HANFORD-WAUTOMA NO 2 500KV LINE | NOH, NWACI, PDCI, SIG, COI
213 | 23-01070 | 12526123 | 03/27/2023 08:00 | 03/31/2023 15:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
214 | 23-00960 | 12526123 | 03/27/2023 08:00 | 03/27/2023 16:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
215 | 23-00150 | 11706397 | 03/28/2023 07:00 | 04/03/2023 17:00 | GRAND COULEE-SCHULTZ NO 1 500KV LINE | IROL, NOEL, NOH, NWACI, PDCI, SOC, WOCN, COI, GEN, SIG, FCRPS
216 | 23-00153 | 11706405 | 03/28/2023 07:00 | 04/03/2023 17:00 | GRAND COULEE-SCHULTZ NO 2 500KV LINE | IROL, NOEL, NOH, NWACI, PDCI, SOC, WOCN, COI, GEN, FCRPS, SIG
217 | 23-01076 | 12570537 | 03/28/2023 07:30 | 03/29/2023 15:00 | MARION: PCB 4371 | NWACI, PDCI, WOCS, COI
218 | 23-00771 | 12538009 | 03/28/2023 08:00 | 03/28/2023 16:00 | CENTRAL FERRY: 500KV CAP GROUP 1, INCLUDING PCB 5430 | WOLM, WOH
219 | 23-00961 | 12526123 | 03/28/2023 08:00 | 03/28/2023 16:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
220 | 23-00612 | 12538041 | 03/29/2023 07:30 | 03/29/2023 17:30 | COLUMBIA: GRAND COULEE-SCHULTZ 2 500KV LINE SERIES CAP GROUP 2, INCLUDING PCB 4693 | IROL, NOEL, NOH, NWACI, PDCI, SOC, WOCN, COI
221 | 23-00962 | 12526123 | 03/29/2023 08:00 | 03/29/2023 16:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
222 | 23-00827 | 12570546 | 03/29/2023 08:30 | 03/29/2023 16:00 | PEARL: PCB 5452 | SOA
223 | 23-00613 | 12537979 | 03/30/2023 08:00 | 03/30/2023 15:00 | COLUMBIA: GRAND COULEE-SCHULTZ 1 500KV LINE SERIES CAP GROUP 1, INCLUDING PCB 4694 | IROL, NOEL, NOH, NWACI, PDCI, SOC, WOCN, COI
224 | 23-01336 | 12690663 | 03/30/2023 08:00 | 03/30/2023 16:00 | GRIZZLY-PGE ROUND BUTTE NO 1 500KV LINE | NWACI, PDCI, SIG, COI
225 | 23-00963 | 12526123 | 03/30/2023 08:00 | 03/30/2023 16:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
226 | 23-00511 | 12293499 | 03/30/2023 10:15 | 03/30/2023 10:45 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 | GEN, NOH, WOCN
227 | 23-00512 | 12293522 | 03/30/2023 11:15 | 03/30/2023 11:45 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 | GEN, NOH, WOCN
228 | 23-00513 | 12218237 | 03/30/2023 12:45 | 03/30/2023 13:15 | GRAND COULEE: PCB 2292, GRAND COULEE: PCB 2296 | GEN, NOH, WOCN
229 | 23-00514 | 12293531 | 03/30/2023 13:45 | 03/30/2023 14:15 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 | GEN, NOH, WOCN
230 | 23-00515 | 12293558 | 03/30/2023 14:45 | 03/30/2023 15:15 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 | GEN, NOH, WOCN
231 | 23-00888 | 12538126 | 03/30/2023 15:45 | 03/30/2023 16:15 | GRAND COULEE: PCB 2092, GRAND COULEE: PCB 2096 | GEN, NOH, WOCN
232 | 23-01200 | 12691483 | 03/30/2023 22:30 | 03/31/2023 03:30 | WEST BURLEY-HEYBURN NO 1 138KV LINE
233 | 23-00964 | 12526123 | 03/31/2023 08:00 | 03/31/2023 16:00 | HATWAI: A-113 TERMINAL OF THE HATWAI-AVA MOSCOW NO 3 230KV LINE | WOH
234 | 23-01345 | 12690748 | 03/31/2023 08:00 | 03/31/2023 16:00 | JOHN DAY-GRIZZLY NO 1 500KV LINE, BAKEOVEN: JOHN DAY-GRIZZLY 1 500KV LINE SERIES CAP GROUP 1 | BCHT, BCHW, NI, NWACI, PDCI, SIG, WOJD, COI
235 | 23-00528 | 12252175 | 04/03/2023 08:00 | 04/28/2023 15:00 | BOARDMAN: 230/115KV TRANSFORMER 1 | GEN, LOAD, WOM, NWACI
236 | 23-00072 | 12595264 | 04/03/2023 08:00 | 04/20/2023 12:00 | HATWAI: 500/230KV TRANSFORMER 1 | ID-NW, MT-NW, NOH, WOH, WOLM
237 | 23-00445 | 12182162 | 04/03/2023 08:00 | 04/04/2023 16:00 | JOHN DAY-GRIZZLY NO 1 500KV LINE, INCLUDING GRIZZLY: PCB 4058 | BCHT, BCHW, NI, NWACI, PDCI, SIG, WOJD, COI
238 | 23-01435 | 12672724 | 04/03/2023 08:00 | 04/06/2023 16:00 | SANTIAM-TOLEDO NO 1 230KV LINE INCLUDING WREN TAP, WREN SUB, AND THE CPI 69KV FEEDER #1 | SWORE, LOAD
239 | 23-00111 | 11597532 | 04/03/2023 22:00 | 04/03/2023 22:30 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 | GEN, NOH, WOCN
240 | 22-01225 | 9562507 | 04/04/2023 06:30 | 04/04/2023 15:30 | CARLTON: 115KV MAIN BUS | LOAD, SOA
241 | 23-00237 | 12118506 | 04/04/2023 08:00 | 04/04/2023 15:00 | OSTRANDER: PCB 4448 | WOCS
242 | 23-00462 | 12289653 | 04/04/2023 22:00 | 05/16/2023 19:00 | GRAND COULEE: 500/230KV CSY TIE BANK, INCLUDING 500KV PCB'S 8692,1996 & 230KV PCB 6582 | GEN, NOH, WOCN, PDCI, SIG, COI, FCRPS, NWACI
243 | 23-00154 | 11756890 | 04/05/2023 07:00 | 04/06/2023 17:00 | GRAND COULEE-BELL NO 6 500KV LINE | GEN, MT-NW, SIG, WOH, COI, NOH, NWACI, PDCI, WOH, COI, NOH, NWACI, PDCI, WOCN, WOH, GEN, MT-NW, WOH, GEN, MT-NW, WOH, MT-NW, WOH, COI, NOH, NWACI, PDCI, WOCN, GEN, MT-NW, WOH, COI, NOH, NWACI, PDCI, WOCN
244 | 23-01409 | 12690849 | 04/05/2023 08:00 | 05/17/2023 16:00 | GRIZZLY: PCB 4058, GRIZZLY: MOD 4057 | NWACI, WOJD, COI
245 | 23-00828 | 12690883 | 04/05/2023 08:30 | 04/05/2023 16:00 | PEARL: PCB 5455 | SOA
246 | 23-00112 | 11597544 | 04/05/2023 17:30 | 04/05/2023 18:00 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 | GEN, NOH, WOCN
247 | 23-00155 | 11756897 | 04/07/2023 07:00 | 04/07/2023 17:00 | GRAND COULEE-CHIEF JOSEPH NO 3 500KV LINE | GEN, NOH, SIG, COI, FCRPS, MT-NW, NWACI, PDCI, WOCN, WOH, WOLM, GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOH, WOCN, COI, NWACI, PDCI, GEN, NOEL, NOH, NWACI, PDCI, SOC, WOCN, COI, GEN, NOH, NWACI, PDCI, COI, WOCN
248 | 23-00368 | 12107228 | 04/07/2023 22:00 | 04/08/2023 07:00 | GRANDVIEW-SNIPES SECTION OF THE GRANDVIEW-REDMOUNTAIN NO 1 115KV LINE INCLUDING THE PROSSER TAP | GEN, TCLA, LOAD, NWACI
249 | 23-00229 | 12118376 | 04/08/2023 07:00 | 06/02/2023 21:00 | PROSSER FROM REMOVED JUMPERS ON GRANDVIEW SIDE OF B-695 -SNIPES SECTION OF GRANDVIEW-RED MOUNTAIN NO 1 115KV LINE INCLUDING B-695, B-696, B-697 DISCONNECTS AND INCLUDING THE PROSSER TAP TO REMOVED JUMPERS ON FEEDER SIDE OF B-696 DISCONNECT | GEN, TCLA, LOAD
250 | 23-00156 | 11694133 | 04/10/2023 07:00 | 04/10/2023 17:00 | OLYMPIA-GRAND COULEE NO 1 287KV LINE | NOEL, NOH, RP, SOC, WOCN, IROL, NOEL, PA, RP, SOC, WOCN, NOH, WOCN, COI, NWACI, PDCI, NOH, OKLA, NOEL, PA, RP, SOC, WOCN, IROL
251 | 23-00859 | 12454457 | 04/10/2023 08:00 | 04/13/2023 17:00 | BIG EDDY-CHEMAWA NO 1 230KV LINE | NWACI, PDCI, WOCS, COI, WOJD
252 | 23-00213 | 12690973 | 04/10/2023 08:00 | 04/10/2023 16:00 | GRIZZLY: PCB 4720, GRIZZLY: 500KV REACTOR 2 | COI, NWACI, PDCI
253 | 23-00403 | 12143754 | 04/10/2023 08:00 | 04/21/2023 15:00 | RATTLESNAKE-MOXEE SECTION OF MIDWAY-MOXEE NO 1 115KV LINE | TCLA
254 | 23-00082 | 12691383 | 04/10/2023 08:00 | 04/14/2023 19:00 | REDMOND-PILOT BUTTE PACW NO 1 230KV LINE | NWACI, PDCI, COI, LOAD
255 | 23-00157 | 11756938 | 04/11/2023 07:00 | 04/11/2023 17:00 | SICKLER-SCHULTZ NO 1 500KV LINE | COI, IROL, NI, NOH, NWACI, PDCI, WOCN, CI, GEN, NOH, NWACI, WOCN, COI, BCHT, BCHW, CI, GEN, NOH, NWACI, PDCI, WOCN, COI, WOCN, WOCN
256 | 23-00847 | 12454621 | 04/11/2023 09:30 | 04/11/2023 11:00 | MCNARY: 230KV CAP GROUP #1 SECT 2 INCLUDING PCB A-3025 | LOAD
257 | 23-01273 | 12690615 | 04/12/2023 09:00 | 04/12/2023 11:00 | ECHO LAKE: PCB 5072 | BCHT, BCHW, NOEL, SOC, NI, WOCN
258 | 23-01128 | 12559952 | 04/12/2023 11:00 | 04/12/2023 12:00 | MORROW FLAT: 115KV CAP GROUP 1 INCLUDING PCB B-2251 | WOM
259 | 23-01275 | 12690650 | 04/12/2023 12:00 | 04/12/2023 14:00 | ECHO LAKE: PCB 5121 | BCHT, BCHW, NOEL, SOC, WOCN, NI
260 | 23-00158 | 11685280 | 04/13/2023 07:00 | 04/13/2023 16:00 | KELLER TAP TO GRAND COULEE-OKANOGAN NO 2 115KV LINE | LOAD, OKLA
261 | 23-00335 | 12118736 | 04/13/2023 08:00 | 04/13/2023 16:00 | CHIEF JOSEPH: PCB A-590, BFR | WOCN
262 | 23-00993 | 12690947 | 04/13/2023 08:00 | 04/13/2023 12:00 | JOHN DAY: PCB 4140 | NWACI, PDCI, WOJD, COI
263 | 23-01368 | 12690777 | 04/13/2023 09:00 | 04/13/2023 10:00 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 | GEN, NOH, WOCN
264 | 23-01369 | 12690929 | 04/13/2023 10:00 | 04/13/2023 11:00 | GRAND COULEE: PCB 2092, GRAND COULEE: PCB 2096 | GEN, NOH, WOCN
265 | 23-01370 | 12690950 | 04/13/2023 11:00 | 04/13/2023 12:00 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 | GEN, NOH, WOCN
266 | 23-00994 | 12690952 | 04/13/2023 12:00 | 04/13/2023 15:00 | JOHN DAY: PCB 4137 | NWACI, PDCI, WOJD, COI
267 | 23-01372 | 12691153 | 04/13/2023 12:30 | 04/13/2023 13:30 | GRAND COULEE: PCB 2292, GRAND COULEE: PCB 2296 | GEN, NOH, WOCN
268 | 23-01371 | 12691159 | 04/13/2023 13:30 | 04/13/2023 14:30 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 | GEN, NOH, WOCN
269 | 23-01373 | 12691166 | 04/13/2023 14:30 | 04/13/2023 15:30 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 | GEN, NOH, WOCN
270 | 23-01133 | 12584037 | 04/14/2023 07:30 | 04/14/2023 09:00 | JONES CANYON: 230KV CAP GROUP 1 SECTION 1 INCLUDING PCB A-1688 | WOCS
271 | 23-00159 | 11685399 | 04/14/2023 08:00 | 04/14/2023 15:00 | ICE HARBOR-FRANKLIN NO 1 115KV LINE | GEN, TCLA
272 | 23-00160 | 11688371 | 04/14/2023 08:00 | 04/14/2023 15:00 | ICE HARBOR-FRANKLIN NO 2 115KV LINE INCLUDING THE SACAJAWEA TAP | TCLA, TCLA, GEN, TCLA, FCRPS, LOAD
273 | 23-01134 | 12584045 | 04/14/2023 09:30 | 04/14/2023 11:00 | JONES CANYON: 230KV CAP GROUP 1 SECTION 2 INCLUDING PCB A-1689 | WOCS
274 | 23-00161 | 11756959 | 04/17/2023 07:00 | 04/18/2023 17:00 | WAUTOMA-KNIGHT NO 1 500KV LINE | BCHT, BCHW, NI, NOH, NWACI, PDCI, SIG, WOCN, WOCS, WOJD, COI, WOCN, WOCN, NWACI, PDCI, WOCN, WOCS, WOJD, NWACI, PDCI, WOCN, WOCS, WOJD, COI
275 | 23-01217 | 12667458 | 04/17/2023 07:30 | 04/20/2023 16:00 | ALLSTON-DRISCOLL NO 1 230KV LINE | LOAD, SOA
276 | 23-00739 | 12690366 | 04/17/2023 08:00 | 04/18/2023 15:00 | BELL: PCB 5307, BFR AND DIFFERENTIAL RELAY | MT-NW, WOH
277 | 23-00034 | 10044811 | 04/17/2023 08:00 | 04/21/2023 18:30 | PILOT BUTTE-LAPINE NO 1 230KV LINE | NWACI, PDCI, COI, COI, PDCI, NWACI
278 | 22-10183 | 12036167 | 04/17/2023 09:00 | 04/17/2023 18:00 | BEST LANE TAP TO BRASADA-HARNEY NO 1 115KV LINE | NWACI, ID-NW
279 | 23-00597 | 12690729 | 04/18/2023 06:30 | 04/18/2023 19:00 | ECHO LAKE-MONROE NO 1 500KV LINE, ECHO LAKE: PCB 5111, ECHO LAKE: PCB 5114, MONROE: PCB 4522, MONROE: PCB 4526, SNO-KING: PCB 4815, SNO-KING: 500/230KV TRANSFORMER 4 | IROL, NI, NOEL, SIG, SOC, WOCN, COI, NWACI, PDCI, BCHT, BCHW, LOAD
280 | 22-14994 | 12691204 | 04/18/2023 07:00 | 04/18/2023 16:00 | TAFT: PCB 4125 | MT-NW, WOH
281 | 22-10180 | 12076115 | 04/18/2023 09:00 | 04/18/2023 18:00 | STARVATION RIDGE TAP TO BRASADA-HARNEY NO 1 115KV LINE | ID-NW, NWACI/PDCI
282 | 23-00727 | 12380710 | 04/18/2023 10:30 | 04/18/2023 11:30 | ADDY: 230KV CAP GROUP 1 INCLUDING PCB A-147 | SOB
283 | 23-00718 | 12379595 | 04/19/2023 07:00 | 04/19/2023 09:00 | BELL: 230KV CAP GROUP 10 SECTIONS 1 AND 2 INCLUDING LBDS A-925 AND A-926 | MT-NW, WOH
284 | 23-00717 | 12690388 | 04/19/2023 07:00 | 04/19/2023 13:00 | BELL: TAFT 1 500KV LINE SERIES CAP GROUP 1 INCLUDING PCB 5320 | WOH, MT-NW
285 | 23-00429 | 12691354 | 04/19/2023 07:00 | 04/21/2023 16:00 | MALIN-HILLTOP NO 1 230KV LINE INCLUDING CANBY TAP | COI, PDCI, RATS, NWACI, SWORE
286 | 22-14995 | 12691269 | 04/19/2023 07:00 | 04/19/2023 16:00 | TAFT: PCB 4145 | MT-NW, WOH
287 | 23-01448 | 12691282 | 04/19/2023 07:30 | 04/19/2023 16:00 | ALVEY: PCB 5099 INCLUDING 500KV REACTOR #2 | COI, NWACI, PDCI, SLAL
288 | 23-00740 | 12690371 | 04/19/2023 08:00 | 04/20/2023 15:00 | BELL: PCB 5310, BFR AND DIFFERENTIAL RELAY | MT-NW, WOH
289 | 23-01527 | 12690348 | 04/19/2023 09:00 | 04/19/2023 16:00 | ASHE-MARION NO 2 500KV LINE | BCHT, BCHW, NI, NWACI, PDCI, SIG, WOCS, WOJD, WOM, COI
290 | 23-00719 | 12379756 | 04/19/2023 09:00 | 04/19/2023 11:00 | BELL: 230KV CAP GROUP 9 SECTIONS 1, 2, AND 3 INCLUDING PCBS A-931, A-932, AND A-933 | MT-NW, WOH
291 | 23-01430 | 12691294 | 04/19/2023 09:00 | 04/19/2023 16:00 | SLATT-BUCKLEY NO 1 500KV LINE | NWACI, PDCI, SIG, WOJD, WOM, WOS, COI
292 | 23-00720 | 12379762 | 04/19/2023 11:00 | 04/19/2023 13:00 | BELL: 230KV CAP GROUP 1 | MT-NW, WOH
293 | 23-00745 | 12408619 | 04/20/2023 08:00 | 04/20/2023 12:00 | TRENTWOOD: 115KV CAP GROUP 1 SECTIONS 1 AND 2 INCLUDING PCB'S B-1937 AND B-1938 AND 115KV REACTIVE BUS | LOAD
294 | 23-01170 | 12690378 | 04/24/2023 07:00 | 04/27/2023 16:00 | BELL: PCB 5313 | MT-NW, WOH
295 | 23-01330 | 12691389 | 04/24/2023 07:00 | 06/16/2023 17:00 | ROCKY REACH: ROCKY REACH-MAPLE VALLEY NO 1 345KV LINE INCLUDING ROCKY REACH 345/230 TRANSFORMER 1 | GEN, IROL, NOEL, NOH, SOC, WOCN, CI
296 | 23-00276 | 12394681 | 04/24/2023 07:00 | 04/27/2023 16:30 | SATSOP: 500/230KV TRANSFORMER 1, (FORCES OUT THE PAUL-SATSOP 1 500KV LINE) | PA, RP, LOAD, SI, SIG
297 | 23-01312 | 12623367 | 04/24/2023 08:00 | 04/26/2023 15:00 | ALVEY: MARION 1 500KV LINE SERIES CAP GROUP 1 | NWACI, PDCI, COI, BCHT, BCHW, NI, SIG
298 | 23-00851 | 12465609 | 04/24/2023 08:00 | 04/25/2023 12:00 | BELL: PCB A-577 500/230KV BFR | MT-NW, WOH
299 | 23-00821 | 12649670 | 04/24/2023 08:00 | 04/27/2023 16:00 | CHEMAWA: 230/115KV TRANSFORMER 2 | WOCS, LOAD
300 | 23-00529 | 12236138 | 04/24/2023 08:00 | 05/12/2023 07:30 | HANFORD-WAUTOMA NO 1 500KV LINE | NOH, NWACI, PDCI, SIG, COI
301 | 23-01263 | 12623352 | 04/24/2023 08:00 | 04/26/2023 15:00 | MARION-ALVEY NO 1 500KV LINE | NWACI, PDCI, COI, BCHT, BCHW, NI, SIG
302 | 23-00031 | 10031031 | 04/24/2023 08:00 | 04/28/2023 18:30 | PILOT BUTTE-LAPINE NO 1 230KV LINE | NWACI, PDCI, COI, COI, PDCI, NWACI
303 | 22-14567 | 12465455 | 04/26/2023 06:00 | 04/26/2023 14:00 | SWAN VALLEY - TETON #2 115KV LINE INCLUDING SWAN VALLEY PCB B-1675 AND 115KV AUX BUS | SEIL, GEN
304 | 23-01374 | 12690752 | 04/27/2023 09:00 | 04/27/2023 10:00 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 | GEN, NOH, WOCN
305 | 23-01375 | 12690801 | 04/27/2023 10:00 | 04/27/2023 11:00 | GRAND COULEE: PCB 2092, GRAND COULEE: PCB 2096 | GEN, NOH, WOCN
306 | 23-01376 | 12690942 | 04/27/2023 11:00 | 04/27/2023 12:00 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 | GEN, NOH, WOCN
307 | 23-01378 | 12691297 | 04/27/2023 12:30 | 04/27/2023 13:30 | GRAND COULEE: PCB 2292, GRAND COULEE: PCB 2296 | GEN, NOH, WOCN
308 | 23-01377 | 12691317 | 04/27/2023 13:30 | 04/27/2023 14:30 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 | GEN, NOH, WOCN
309 | 23-01379 | 12691326 | 04/27/2023 14:30 | 04/27/2023 15:30 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 | GEN, NOH, WOCN