## Request List
Row | Request# | CAISO# | Start | End | Main Element Impacted | Elements Involved | Path Affected
1 | 21-01711 | 9741845 | 02/03/2021 09:00 | 02/28/2030 17:00 | -USBR- GRAND COULEE 287/230KV TRANSFORMER KX-17-A (OLYMPIA-GRAND COULEE NO 1 287KV LINE OPERATING AT 230KV) | -USBR- GRAND COULEE 287/230KV TRANSFORMER KX-17-A (OLYMPIA-GRAND COULEE NO 1 287KV LINE OPERATING AT 230KV), OLYMPIA: 287/230KV TRANSFORMER 3, GRAND COULEE: 287/230KV TRANSFORMER 1 | NOEL, PA, RP, SOC, WOCN, IROL, NOH, OKLA
2 | 21-01767 | 10359382 | 06/30/2021 10:00 | 06/30/2023 16:00 | PAUL: 4805 TERMINAL OF PAUL-PSE TONO NO 1 500KV LINE | PAUL: 4805 TERMINAL OF PAUL-PSE TONO NO 1 500KV LINE, PAUL-PSE TONO NO 1 500KV LINE | LOAD, RP, SIG, SOA
3 | 22-06746 | 11593785 | 04/06/2022 06:30 | 12/28/2023 15:00 | CONKELLEY: LBD A-1575 INCLUDING 230KV CAP GROUP 2 SECTION 1 | CONKELLEY: LBD A-1575 INCLUDING 230KV CAP GROUP 2 SECTION 1, CONKELLEY: 230KV CAP GROUP 2 SECTION 1 | MT-NW
4 | 22-06836 | 11597875 | 04/06/2022 12:25 | 05/31/2023 15:00 | OSTRANDER-TROUTDALE 1 500KV LINE INCLUDING TROUTDALE: 500/230KV TRANSFORMER BANK 8 | OSTRANDER-TROUTDALE NO 1 500KV LINE, OSTRANDER-TROUTDALE 1 500KV LINE INCLUDING TROUTDALE: 500/230KV TRANSFORMER BANK 8, TROUTDALE: 500/230KV TRANSFORMER 8 | SIG, SOA, WOCS, SIG, WOCS, SOA
5 | 22-13128 | 12651062 | 08/17/2022 08:00 | 05/31/2023 23:59 | MAPLE VALLEY: 500/230KV TRANSFORMER 2, (DERATED) | MAPLE VALLEY: 500/230KV TRANSFORMER 2, (DERATED) | IROL, NOEL, SIG, SOC, WOCN
6 | 22-17044 | 12730571 | 11/16/2022 14:00 | 11/16/2023 19:00 | (EWEB) CURRIN: PCB'S 4590 & 4584 | (EWEB) CURRIN: PCB'S 4590 & 4584, CURRIN: PCB 4590, CURRIN: PCB 4584, CURRIN-OAKWAY-WILLAMETTE 115KV LINE | NWACI, PDCI, COI
7 | 23-01684 | 11460660 | 02/03/2023 15:30 | 10/10/2023 09:00 | PG&E -TABLE MOUNTAIN: ROUND MOUNTAIN 1 500KV LINE SERIES CAP 1 | PG&E -TABLE MOUNTAIN: ROUND MOUNTAIN 1 500KV LINE SERIES CAP 1 | COI, NWACI
8 | 23-03222 | 11461724 | 02/10/2023 18:30 | 10/19/2023 09:00 | PG&E- TABLE MOUNTAIN: ROUND MOUNTAIN 500KV LINE SERIES CAP GROUP 2 | PG&E- TABLE MOUNTAIN: ROUND MOUNTAIN 500KV LINE SERIES CAP GROUP 2 | NWACI, COI
9 | 23-05354 |  | 03/13/2023 06:00 | 08/18/2023 17:00 | -PACW- PACW KNOTT-PGE NORTHERN SECTION OF THE KNOTT-ST JOHNS 57KV LINE | -PACW- PACW KNOTT-PGE NORTHERN SECTION OF THE KNOTT-ST JOHNS 57KV LINE | SOA
10 | 23-04279 | 13037076 | 03/20/2023 15:30 | 05/12/2023 15:00 | JOHN DAY: PCB 4128, INCLUDING MOD 4127 | JOHN DAY: PCB 4128, INCLUDING MOD 4127 | NWACI, WOJD, WOS
11 | 23-00011 | 11242268 | 03/20/2023 17:30 | 05/11/2023 07:30 | HANFORD: PCB 4095 INCLUDING MODS 4094 & 4096 | HANFORD: PCB 4095 INCLUDING MODS 4094 & 4096, HANFORD: MOD 4094, HANFORD: MOD 4096 | NWACI, PDCI, WOLM, COI, NOH, WOM
12 | 23-04595 | 13065750 | 04/03/2023 07:00 | 05/01/2023 09:00 | LOOKOUT POINT: B-566 TERMINAL OF THE LOOKOUT POINT PH-LOOKOUT POINT NO 1 115KV LINE | LOOKOUT POINT: B-566 TERMINAL OF THE LOOKOUT POINT PH-LOOKOUT POINT NO 1 115KV LINE, LOOKOUT POINT PH-LOOKOUT POINT NO 1 115KV LINE, LOOKOUT POINT: PCB B-566 | GEN, EWEB
13 | 23-00462 | 12289653 | 04/04/2023 22:00 | 05/16/2023 19:00 | GRAND COULEE: 500/230KV CSY TIE BANK, INCLUDING 500KV PCB'S 8692,1996 & 230KV PCB 6582 | GRAND COULEE: PCB 1996, GRAND COULEE: 500/230KV CSY TIE BANK, INCLUDING 500KV PCB'S 8692,1996 & 230KV PCB 6582, GRAND COULEE: PCB 8692, GRAND COULEE: PCB 6582 | GEN, NOH, WOCN, PDCI, SIG, COI, FCRPS, NWACI
14 | 23-00391 |  | 04/07/2023 22:00 | 06/03/2023 07:00 | PROSSER: B-695 REMOVED JUMPERS AND B-696 REMOVED JUMPERS | PROSSER: B-695 REMOVED JUMPERS AND B-696 REMOVED JUMPERS
15 | 23-05041 |  | 04/11/2023 04:00 | 05/14/2023 20:00 | LADWP- ADELANTO-TOLUCA 1 500KV LINE | LADWP- ADELANTO-TOLUCA 1 500KV LINE | PDCI
16 | 23-03864 | 13005625 | 04/12/2023 15:00 | 05/02/2023 15:00 | BETTAS ROAD: 230KV EAST BUS INCLUDING PCB'S A-3046 & A-3043, THE COLUMBIA-BETTAS ROAD NO 1 230KV LINE AND THE KITTITAS PUD BETTAS ROAD 230KV LINE TO THE BB1-1 DISCONNECT | BETTAS ROAD: 230KV EAST BUS, BETTAS ROAD: 230KV EAST BUS INCLUDING PCB'S A-3046 & A-3043, THE COLUMBIA-BETTAS ROAD NO 1 230KV LINE AND THE KITTITAS PUD BETTAS ROAD 230KV LINE TO THE BB1-1 DISCONNECT, BETTAS ROAD: PCB A-3046, BETTAS ROAD-COLUMBIA NO 1 230KV LINE, BETTAS ROAD: PCB A-3043 | NOEL, CI, NOH, SOC, WOCN, IROL
17 | 23-03525 | 12976427 | 04/17/2023 17:01 | 05/04/2023 08:30 | LONGVIEW-ALLSTON #1 230KV LINE INCLUDING LONGVIEW: PCB A-100, A-100 M/B DISC, AND 230KV SOUTH AUX BUS | LONGVIEW-ALLSTON #1 230KV LINE INCLUDING LONGVIEW: PCB A-100, A-100 M/B DISC, AND 230KV SOUTH AUX BUS, LONGVIEW-ALLSTON NO 1 230KV LINE, LONGVIEW: PCB A-100, LONGVIEW: 230KV SOUTH AUX BUS, LONGVIEW: PCB A-642, ALLSTON: PCB A-1362 | SOA
18 | 23-01686 | 12735737 | 04/20/2023 06:30 | 05/12/2023 17:00 | GRAND COULEE: PCB 5782 | GRAND COULEE: PCB 5782 | NOH, WOCN, COI, NWACI, PDCI
19 | 23-05080 | 13126620 | 04/24/2023 07:00 | 05/10/2023 16:00 | LANE: 115KV SOUTH MAIN BUS INCLUDING PCB'S B-1614, B-1612, B-1610 AND B-1608 | LANE: 115KV SOUTH MAIN BUS, LANE: 115KV SOUTH MAIN BUS INCLUDING PCB'S B-1614, B-1612, B-1610 AND B-1608 , LANE: 115KV CENTER MAIN BUS, LANE: 230/115KV TRANSFORMER 1 | LOAD, EWEB
20 | 23-04284 |  | 04/24/2023 08:00 | 05/05/2023 15:00 | -PGE- MURRAYHILL- SHERWOOD NO 1 & 2 230KV LINES | -PGE- MURRAYHILL- SHERWOOD NO 1 & 2 230KV LINES, MURRAY HILL (PGE)-SHERWOOD NO 1 230KV LINE, MURRAY HILL (PGE)-SHERWOOD NO 2 230KV LINE | SOA
21 | 23-00530 | 12570534 | 04/24/2023 08:00 | 05/26/2023 16:00 | HANFORD-WAUTOMA NO 2 500KV LINE | HANFORD-WAUTOMA NO 2 500KV LINE | NOH, SIG
22 | 23-02735 | 12888833 | 04/24/2023 12:00 | 05/12/2023 11:00 | GARRISON-TAFT NO 2 500KV LINE, INCLUDING GARRISON PCB'S 4360, 4463 | GARRISON-TAFT NO 2 500KV LINE, GARRISON: PCB 4360, GARRISON: PCB 4463, INCLUDING GARRISON PCB'S 4360, 4463, GARRISON: TAFT 2 500KV LINE SERIES CAP GROUP 2 | MT-NW, SIG
23 | 22-02103 | 10879173 | 05/01/2023 01:00 | 05/12/2023 20:00 | GRAND COULEE: PCB 2296, PCB 2292 | GRAND COULEE: PCB 2296, PCB 2292, GRAND COULEE: PCB 2292 | GEN, NOH, WOCN
24 | 23-01241 | 12734923 | 05/01/2023 06:00 | 05/26/2023 17:00 | ROCK CREEK: 500/230KV TRANSFORMER 1, INCLUDING 500/230 TRANSFORMER SPARE PHASE, PCB'S 5291, 5294, A-1704, A-1711, A-1714 AND PACIFICORP 230KV FEEDER #1 TO IMRIE | ROCK CREEK: 500/230KV TRANSFORMER 1, ROCK CREEK: PCB A-1704, ROCK CREEK: PCB A-1714, INCLUDING 500/230 TRANSFORMER SPARE PHASE, PCB'S 5291, 5294, A-1704, A-1711, A-1714 AND PACIFICORP 230KV FEEDER #1 TO IMRIE, ROCK CREEK: PACIFICORP (PACW) 230KV FEEDER 1 TO IMRIE, ROCK CREEK: PCB A-1711, ROCK CREEK: PCB 5291, ROCK CREEK: PCB 5294, ROCK CREEK: 500/230 TRANSFORMER SPARE PHASE | GEN, RKCR
25 | 23-01948 | 12858082 | 05/01/2023 07:00 | 05/12/2023 14:00 | SPAR CANYON: LBD A-137 | SPAR CANYON: LBD A-137 | LOAD, SEIL
26 | 23-04315 | 13066617 | 05/01/2023 07:00 | 05/02/2023 15:00 | MCNARY: PCB A-428 | MCNARY: PCB A-428 | WOM
27 | 23-05311 | 13134393 | 05/01/2023 07:00 | 05/02/2023 16:00 | DEXTER: B-1009 TERMINAL OF THE DEXTER TAP OF THE LOOKOUT POINT-ALVEY NO 1 115KV LINE | DEXTER PH: 115/13.8KV BANK 1, DEXTER: B-1009 TERMINAL OF THE DEXTER TAP OF THE LOOKOUT POINT-ALVEY NO 1 115KV LINE
28 | 23-01389 | 12694988 | 05/01/2023 07:00 | 05/01/2023 15:30 | CUSTER: PCB 4482 | CUSTER: PCB 4482 | BCHT, BCHW, NOEL, SOC, NI
29 | 23-04828 | 13099139 | 05/01/2023 07:00 | 05/01/2023 16:00 | SATSOP: PCB A-613 | SATSOP: PCB A-613 | GEN, LOAD, PA
30 | 23-01178 | 12695006 | 05/01/2023 07:00 | 05/06/2023 16:00 | MONROE-SNOHOMISH NO 1&2 230KV LINE, INCLUDING HORSE RANCH TAP | MONROE-SNOHOMISH NO 1&2 230KV LINE, HORSE RANCH TAP TO MONROE-SNOHOMISH NO 1&2 230KV LINE, INCLUDING HORSE RANCH TAP | NOEL, SOC, BCHT, BCHW, SIG
31 | 23-01171 | 12695240 | 05/01/2023 07:00 | 05/03/2023 16:00 | BELL: PCB 5316 | BELL: PCB 5316 | MT-NW, WOH
32 | 23-01403 | 12695959 | 05/01/2023 08:00 | 05/04/2023 15:00 | CAPTAIN JACK: PCB 4983 | CAPTAIN JACK: PCB 4983 | NWACI, PDCI, COI
33 | 23-01558 | 12810676 | 05/01/2023 08:00 | 05/01/2023 09:30 | HARVALUM: 230KV CAP GROUP 1 | HARVALUM: 230KV CAP GROUP 1 | WOM
34 | 23-02492 | 12880817 | 05/01/2023 08:00 | 05/02/2023 16:00 | RILEY-STARVATION RIDGE SECTION OF BRASADA-HARNEY NO 1 115KV LINE | RILEY-STARVATION RIDGE SECTION OF BRASADA-HARNEY NO 1 115KV LINE
35 | 23-05407 | 13190799 | 05/01/2023 08:00 | 05/01/2023 15:00 | MURRAY: PCB A-1516 INCLUDING 230KV AUX BUS | MURRAY: PCB A-1516, MURRAY: PCB A-1516 INCLUDING 230KV AUX BUS, MURRAY: 230KV AUX BUS | BCHT, BCHW, NOEL, SOC
36 | 23-02414 | 13016855 | 05/01/2023 08:00 | 05/04/2023 16:00 | CARLTON: PCB A-318 | CARLTON: PCB A-318
37 | 23-00445 | 12182162 | 05/01/2023 08:00 | 05/02/2023 16:00 | JOHN DAY-GRIZZLY NO 1 500KV LINE, INCLUDING GRIZZLY: PCB 4058 | JOHN DAY-GRIZZLY NO 1 500KV LINE, GRIZZLY: PCB 4058, INCLUDING GRIZZLY: PCB 4058 | BCHT, BCHW, NI, NWACI, PDCI, SIG, WOJD, COI
38 | 23-00784 | 12695352 | 05/01/2023 08:00 | 05/04/2023 16:00 | MARION: PCB 4380 | MARION: PCB 4380 | NWACI, PDCI, COI
39 | 23-00732 | 12380742 | 05/01/2023 08:00 | 05/25/2023 15:00 | CARDWELL: B-1542 TERMINAL OF THE SOUTH KELSO-CARDWELL #1 115KV LINE | CARDWELL: PCB B-1542, CARDWELL: B-1542 TERMINAL OF THE SOUTH KELSO-CARDWELL #1 115KV LINE, SOUTH KELSO-CARDWELL 115KV LINE | LOAD, SOA
40 | 23-05271 |  | 05/01/2023 08:00 | 05/11/2023 16:00 | DORENA TAP TO THE ALVEY-MARTIN CREEK NO 1 115KV LINE INCLUDING B-1577 DISCONNECT | DORENA: 34.5KV PCB L-1414, DORENA TAP TO THE ALVEY-MARTIN CREEK NO 1 115KV LINE INCLUDING B-1577 DISCONNECT, DORENA: 115/34.5KV TRANSFORMER 1, DORENA TAP TO ALVEY-MARTIN CREEK NO 1 115KV LINE, DORENA: LANE ELEC COOP 34.5KV FEEDER 1 BY PACIFICORP (PACW), DORENA: LANE ELEC COOP 34.5KV FEEDER 2 BY PACIFICORP (PACW), DORENA-LATHAM SECTION OF ALVEY-MARTIN CREEK NO 1 115KV LINE | SCORC
41 | 23-05362 | 13159732 | 05/01/2023 08:00 | 05/11/2023 15:00 | NASELLE-TARLETT NO 1 115KV LINE | NASELLE-TARLETT NO 1 115KV LINE
42 | 23-02654 | 13033038 | 05/01/2023 08:30 | 05/01/2023 15:00 | HILLTOP: PCB A-1525 BFR | HILLTOP: PCB A-1525 BFR, HILLTOP: PCB A-1525 | RATS, NWACI
43 | 23-00234 | 12118758 | 05/01/2023 08:30 | 05/02/2023 15:00 | OSTRANDER: PCB 5134 | OSTRANDER: PCB 5134 | WOCS
44 | 23-01089 | 12622881 | 05/02/2023 07:00 | 05/02/2023 16:00 | ABERDEEN: 230/115KV TRANSFORMER 4 AND THE 115KV AUX BUS | SATSOP-ABERDEEN NO 2 230KV LINE, ABERDEEN: 230/115KV TRANSFORMER 4 AND THE 115KV AUX BUS, ABERDEEN: 230/115KV TRANSFORMER 4, ABERDEEN: 115KV AUX BUS | LOAD, PA, SI
45 | 23-02352 | 13247109 | 05/02/2023 07:00 | 05/03/2023 16:00 | MAPLE VALLEY: 500/230KV TRANSFORMER 2 | MAPLE VALLEY: 500/230KV TRANSFORMER 2, ECHO LAKE-MAPLE VALLEY NO 1&2 500KV LINE | IROL, NOEL, SIG, SOC, WOCN
46 | 23-04063 | 13029033 | 05/02/2023 07:00 | 05/02/2023 16:30 | LEBANON: AIRPORT-LEBANON SECTION OF ALBANY-LEBANON NO 1 115KV LINE INCLUDING PCB B-848 AND THE 115KV AUX BUS | LEBANON: 115KV AUX BUS, LEBANON: AIRPORT-LEBANON SECTION OF ALBANY-LEBANON NO 1 115KV LINE INCLUDING PCB B-848 AND THE 115KV AUX BUS, LEBANON: PCB B-848, AIRPORT-LEBANON SECTION OF ALBANY-LEBANON NO 1 115KV LINE | SLAL
47 | 23-01384 | 12695541 | 05/02/2023 07:30 | 05/03/2023 15:00 | MONROE: PCB 5053 | MONROE: PCB 5053 | BCHT, BCHW, NOEL, SOC, WOCN, NI
48 | 23-02663 | 12858455 | 05/02/2023 08:00 | 05/25/2023 16:00 | REDMOND: A-262 TERMINAL OF THE REDMOND-PGE ROUND BUTTE 230KV LINE | REDMOND: A-262 TERMINAL OF THE REDMOND-PGE ROUND BUTTE 230KV LINE, REDMOND-PGE ROUND BUTTE NO 1 230KV LINE, REDMOND: PCB A-262 | SIG, COR
49 | 23-01568 | 12873306 | 05/02/2023 08:00 | 05/02/2023 15:00 | DWORSHAK: TAFT 1 500KV LINE SERIES CAP GROUP 1, INCLUDING PCB 4765 | DWORSHAK: TAFT 1 500KV LINE SERIES CAP GROUP 1, DWORSHAK: PCB 4765, INCLUDING PCB 4765 | MT-NW, WOH, WOLM, SLAL
50 | 23-05678 | 13191083 | 05/02/2023 08:00 | 05/03/2023 15:00 | SCHULTZ 500KV REACTOR #1, INCLUDING PCB 5106 | SCHULTZ: 500KV REACTOR 1, SCHULTZ 500KV REACTOR #1, INCLUDING PCB 5106, SCHULTZ: PCB 5106 | WOCN
51 | 23-03319 | 12969499 | 05/02/2023 08:00 | 05/14/2023 18:00 | NORTH BONNEVILLE-TROUTDALE NO 1 230KV LINE | NORTH BONNEVILLE-TROUTDALE NO 1 230KV LINE | GEN, LOAD, WOCS, FCRPS
52 | 23-02655 | 13033069 | 05/02/2023 08:30 | 05/02/2023 15:00 | HILLTOP: PCB A-1529 BFR | HILLTOP: PCB A-1529 BFR, HILLTOP: PCB A-1529 | RATS, NWACI
53 | 23-04829 | 13099156 | 05/03/2023 07:00 | 05/03/2023 16:00 | SATSOP: PCB A-622 | SATSOP: PCB A-622 | GEN, LOAD, PA
54 | 23-04068 | 13032348 | 05/03/2023 07:00 | 05/03/2023 16:30 | LEBANON: 115KV MAIN BUS INCLUDING PCB'S B-848, B-850, B-1950 AND THE 115KV CAP GROUP NO 1 INCLUDING PCB B-1951 | LEBANON: 115KV CAP GROUP 1, LEBANON: 115KV MAIN BUS INCLUDING PCB'S B-848, B-850, B-1950 AND THE 115KV CAP GROUP NO 1 INCLUDING PCB B-1951, LEBANON: PCB B-1950, LEBANON: PCB B-1951, LEBANON: PCB B-848, LEBANON: PCB B-850, FOSTER TAP-LEBANON SECTION OF GREEN PETER-LEBANON NO 1 115KV LINE | SLAL
55 | 23-00740 | 12690371 | 05/03/2023 08:00 | 05/04/2023 15:00 | BELL: PCB 5310, BFR AND DIFFERENTIAL RELAY | BELL: PCB 5310, BFR AND DIFFERENTIAL RELAY, BELL: PCB 5310 | MT-NW, WOH
56 | 23-00235 | 12182585 | 05/03/2023 08:00 | 05/03/2023 15:00 | TROUTDALE: PCB A-1306 | TROUTDALE: PCB A-1306 | WOCS
57 | 23-01409 | 12690849 | 05/03/2023 16:00 | 06/14/2023 16:00 | GRIZZLY: PCB 4058, GRIZZLY: MOD 4057 | GRIZZLY: PCB 4058, GRIZZLY: MOD 4057 | NWACI, WOJD, COI
58 | 23-04070 | 13032429 | 05/04/2023 07:00 | 05/04/2023 16:30 | LEBANON: FOSTER TAP-LEBANON SECTION OF GREEN PETER-LEBANON NO 1 115KV LINE INCLUDING PCB B-850 AND THE LEBANON 115KV A/B | LEBANON: FOSTER TAP-LEBANON SECTION OF GREEN PETER-LEBANON NO 1 115KV LINE INCLUDING PCB B-850 AND THE LEBANON 115KV A/B, LEBANON: 115KV AUX BUS, FOSTER TAP-LEBANON SECTION OF GREEN PETER-LEBANON NO 1 115KV LINE, LEBANON: PCB B-850
59 | 23-05402 | 13191146 | 05/04/2023 07:00 | 05/04/2023 16:00 | SNO-KING: PCB A-1205 | SNO-KING: PCB A-1205 | BCHT, BCHW, NOEL, SOC
60 | 23-04830 | 13099165 | 05/04/2023 07:00 | 05/04/2023 16:00 | SATSOP: PCB A-616 | SATSOP: PCB A-616 | GEN, LOAD, PA
61 | 23-04243 | 13038028 | 05/04/2023 08:00 | 05/04/2023 09:30 | LOWER MONUMENTAL: PCB 4599 | LOWER MONUMENTAL: PCB 4599 | WOLM
62 | 23-03532 | 12976505 | 05/04/2023 08:31 | 05/04/2023 17:00 | LONGVIEW: 230KV SOUTH MAIN BUS INCLUDING PCB A-100 | LONGVIEW: 230KV SOUTH MAIN BUS INCLUDING PCB A-100, LONGVIEW: 230KV SOUTH MAIN BUS, LONGVIEW: PCB A-98, LONGVIEW: PCB A-640, LONGVIEW: PCB A-100, LONGVIEW: PCB A-104, LONGVIEW: PCB A-106, LONGVIEW: PCB A-1960, LONGVIEW-ALLSTON NO 1 230KV LINE, LONGVIEW-ALLSTON NO 2 230KV LINE, LONGVIEW: 230/69KV TRANSFORMER 1, LONGVIEW: 230/115KV TRANSFORMER 3 | SOA, PA, LOAD
63 | 23-04245 | 13038045 | 05/04/2023 10:00 | 05/04/2023 11:30 | LOWER MONUMENTAL: PCB 4263 | LOWER MONUMENTAL: PCB 4263 | WOLM
64 | 23-04248 | 13038057 | 05/04/2023 13:00 | 05/04/2023 14:30 | LOWER MONUMENTAL: PCB 4316 | LOWER MONUMENTAL: PCB 4316 | WOLM
65 | 23-03873 | 13001946 | 05/05/2023 09:00 | 05/13/2023 08:00 | ASHE: 4886/4887 TERMINAL OF COLUMBIA GENERATING STATION-ASHE 1 500KV LINE | ASHE: PCB 4888, ASHE: 4886/4887 TERMINAL OF COLUMBIA GENERATING STATION-ASHE 1 500KV LINE, ASHE: PCB 4885, COLUMBIA GENERATING STATION-ASHE NO 1 500KV LINE | GEN, NWACI, FCRPS, SIG, NOH, STCON
66 | 23-05371 | 13139779 | 05/06/2023 06:00 | 05/07/2023 18:00 | COVINGTON: A-86 TERMINAL OF , COVINGTON-DUWAMISH NO 1 230KV LINE | COVINGTON: A-86 TERMINAL OF , COVINGTON-DUWAMISH NO 1 230KV LINE | NOEL, SOC
67 | 23-05372 | 13139807 | 05/06/2023 06:00 | 05/07/2023 18:00 | MAPLE VALLEY: A-1106 TERMINAL OF, MAPLE VALLEY-DUWAMISH NO 1 230KV LINE | MAPLE VALLEY: A-1106 TERMINAL OF, MAPLE VALLEY-DUWAMISH NO 1 230KV LINE | NOEL, SOC
68 | 23-03883 | 13004870 | 05/06/2023 07:00 | 05/09/2023 12:00 | ASHE: PCB 4885 | ASHE: PCB 4885 | GEN, NWACI, FCRPS
69 | 23-00330 | 12011700 | 05/08/2023 06:30 | 05/08/2023 07:00 | BIG EDDY: PCB A-824 OF THE DALLES PH-BIG EDDY NO 4 230KV LINE | BIG EDDY: PCB A-824 OF THE DALLES PH-BIG EDDY NO 4 230KV LINE | GEN, FCRPS
70 | 23-01177 | 12695738 | 05/08/2023 07:00 | 05/13/2023 16:00 | SNOHOMISH-BOTHELL NO 1 230KV LINE | SNOHOMISH-BOTHELL NO 1 230KV LINE | NOEL, SOC
71 | 23-03928 | 13011876 | 05/08/2023 07:00 | 05/09/2023 12:00 | ASHE: PCB 4888 BFR and BREAKER DIFFERENTIAL RELAY | ASHE: PCB 4888, ASHE: PCB 4888 BFR and BREAKER DIFFERENTIAL RELAY | GEN, NWACI, FCRPS
72 | 23-00481 | 12220066 | 05/08/2023 07:00 | 05/10/2023 16:00 | PAUL: PCB 4540 | PAUL: PCB 4540 | NWACI, PDCI, COI, WOCS, SOA
73 | 23-01348 | 12695763 | 05/08/2023 07:00 | 05/11/2023 12:00 | BELL: 500/230KV TRANSFORMER 1 | BELL: 500/230KV TRANSFORMER 1, BELL: PCB 5307, BELL: PCB 5310 | GEN, MT-NW, WOH
74 | 23-04472 | 13060177 | 05/08/2023 07:00 | 05/25/2023 15:00 | SIFTON: 230/115KV TRANSFORMER NO 2 RELAYS | SIFTON: 230KV EAST MAIN BUS, SIFTON: 230/115KV TRANSFORMER NO 2 RELAYS, SIFTON: 230/115KV TRANSFORMER 2, SIFTON: PCB A-163, SIFTON: PCB B-1500 | SOA
75 | 23-00379 | 12161569 | 05/08/2023 07:30 | 05/09/2023 15:00 | NORTH BONNEVILLE: PCB A-8 | NORTH BONNEVILLE: PCB A-8
76 | 23-04984 | 13104565 | 05/08/2023 07:30 | 05/12/2023 17:30 | NORTH BONNEVILLE: UNDERWOOD TAP-ALCOA SECTION OF BONNEVILLE PH 1-ALCOA NO 1&2 115KV LINE | NORTH BONNEVILLE: UNDERWOOD TAP-ALCOA SECTION OF BONNEVILLE PH 1-ALCOA NO 1&2 115KV LINE, UNDERWOOD: PCB B-1521, ALCOA: PCB B-236, ALCOA: PCB B-234 | SOA, GEN, LOAD
77 | 23-04979 | 13104546 | 05/08/2023 07:30 | 05/12/2023 17:30 | SIFTON-ROSS NO 1 115KV LINE | SIFTON-ROSS NO 1 115KV LINE, SIFTON: PCB B-1508, ROSS: PCB B-6 | SOA, WOCS
78 | 23-01614 | 12729060 | 05/08/2023 07:30 | 05/09/2023 15:00 | ECHO LAKE: PCB 5072 | ECHO LAKE: PCB 5072, ECHO LAKE: PCB 5111 | BCHT, BCHW, NOEL, SOC, NI, WOCN
79 | 23-02416 | 13048431 | 05/08/2023 08:00 | 05/11/2023 15:00 | KEELER: PCB 4394 | KEELER: PCB 4394 | SOA
80 | 23-01514 | 12757600 | 05/08/2023 08:00 | 05/08/2023 15:00 | SHELTON: PCB A-971 RELAYS | SHELTON: PCB A-971, SHELTON: PCB A-971 RELAYS | PA, RP
81 | 23-02494 | 12880157 | 05/08/2023 08:00 | 05/12/2023 16:00 | HAMPTON-BEST LANE SECTION OF BRASADA-HARNEY NO 1 115KV LINE | HAMPTON-BEST LANE SECTION OF BRASADA-HARNEY NO 1 115KV LINE | NWACI
82 | 23-00851 | 12465609 | 05/08/2023 08:00 | 05/09/2023 12:00 | BELL: PCB A-577 500/230KV BFR | BELL: PCB A-577, BELL: PCB A-577 500/230KV BFR | MT-NW, WOH
83 | 22-13081 | 12264072 | 05/08/2023 08:00 | 05/26/2023 15:00 | DIAMOND LAKE-ALBENI FALLS SECTION OF THE SACHEEN-ALBENI FALLS NO 1 115KV LINE INCLUDING ALBENI FALLS 115KV AUX BUS, AND PCB B-960 | ALBENI FALLS: PCB B-960, DIAMOND LAKE-ALBENI FALLS SECTION OF THE SACHEEN-ALBENI FALLS NO 1 115KV LINE INCLUDING ALBENI FALLS 115KV AUX BUS, AND PCB B-960, ALBENI FALLS: 115KV AUX BUS, DIAMOND LAKE-ALBENI FALLS SECTION OF SACHEEN-ALBENI FALLS NO 1 115KV LINE | SOB, GEN
84 | 23-01291 | 12695258 | 05/08/2023 08:00 | 05/11/2023 15:00 | MALIN: PCB 4582 | MALIN: PCB 4582 | NWACI, PDCI, COI
85 | 23-02165 | 13038451 | 05/08/2023 08:00 | 05/18/2023 15:00 | BENTON CITY-RED MOUNTAIN SECTION OF GRANDVIEW-RED MOUNTAIN NO 1 115KV LINE | BENTON CITY-RED MOUNTAIN SECTION OF GRANDVIEW-RED MOUNTAIN NO 1 115KV LINE, RED MOUNTAIN: PCB B-1978, RED MOUNTAIN: PCB B-1974 | GEN, TCLA, LOAD
86 | 23-04600 | 13125767 | 05/08/2023 08:00 | 05/16/2023 16:00 | GRAND COULEE-NILLES CORNER SECTION OF GRAND COULEE-FOSTER CREEK NO 1 115KV LINE INCLUDING B-1236 DISCONNECT | GRAND COULEE-NILLES CORNER SECTION OF GRAND COULEE-FOSTER CREEK NO 1 115KV LINE INCLUDING B-1236 DISCONNECT, GRAND COULEE: PCB 2472, GRAND COULEE-NILLES CORNER SECTION OF GRAND COULEE-FOSTER CREEK NO 1 115KV LINE, NILLES CORNER: B-1236 LINE SECTIONALIZING DISC | CI
87 | 23-01943 | 12824401 | 05/08/2023 08:00 | 05/11/2023 16:00 | MARION: 500KV REACTOR 1 INCLUDING PCB 4012 | MARION: 500KV REACTOR 1, MARION: 500KV REACTOR 1 INCLUDING PCB 4012, MARION: PCB 4012 | COI, NWACI
88 | 23-05620 | 13195792 | 05/08/2023 08:00 | 05/08/2023 13:00 | WENDSON: 230/115KV TRANSFORMER 1, INCLUDING: THREE-PHASE PRIMARY STATION SERVICE TRANSFORMER 1 AND AUTOMATIC TRANSFER SWITCH | WENDSON: 230/115KV TRANSFORMER 1, WENDSON: THREE-PHASE STATION SERVICE TRANSFORMER 1, INCLUDING: THREE-PHASE PRIMARY STATION SERVICE TRANSFORMER 1 AND AUTOMATIC TRANSFER SWITCH, WENDSON: 120/240VAC DISTRIBUTION CENTER, WENDSON: STATION SERVICE AUTO TRANSFER SWITCH, WENDSON: PCB A-1578, WENDSON: PCB B-1784, WENDSON: 230/115KV TIE NO 1 115KV LINE, WENDSON: 120/240V ALTERNATE STATION SERVICE TRANSFORMER | LOAD, SCORC
89 | 23-05994 | 13208479 | 05/08/2023 09:00 | 05/19/2023 16:30 | SUMMER LAKE: PCB 4957 | SUMMER LAKE: PCB 4957 | ID-NW, NWACI, COI
90 | 23-05993 | 13208474 | 05/08/2023 09:00 | 05/19/2023 16:30 | SUMMER LAKE: PCB 4958 | SUMMER LAKE: PCB 4958 | ID-NW, NWACI, COI
91 | 23-03487 | 13017484 | 05/08/2023 09:00 | 05/10/2023 17:00 | HARRISBURG: B-975 LSD | HARRISBURG: B-975 LSD, HALSEY MILL-HARRISBURG SECTION OF ALBANY-EUGENE NO 1 115KV LINE
92 | 23-05183 | 13110444 | 05/08/2023 09:00 | 05/19/2023 16:30 | SUMMER LAKE: 4951/4952 TERMINALS OF THE HEMINGWAY-SUMMER LAKE NO 1 500KV LINE | SUMMER LAKE: 4951/4952 TERMINALS OF THE HEMINGWAY-SUMMER LAKE NO 1 500KV LINE, HEMINGWAY-SUMMER LAKE NO 1 500KV LINE, SUMMER LAKE: PCB 4958, SUMMER LAKE: PCB 4957 | ID-NW, NWACI, SIG, COI
93 | 23-01387 | 12736322 | 05/08/2023 11:30 | 05/09/2023 15:00 | MONROE: PCB 4715, MONROE: 500KV CAP GROUP 2 | MONROE: PCB 4715, MONROE: 500KV CAP GROUP 2 | WOCN, NI, NOEL, SOC, IROL
94 | 23-01516 | 12981073 | 05/09/2023 07:00 | 05/09/2023 15:00 | SHELTON: PCB A-77 | SHELTON: PCB A-77 | PA, RP
95 | 23-04306 | 13039399 | 05/09/2023 07:00 | 05/09/2023 14:00 | DRUMMOND-MACKS INN NO 1 115KV LINE INCLUDING MACKS INN PCB B-363 AND THE MACKS INN-MADISON NO 1 115KV LINE | DRUMMOND-MACKS INN NO 1 115KV LINE, DRUMMOND-MACKS INN NO 1 115KV LINE INCLUDING MACKS INN PCB B-363 AND THE MACKS INN-MADISON NO 1 115KV LINE, MACKS INN-MADISON NO 1 115KV LINE, MACKS INN: PCB B-363, MACKS INN: B-355 LINE SECTIONALIZING DISC | SEIL
96 | 23-03211 | 13027416 | 05/09/2023 07:30 | 05/10/2023 15:30 | ALBANY: 115KV WEST, CENTER, AND EAST MAIN BUS INCLUDING PCB’S: B-512 , B-514 , B-516 , B-518 , B-520 , B-522 , B-524 , B-526 , B-528 , B-1272 | ALBANY: 115KV WEST, CENTER, AND EAST MAIN BUS INCLUDING PCB’S: B-512 , B-514 , B-516 , B-518 , B-520 , B-522 , B-524 , B-526 , B-528 , B-1272, ALBANY: 115KV WEST MAIN BUS, ALBANY: 115KV EAST MAIN BUS, ALBANY: 115KV CENTER MAIN BUS, ALBANY: 115KV CAP GROUP 1 SECTION 1, ALBANY: 115KV CAP GROUP 1 SECTION 2, ALBANY-BURNT WOODS NO 1 115KV LINE, ALBANY: PACIFICORP (PACW) 115KV FEEDER 1, ALBANY: 230/115KV TRANSFORMER 1, ALBANY: PCB B-1272, ALBANY: PCB B-512, ALBANY: PCB B-514, ALBANY: PCB B-516, ALBANY: PCB B-517, ALBANY: PCB B-518, ALBANY: PCB B-520, ALBANY: PCB B-521, ALBANY: PCB B-522, ALBANY: PCB B-524, ALBANY: PCB B-526, ADAIR-ALBANY SECTION OF SALEM-ALBANY NO 2 115KV LINE, ALBANY-LOCHNER SECTION OF ALBANY-LEBANON NO 1 115KV LINE, ALBANY-HALSEY MILL SECTION OF ALBANY-EUGENE NO 1 115KV LINE, BURNT WOODS: CONSUMERS POWER 24.9KV FEEDER 1, ALBANY: PCB B-528, SANTIAM-ALBANY NO 1 230KV LINE | LOAD, SLAL, SCORC
97 | 23-01584 |  | 05/09/2023 08:00 | 05/09/2023 12:00 | BIG EDDY: 230KV CAP GROUP 1 SECTIONS 1&2 INCLUDING LBD'S A-837 AND A-841 | BIG EDDY: 230KV CAP GROUP 1 SECTION 1, BIG EDDY: 230KV CAP GROUP 1 SECTIONS 1&2 INCLUDING LBD'S A-837 AND A-841, BIG EDDY: 230KV CAP GROUP 1 SECTION 2, BIG EDDY: LBD A-837, BIG EDDY: LBD A-841, BIG EDDY: PCB A-839 | COI, PDCI, NWACI, WOJD
98 | 23-01585 | 12685834 | 05/09/2023 12:00 | 05/09/2023 15:00 | BIG EDDY: 230KV CAP GROUP 2 SECTION 1 INCLUDING PCB A-818 | BIG EDDY: 230KV CAP GROUP 2 SECTION 1 INCLUDING PCB A-818, BIG EDDY: 230KV CAP GROUP 2 SECTION 1, BIG EDDY: PCB A-818 | COI, PDCI, NWACI, WOJD
99 | 23-03884 | 13004874 | 05/09/2023 12:00 | 05/12/2023 15:00 | ASHE: PCB 4888 | ASHE: PCB 4888 | GEN, NWACI, FCRPS
100 | 23-03929 | 13043407 | 05/09/2023 13:00 | 05/10/2023 15:00 | ASHE: PCB 4885 BFR | ASHE: PCB 4885 BFR, ASHE: PCB 4885 | GEN, NWACI, FCRPS
101 | 23-03593 | 12981092 | 05/09/2023 15:00 | 05/09/2023 15:30 | SHELTON: PCB A-990 | SHELTON: PCB A-990 | PA, RP
102 | 23-01517 | 12981098 | 05/10/2023 07:00 | 05/10/2023 15:00 | SHELTON: PCB A-936 | SHELTON: PCB A-936 | PA, RP
103 | 23-04291 | 13038828 | 05/10/2023 07:00 | 05/10/2023 14:00 | DRUMMOND-MACKS INN NO 1 115KV LINE, INCLUDING MACKS INN 115KV MAIN BUS | DRUMMOND-MACKS INN NO 1 115KV LINE, MACKS INN-MADISON NO 1 115KV LINE, MACKS INN: PCB B-363, INCLUDING MACKS INN 115KV MAIN BUS, DRUMMOND: PCB B-1502, MACKS INN: 115KV MAIN BUS | SEIL, LOAD
104 | 23-01615 | 12736418 | 05/10/2023 07:00 | 05/11/2023 15:00 | RAVER: 500KV CAP GROUP 1 SECTION 2, INCLUDING PCB 4919 | RAVER: 500KV CAP GROUP 1 SECTION 2, RAVER: PCB 4919, INCLUDING PCB 4919 | IROL, WOCN, NOEL, RP, SOC
105 | 23-01390 | 12718082 | 05/10/2023 07:00 | 05/10/2023 15:00 | CUSTER: PCB 4486 | CUSTER: PCB 4486 | BCHT, BCHW, NOEL, SOC, NI
106 | 23-01553 | 12736452 | 05/10/2023 08:00 | 05/10/2023 12:00 | JOHN DAY: 500KV CAP GROUP 1 | JOHN DAY: 500KV CAP GROUP 1, JOHN DAY: PCB 4153 | COI, NWACI, PDCI, WOJD
107 | 23-00400 | 13235709 | 05/10/2023 08:00 | 05/25/2023 16:00 | CALPINE-MCNARY NO 1 500KV LINE INCLUDING PCB'S 5198 AND 5199 | CALPINE-MCNARY NO 1 500KV LINE INCLUDING PCB'S 5198 AND 5199, CALPINE-MCNARY NO 1 500KV LINE, MCNARY: PCB 5198, MCNARY: PCB 5199 | GEN, SIG, WOJD, WOM, WOS
108 | 23-00377 | 12161580 | 05/10/2023 08:00 | 05/10/2023 15:00 | NORTH BONNEVILLE: PCB A-2 | NORTH BONNEVILLE: PCB A-2 | WOCS
109 | 23-01766 | 12761655 | 05/10/2023 12:00 | 05/10/2023 13:30 | JOHN DAY: 230KV CAP GROUP 2 SECTION 1 INCLUDING PCB A-1734 | JOHN DAY: PCB A-1734, JOHN DAY: 230KV CAP GROUP 2 SECTION 1 INCLUDING PCB A-1734, JOHN DAY: 230KV CAP GROUP 2 SECTION 1 | COI, JDAY, PDCI, WOJD, NWACI
110 | 23-02890 | 12918111 | 05/10/2023 12:30 | 05/11/2023 16:00 | PORT ANGELES: PCB B-1205 | PORT ANGELES: PCB B-1205
111 | 23-01767 | 12761828 | 05/10/2023 13:00 | 05/10/2023 14:00 | JOHN DAY: 230KV CAP GROUP 2 SECTION 2 INCLUDING PCB A-1735 | JOHN DAY: PCB A-1735, JOHN DAY: 230KV CAP GROUP 2 SECTION 2 INCLUDING PCB A-1735, JOHN DAY: 230KV CAP GROUP 2 SECTION 2 | COI, JDAY, PDCI, WOJD, NWACI
112 | 23-01768 | 12810475 | 05/10/2023 14:00 | 05/10/2023 15:00 | JOHN DAY: 230KV CAP GROUP 2 SECTION 1 INCLUDING PCB A-1734 | JOHN DAY: PCB A-1734, JOHN DAY: 230KV CAP GROUP 2 SECTION 1 INCLUDING PCB A-1734, JOHN DAY: 230KV CAP GROUP 2 SECTION 1 | COI, JDAY, PDCI, WOJD, NWACI
113 | 23-01769 |  | 05/10/2023 14:00 | 05/10/2023 16:00 | JOHN DAY: 230KV CAP GROUP 2 SECTION 3 INCLUDING PCB A-1736 | JOHN DAY: PCB A-1736, JOHN DAY: 230KV CAP GROUP 2 SECTION 3 INCLUDING PCB A-1736
114 | 23-03594 | 12981124 | 05/10/2023 15:00 | 05/10/2023 15:30 | SHELTON: PCB A-83 | SHELTON: PCB A-83 | PA, RP
115 | 23-04292 | 13042468 | 05/11/2023 07:00 | 05/11/2023 14:00 | DRUMMOND - MACKS INN #1 115KV LINE INCLUDING MACKS INN: 115/46KV TRANSFORMERS #1 AND #2, 115KV MAIN BUS, AND LBD B-1842 | MACKS INN: 115/46KV TRANSFORMER 1, DRUMMOND - MACKS INN #1 115KV LINE INCLUDING MACKS INN: 115/46KV TRANSFORMERS #1 AND #2, 115KV MAIN BUS, AND LBD B-1842, MACKS INN: 115/46KV TRANSFORMER 2, MACKS INN: 115KV MAIN BUS, DRUMMOND-MACKS INN NO 1 115KV LINE, MACKS INN-MADISON NO 1 115KV LINE, MACKS INN: LBD B-1842 | LOAD, SEIL
116 | 23-00012 | 11242303 | 05/11/2023 07:30 | 05/11/2023 15:00 | LOWER MONUMENTAL-HANFORD NO 1 500KV LINE INCLUDING HANFORD: PCB 4095 | LOWER MONUMENTAL-HANFORD NO 1 500KV LINE INCLUDING HANFORD: PCB 4095 | NWACI, PDCI, WOLM, COI, NOH, WOM, SIG
117 | 23-05242 | 13126532 | 05/11/2023 08:00 | 05/11/2023 15:00 | LANE: 115KV NORTH MAIN BUS | LANE: 115KV NORTH MAIN BUS, LANE: 230/115KV TRANSFORMER 2, LANE: 115KV CAP GROUP 1, LANE: EWEB (EUGENE OR) 115KV FEEDER 1, LANE: EWEB (EUGENE OR) 115KV FEEDER 2, WILLOW CREEK-LANE 115KV LINE, DANEBO-LANE 115KV LINE | LOAD, EWEB
118 | 23-01796 | 12782135 | 05/11/2023 08:30 | 05/11/2023 12:00 | BAKEOVEN: JOHN DAY-GRIZZLY 1 500KV LINE SERIES CAP GROUP 1, INCLUDING PCB 5363 | BAKEOVEN: PCB 5363, BAKEOVEN: JOHN DAY-GRIZZLY 1 500KV LINE SERIES CAP GROUP 1, INCLUDING PCB 5363 | NWACI, PDCI, COI, WOJD
119 | 23-04776 | 13078297 | 05/11/2023 09:00 | 05/11/2023 15:00 | COLVILLE: 115KV CAP GROUP 1 SECTIONS 1, 2, & 3 INCLUDING PCB'S B-1769, B-1771, B-1773, & B-1780 | COLVILLE: 115KV CAP GROUP 1 SECTIONS 1, 2, & 3 INCLUDING PCB'S B-1769, B-1771, B-1773, & B-1780, COLVILLE: 115KV CAP GROUP 1 SECTION 1, COLVILLE: 115KV CAP GROUP 1 SECTION 2, COLVILLE: 115KV CAP GROUP 1 SECTION 3, COLVILLE: PCB B-1769, COLVILLE: PCB B-1771, COLVILLE: PCB B-1773, COLVILLE: PCB B-1780
120 | 23-01452 | 12736469 | 05/11/2023 09:00 | 05/11/2023 10:00 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 | GEN, NOH, WOCN
121 | 23-01453 | 12736473 | 05/11/2023 10:00 | 05/11/2023 11:00 | GRAND COULEE: PCB 2092, GRAND COULEE: PCB 2096 | GRAND COULEE: PCB 2092, GRAND COULEE: PCB 2096 | GEN, NOH, WOCN
122 | 23-01454 | 12736479 | 05/11/2023 11:00 | 05/11/2023 12:00 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 | GEN, NOH, WOCN
123 | 23-01816 | 12782062 | 05/11/2023 12:00 | 05/11/2023 15:00 | BAKEOVEN: JOHN DAY-GRIZZLY 2 500KV LINE SERIES CAP GROUP 2, INCLUDING PCB 5367 | BAKEOVEN: JOHN DAY-GRIZZLY 2 500KV LINE SERIES CAP GROUP 2, BAKEOVEN: PCB 5367, INCLUDING PCB 5367 | NWACI, PDCI, COI, WOJD
124 | 23-05124 |  | 05/11/2023 12:01 | 05/11/2023 16:30 | BELL: 230KV AUX BUS SECTION 5, BELL: PCB A-577 | BELL: 230KV AUX BUS SECTION 5, BELL: PCB A-577 | MT-NW, WOH
125 | 23-01456 | 12736651 | 05/11/2023 13:30 | 05/11/2023 14:30 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 | GEN, NOH, WOCN
126 | 23-01457 | 12736655 | 05/11/2023 14:30 | 05/11/2023 15:30 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 | GEN, NOH, WOCN
127 | 23-00013 | 11242330 | 05/12/2023 07:30 | 05/12/2023 15:00 | HANFORD-WAUTOMA NO 1 500KV LINE, INCLUDING HANFORD: PCB 4095 | HANFORD: PCB 4095, HANFORD-WAUTOMA NO 1 500KV LINE, INCLUDING HANFORD: PCB 4095 | NWACI, PDCI, WOLM, COI, NOH, WOM, SIG
128 | 23-05245 | 13139869 | 05/12/2023 08:00 | 05/26/2023 15:00 | DANEBO (EWEB)-LANE #1 115KV LINE INCLUDING LANE: PCB B-1620 AND THE 115KV A/B | LANE: 115KV AUX BUS, DANEBO (EWEB)-LANE #1 115KV LINE INCLUDING LANE: PCB B-1620 AND THE 115KV A/B, DANEBO-LANE 115KV LINE, LANE: EWEB (EUGENE OR) 115KV FEEDER 1 | EWEB
129 | 23-05260 | 13134487 | 05/12/2023 08:00 | 05/12/2023 16:00 | JOHN DAY: 500KV EAST BUS, INCLUDING PCB 4128 | JOHN DAY: 500KV EAST BUS, JOHN DAY: PCB 4128, INCLUDING PCB 4128 | WOJD, NWACI, WOS
130 | 23-04358 | 13039409 | 05/12/2023 08:00 | 05/12/2023 18:00 | COVINGTON: A-86 TERMINAL OF COVINGTON-DUWAMISH 1 230KV LINE | COVINGTON-DUWAMISH NO 1 230KV LINE, COVINGTON: A-86 TERMINAL OF COVINGTON-DUWAMISH 1 230KV LINE | NOEL, SOC
131 | 23-04123 |  | 05/14/2023 08:00 | 05/19/2023 16:00 | ASHE: A-809 TERMINAL OF, COLUMBIA GENERATING STATION-ASHE NO 2 230KV LINE | ASHE: A-809 TERMINAL OF, ASHE: PCB A-809, COLUMBIA GENERATING STATION-ASHE NO 2 230KV LINE | NOH, GEN, SIG
132 | 23-04124 |  | 05/14/2023 10:00 | 05/19/2023 15:00 | ASHE: PCB A-809 | ASHE: PCB A-809 | NOH
133 | 23-04127 | 13032973 | 05/14/2023 12:00 | 05/18/2023 16:00 | ASHE: 230KV MAIN BUS INCLUDING PCB A-924 | ASHE: 230KV MAIN BUS INCLUDING PCB A-924, ASHE: 230KV EAST MAIN BUS, ASHE: 230KV WEST MAIN BUS, ASHE: PCB A-924, ASHE TAP TO MIDWAY-HEW NO 2 230KV LINE, ASHE-WHITE BLUFFS NO 1 230KV LINE, WNP 1-ASHE NO 2 230KV LINE, ASHE: PCB A-921, ASHE: PCB A-401, ASHE: PCB A-809, ASHE: PCB A-920, ASHE: PCB A-894, ASHE: PCB A-892, ASHE: 230KV AUX BUS, ASHE: 230KV CAP GROUP 1, ASHE: 230KV CAP GROUP 2 | TCLA, NOH, COI, PDCI, GEN, FCRPS, LOAD
134 | 23-01665 | 12736670 | 05/14/2023 22:00 | 05/19/2023 17:00 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 | GEN, NOH, WOCN
135 | 23-06001 |  | 05/15/2023 06:00 | 05/26/2023 17:00 | -PACW- HANNA TAP-DIXONVILLE SECTION OF GRANTS PASS-DIXONVILLE 230KV LINE | -PACW- HANNA TAP-DIXONVILLE SECTION OF GRANTS PASS-DIXONVILLE 230KV LINE
136 | 23-05996 | 13176764 | 05/15/2023 06:00 | 05/26/2023 17:00 | PACW - Hanna Tap-Dixonville section of the Grants Pass-Dixonville | PACW - Hanna Tap-Dixonville section of the Grants Pass-Dixonville | NWACI, SWORE
137 | 23-01613 | 12735859 | 05/15/2023 07:00 | 05/16/2023 15:00 | RAVER: PCB 4789 | RAVER: PCB 4789 | NOEL, RP, SOC, WOCN
138 | 23-01949 | 12858231 | 05/15/2023 07:00 | 06/23/2023 14:00 | SPAR CANYON: 230KV REACTOR #1 INCLUDING LBD A-151 | SPAR CANYON: 230KV REACTOR #1 INCLUDING LBD A-151, SPAR CANYON: LBD A-151, SPAR CANYON: 230KV REACTOR 1
139 | 23-01704 | 12736212 | 05/15/2023 07:00 | 06/02/2023 17:00 | -USBR- COLUMBIA-GRAND COULEE NO 1 230KV LINE INCLUDING GRAND COULEE PCB 5686 | GRAND COULEE: PCB 5686, -USBR- COLUMBIA-GRAND COULEE NO 1 230KV LINE INCLUDING GRAND COULEE PCB 5686, COLUMBIA-GRAND COULEE NO 1 230KV LINE | NOH, WOCN, CI
140 | 23-01729 |  | 05/15/2023 07:00 | 06/02/2023 17:00 | COLUMBIA: A-160 TERMINAL OF THE COLUMBIA-GRAND COULEE #1 230KV LINE | COLUMBIA: A-160 TERMINAL OF THE COLUMBIA-GRAND COULEE #1 230KV LINE , COLUMBIA: PCB A-160 | CI, WOCN
141 | 23-05326 | 13135265 | 05/15/2023 07:00 | 05/18/2023 17:00 | -COE- DWORSHAK: 115/13.8KV BANK TW1 | DWORSHAK PH-AHSAHKA SECTION OF DWORSHAK PH-OROFINO NO 1 115KV LINE, -COE- DWORSHAK: 115/13.8KV BANK TW1, DWORSHAK PH: PCB XJ-7, DWORSHAK PH: 500/13.8KV BANK T1 | GEN, MT-NW, NOH, SIG, WOH, WOLM
142 | 23-03137 | 13166359 | 05/15/2023 07:30 | 05/15/2023 16:30 | INTALCO: PCB A-1012 | INTALCO: PCB A-1012 | BCHT, BCHW
143 | 23-01288 | 13012752 | 05/15/2023 08:00 | 05/18/2023 15:00 | WARNER: 230/115KV TRANSFORMER 1 | WARNER: 230/115KV TRANSFORMER 1 | NWACI
144 | 23-01226 | 13202169 | 05/15/2023 08:00 | 05/25/2023 10:00 | KEELER: PCB 4324 RELAYS | KEELER: PCB 4324 RELAYS, KEELER: PCB 4324 | SOA
145 | 23-04769 | 13077694 | 05/15/2023 08:00 | 05/17/2023 16:00 | REDMOND: A-262 TERMINAL OF REDMOND-PGE ROUND BUTTE NO 1 230KV LINE | REDMOND: PCB A-262, REDMOND: A-262 TERMINAL OF REDMOND-PGE ROUND BUTTE NO 1 230KV LINE, REDMOND-PGE ROUND BUTTE NO 1 230KV LINE | COR, SIG
146 | 23-00695 | 12593780 | 05/15/2023 08:00 | 05/25/2023 16:00 | CENTRAL FERRY: PCB 5432, INCLUDING 500KV REACTOR 1 | CENTRAL FERRY: PCB 5432, CENTRAL FERRY: PCB 5432, INCLUDING 500KV REACTOR 1, CENTRAL FERRY: 500KV REACTOR 1 | WOH, WOLM, SOA
147 | 23-05319 | 13160272 | 05/15/2023 08:00 | 05/15/2023 15:00 | LARENE-SPRINGHILL SECTION OF CRESTON-BELL NO 1 115KV LINE INCLUDING B-1932 LINE DISC | LARENE-SPRINGHILL SECTION OF CRESTON-BELL NO 1 115KV LINE INCLUDING B-1932 LINE DISC, LARENE-SPRINGHILL SECTION OF CRESTON-BELL NO 1 115KV LINE
148 | 23-02612 | 13060951 | 05/15/2023 08:00 | 05/18/2023 15:00 | KEELER: PCB A-858 | KEELER: PCB A-858 | SOA
149 | 23-04130 |  | 05/15/2023 08:00 | 05/17/2023 15:00 | ASHE TAP TO MIDWAY-HEW NO 2 230KV LINE INCLUDING ASHE PCB A-401 AND 230KV AUX BUS | ASHE TAP TO MIDWAY-HEW NO 2 230KV LINE, ASHE TAP TO MIDWAY-HEW NO 2 230KV LINE INCLUDING ASHE PCB A-401 AND 230KV AUX BUS, ASHE: 230KV AUX BUS, ASHE: PCB A-401 | GEN, LOAD, NOH, TCLA
150 | 23-04024 | 13059140 | 05/15/2023 08:00 | 05/18/2023 15:00 | SATSOP-SHELTON NO 1 230KV LINE | SATSOP-SHELTON NO 1 230KV LINE | LOAD, PA, SI
151 | 23-03325 | 12985544 | 05/15/2023 08:00 | 05/25/2023 18:00 | NORTH BONNEVILLLE-ROSS NO 1 230KV LINE INCLUDING SIFTON TAP | NORTH BONNEVILLLE-ROSS NO 1 230KV LINE INCLUDING SIFTON TAP, NORTH BONNEVILLE-ROSS NO 1 230KV LINE, SIFTON TAP TO NORTH BONNEVILLE-ROSS NO 1 230KV LINE | GEN, LOAD, WOCS, FCRPS, SOA
152 | 23-01220 | 12660992 | 05/15/2023 08:30 | 05/19/2023 17:30 | MALIN: 4065/4187/4075/4076 TERMINAL OF, MALIN-ROUND MOUNTAIN NO 1 500KV LINE | MALIN: PG&E ROUND MOUNTAIN 1 500KV LINE SERIES CAP GROUP, MALIN: 4065/4187/4075/4076 TERMINAL OF, MALIN-ROUND MOUNTAIN NO 1 500KV LINE | BCHT, BCHW, NI, NWACI, COI
153 | 23-00406 |  | 05/15/2023 09:00 | 06/16/2023 15:00 | -IPCO- HINES-WEST JOHN DAY 115KV LINE | -IPCO- HINES-WEST JOHN DAY 115KV LINE | ID-NW
154 | 23-02736 | 12888914 | 05/15/2023 12:00 | 06/08/2023 16:00 | BROADVIEW-GARRISON NO 1 500KV LINE, INCLUDING GARRISON PCB'S 4418, 4421 | GARRISON: 500KV REACTOR 1, BROADVIEW-GARRISON NO 1 500KV LINE, GARRISON: BROADVIEW 1 500KV LINE SERIES CAP GROUP 1, INCLUDING GARRISON PCB'S 4418, 4421, GARRISON: PCB 4418, GARRISON: PCB 4421 | MT-NW, GEN
155 | 23-02816 | 12888935 | 05/15/2023 12:00 | 06/08/2023 16:00 | GARRISON-TAFT NO 1 500KV LINE, INCLUDING GARRISON PCB'S 4415, 4418 | GARRISON-TAFT NO 1 500KV LINE, GARRISON: PCB 4415, INCLUDING GARRISON PCB'S 4415, 4418, GARRISON: PCB 4418, GARRISON: TAFT 1 500KV LINE SERIES CAP GROUP 1 | MT-NW, SIG
156 | 23-05335 | 13161169 | 05/16/2023 07:00 | 05/16/2023 16:00 | LARENE-BELL SECTION OF CRESTON BELL NO 1 115KV LINE INCLUDING SPRINGHILL TAP | LARENE-SPRINGHILL SECTION OF CRESTON-BELL NO 1 115KV LINE, LARENE-BELL SECTION OF CRESTON BELL NO 1 115KV LINE INCLUDING SPRINGHILL TAP, SPRINGHILL-BELL SECTION OF CRESTON-BELL NO 1 115KV LINE
157 | 23-04483 | 13048280 | 05/16/2023 07:00 | 05/25/2023 15:00 | SIFTON: PCB A-163 | SIFTON: PCB A-163 | SOA
158 | 23-01687 |  | 05/16/2023 07:30 | 05/18/2023 17:00 | JONES CANYON: 230KV REACTIVE BUS INCLUDING PCB'S A -1647, A-1682, A-1688, A-1689 AND THE 230KV CAP GROUP #1 SECTION 1 AND 2 | JONES CANYON: 230KV CAP GROUP 1 SECTION 1, JONES CANYON: 230KV REACTIVE BUS INCLUDING PCB'S A -1647, A-1682, A-1688, A-1689 AND THE 230KV CAP GROUP #1 SECTION 1 AND 2, JONES CANYON: 230KV CAP GROUP 1 SECTION 2, JONES CANYON: PCB A-1647, JONES CANYON: PCB A-1682, JONES CANYON: PCB A-1688, JONES CANYON: PCB A-1689 | WOCS
159 | 23-00378 | 12161590 | 05/16/2023 07:30 | 05/16/2023 15:00 | NORTH BONNEVILLE: PCB A-6 | NORTH BONNEVILLE: PCB A-6 | WOCS
160 | 23-03115 | 13166371 | 05/16/2023 07:30 | 05/16/2023 16:30 | INTALCO: PCB A-1016 | INTALCO: PCB A-1016 | BCHT, BCHW
161 | 23-06250 | 12975038 | 05/16/2023 08:00 | 05/19/2023 18:00 | SCL Viewland - SCL Canal 115kV Line | SCL Viewland - SCL Canal 115kV Line
162 | 23-05904 | 13226435 | 05/16/2023 08:00 | 05/16/2023 17:00 | WAUTOMA-ROCK CREEK NO 1 500KV LINE | WAUTOMA-ROCK CREEK NO 1 500KV LINE, WAUTOMA: PCB 5259, WAUTOMA: PCB 5256, ROCK CREEK: PCB 5294, ROCK CREEK: PCB 5288 | BCHT, BCHW, NI, NOH, SIG, WOJD, WOM, WOCN, RKCR
163 | 23-04604 | 13126628 | 05/17/2023 06:30 | 05/19/2023 17:00 | NILLE'S CORNER - B-2136 SECTION OF GRAND COULEE - FOSTER CREEK NO 1 115 KV LINE INCLUDING B-1294 DISCONNECT | NILLES CORNER: B-1294 LINE SECTIONALIZING DISC, NILLE'S CORNER - B-2136 SECTION OF GRAND COULEE - FOSTER CREEK NO 1 115 KV LINE INCLUDING B-1294 DISCONNECT, NILLES CORNER: DOUGLAS CO PUD 115KV FEEDER 1
164 | 23-05868 | 13202383 | 05/17/2023 07:00 | 05/18/2023 15:00 | COVINGTON: REACTIVE GROUP 1 SECTIONS 1, 2, 3, & 230KV REACTOR 1, INCLUDING PCB'S A-999, A-1003, A-1005, A-1007, & REACTIVE GROUP 1 PCB A-1004 | COVINGTON: PCB A-999, COVINGTON: REACTIVE GROUP 1 SECTIONS 1, 2, 3, & 230KV REACTOR 1, INCLUDING PCB'S A-999, A-1003, A-1005, A-1007, & REACTIVE GROUP 1 PCB A-1004, COVINGTON: PCB A-1007, COVINGTON: PCB A-1005, COVINGTON: PCB A-1003, COVINGTON: 230KV REACTIVE GROUP 1 CAP SECTION 1, COVINGTON: 230KV REACTIVE GROUP 1 CAP SECTION 2, COVINGTON: 230KV REACTIVE GROUP 1 CAP SECTION 3, COVINGTON: 230KV REACTIVE GROUP 1 REACTOR 1, COVINGTON: PCB A-1004 | RP, NOEL, SOC, WOCN, LOAD
165 | 23-01104 | 12593664 | 05/18/2023 07:00 | 05/18/2023 15:30 | COVINGTON: PCB A-1006 BFR | COVINGTON: PCB A-1006, COVINGTON: PCB A-1006 BFR | NOEL, SOC
166 | 23-00742 | 12735472 | 05/18/2023 08:00 | 05/18/2023 15:00 | BELL: 500/230KV TRANSFORMER 1 INCLUDING PCB'S 5307, 5310, A-577, AND A-552 | BELL: 500/230KV TRANSFORMER 1, BELL: 500/230KV TRANSFORMER 1 INCLUDING PCB'S 5307, 5310, A-577, AND A-552, BELL: PCB 5307, BELL: PCB 5310, BELL: PCB A-577, BELL: PCB A-552 | GEN, MT-NW, WOH
167 | 23-02362 | 12842609 | 05/18/2023 09:00 | 05/18/2023 11:00 | RAVER: PCB 4296 | RAVER: PCB 4296 | NOEL, RP, SOC
168 | 23-02363 | 12842610 | 05/18/2023 12:00 | 05/18/2023 14:00 | RAVER: PCB 4293 | RAVER: PCB 4293 | NOEL, RP, SOC, WOCN
169 | 23-04133 | 13033021 | 05/18/2023 16:01 | 05/19/2023 13:00 | ASHE: PCB A-924, ASHE: PCB A-809 | ASHE: PCB A-924, ASHE: PCB A-809 | COI, NOH, PDCI
170 | 23-00331 | 12011716 | 05/18/2023 16:30 | 05/18/2023 17:00 | BIG EDDY: PCB A-824 OF THE DALLES PH-BIG EDDY NO 4 230KV LINE | BIG EDDY: PCB A-824 OF THE DALLES PH-BIG EDDY NO 4 230KV LINE | GEN, FCRPS
171 | 23-05452 | 13145446 | 05/19/2023 06:00 | 05/21/2023 18:00 | SNO-KING: A-1417 TERMINAL AND MAPLE VALLEY: A-1124 TERMINAL OF, SNO-KING-MAPLE VALLEY NO 2 230KV LINE | SNO-KING: A-1417 TERMINAL AND MAPLE VALLEY: A-1124 TERMINAL OF, SNO-KING-MAPLE VALLEY NO 2 230KV LINE | NOEL, SOC, SIG
172 | 23-05450 | 13145446 | 05/19/2023 06:00 | 05/21/2023 18:00 | SNO-KING: A-1198 TERMINAL AND MAPLE VALLEY: A-1138 TERMINAL OF, SNO-KING-MAPLE VALLEY NO 1 230KV LINE | SNO-KING: A-1198 TERMINAL AND MAPLE VALLEY: A-1138 TERMINAL OF, SNO-KING-MAPLE VALLEY NO 1 230KV LINE | NOEL, SOC, SIG
173 | 23-06252 | 12975044 | 05/20/2023 08:00 | 05/23/2023 18:00 | SCL Shoreline - SCL Viewland 115kV Line | SCL Shoreline - SCL Viewland 115kV Line
174 | 23-04209 | 13060290 | 05/21/2023 08:00 | 05/27/2023 15:00 | B-599 TERMINAL OF CGS BACKUP BANK ENERGY NORTHWEST 115KV FEEDER NO 1 | B-599 TERMINAL OF CGS BACKUP BANK ENERGY NORTHWEST 115KV FEEDER NO 1, ENERGY NORTHWEST 115KV FEEDER NO 1, CGS BACKUP BANK TAP TO BENTON-451B NO 1 115KV LINE | TCLA, GEN, LOAD
175 | 23-00127 | 11597819 | 05/21/2023 22:00 | 05/21/2023 22:30 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 | GEN, NOH, WOCN
176 | 23-00332 | 12113155 | 05/22/2023 07:00 | 06/01/2023 17:00 | THE DALLES PH: 230/13.2KV BANK 7 | THE DALLES PH: 230/13.2KV BANK 7
177 | 23-00333 | 12011721 | 05/22/2023 07:00 | 05/22/2023 07:30 | BIG EDDY: PCB A-836 OF THE DALLES PH-BIG EDDY NO 5 230KV LINE | BIG EDDY: PCB A-836 OF THE DALLES PH-BIG EDDY NO 5 230KV LINE, THE DALLES PH: 230/13.2KV BANK 7, THE DALLES PH: 230/13.2KV BANK 8 | GEN, FCRPS, BGEDY
178 | 23-05422 | 13191175 | 05/22/2023 07:00 | 05/25/2023 16:00 | MARION-LANE NO 1 500KV LINE, (UNGROUNDED AT MARION) | MARION-LANE NO 1 500KV LINE, LANE: 500/230KV TRANSFORMER 3, (UNGROUNDED AT MARION) | NWACI, SIG, EWEB, SCORC
179 | 23-00681 | 12751723 | 05/22/2023 07:00 | 05/22/2023 11:30 | COVINGTON: 230KV REACTIVE GROUP 1 CAP SECTIONS 1, 2 AND 3 INCLUDING PCB A-999, PCB A-1005, PCB A-1007, PCB A-1003 AND 230KV REACTOR 1 | COVINGTON: 230KV REACTIVE GROUP 1 CAP SECTIONS 1, 2 AND 3 INCLUDING PCB A-999, PCB A-1005, PCB A-1007, PCB A-1003 AND 230KV REACTOR 1, COVINGTON: 230KV REACTIVE GROUP 1 CAP SECTION 1, COVINGTON: 230KV REACTIVE GROUP 1 CAP SECTION 2, COVINGTON: 230KV REACTIVE GROUP 1 CAP SECTION 3, COVINGTON: 230KV REACTIVE GROUP 1 REACTOR 1, COVINGTON: PCB A-999, COVINGTON: PCB A-1005, COVINGTON: PCB A-1007, COVINGTON: PCB A-1003, COVINGTON: PCB A-1004 | NOEL, SOC, WOCN, LOAD, RP
180 | 23-00520 | 12219187 | 05/22/2023 07:00 | 05/23/2023 18:00 | SCHULTZ-WAUTOMA NO 1 500KV LINE | SCHULTZ-WAUTOMA NO 1 500KV LINE | BCHT, BCHW, IROL, NI, NOH, SIG, WOCN
181 | 23-04673 | 13077424 | 05/22/2023 07:30 | 06/06/2023 17:00 | LONGVIEW: PCB A-646 INCLUDING LONGVIEW-CHEHALIS 1&3 230KV LINE | LONGVIEW-CHEHALIS NO 1&3 230KV LINE, LONGVIEW: PCB A-646 INCLUDING LONGVIEW-CHEHALIS 1&3 230KV LINE, LONGVIEW: PCB A-646, CHEHALIS: PCB A-224, CHEHALIS: PCB A-48 | LOAD, NOEL, RP, SOA, PA
182 | 23-02364 | 13059728 | 05/22/2023 08:00 | 05/26/2023 15:00 | PONDEROSA-PILOT BUTTE NO 1 230KV LINE | PONDEROSA-PILOT BUTTE NO 1 230KV LINE, PONDEROSA: PCB A-1821, PONDEROSA: PCB A-1824 | COR
183 | 23-01944 | 12810652 | 05/22/2023 08:00 | 05/25/2023 16:00 | MARION: 500KV REACTOR 2 INCLUDING PCB 4020 | MARION: 500KV REACTOR 2, MARION: 500KV REACTOR 2 INCLUDING PCB 4020, MARION: PCB 4020 | COI, NWACI, PDCI
184 | 23-04025 | 13042801 | 05/22/2023 08:00 | 05/25/2023 15:00 | SATSOP-SHELTON NO 1 230KV LINE | SATSOP-SHELTON NO 1 230KV LINE | LOAD, PA, SI
185 | 23-00239 | 12118767 | 05/22/2023 08:00 | 05/23/2023 15:00 | OSTRANDER: 500KV CAP GROUP 3 INCLUDING PCB 5097 | OSTRANDER: 500KV CAP GROUP 3 INCLUDING PCB 5097, OSTRANDER: PCB 5097, OSTRANDER: RAS AC-A OSTRANDER SHUNT CAPS INSERT CKT 7371, OSTRANDER: RAS AC-B OSTRANDER SHUNT CAPS INSERT CKT 7376 | NWACI, PDCI, WOCS, COI
186 | 23-00067 | 12086691 | 05/22/2023 08:30 | 05/25/2023 15:30 | MCMINNVILLE: PCB B-381 | WALNUT CITY: MCMINNVILLE W&L 115KV FEEDER 1, MCMINNVILLE: PCB B-381
187 | 23-01519 | 12782906 | 05/22/2023 08:30 | 05/25/2023 15:00 | CAPTAIN JACK: PCB 4977 | CAPTAIN JACK: PCB 4977 | NWACI, PDCI, COI
188 | 23-00482 | 12220068 | 05/23/2023 07:00 | 05/25/2023 16:00 | PAUL: PCB 4542 | PAUL: PCB 4542 | GEN, NWACI, PDCI, COI, WOCS, SOA
189 | 23-04233 | 13042417 | 05/23/2023 07:00 | 05/23/2023 14:00 | DRUMMOND - MACKS INN #1 115KV LINE INCLUDING DRUMMOND: 115KV AUX BUS AND PCB B-1502 | DRUMMOND: 115KV AUX BUS, DRUMMOND - MACKS INN #1 115KV LINE INCLUDING DRUMMOND: 115KV AUX BUS AND PCB B-1502, DRUMMOND-MACKS INN NO 1 115KV LINE, MACKS INN-MADISON NO 1 115KV LINE, DRUMMOND: PCB B-1502 | SEIL
190 | 23-04341 | 13048462 | 05/23/2023 07:30 | 05/23/2023 12:00 | SLATT: 230KV CAP GROUP 2 SECTION 2 INCLUDING PCB A -1798 | SLATT: PCB A-1798, SLATT: 230KV CAP GROUP 2 SECTION 2 INCLUDING PCB A -1798, SLATT: 230KV CAP GROUP 2 SECTION 2 | WOJD, GEN
191 | 23-00680 | 12752594 | 05/23/2023 07:30 | 05/23/2023 12:00 | TACOMA: 230KV CAP GROUP 3 SECTION 1, & 2 INCLUDING LBD A-1078, LBD 1079 | TACOMA: LBD A-1078, TACOMA: 230KV CAP GROUP 3 SECTION 1, & 2 INCLUDING LBD A-1078, LBD 1079, TACOMA: LBD A-1079, TACOMA: 230KV CAP GROUP 3 SECTION 2 | NOEL, RP, SOC, WOCN
192 | 23-04343 | 13048465 | 05/23/2023 11:00 | 05/23/2023 16:00 | SLATT: PCB A-1785 | SLATT: PCB A-1785 | WOJD
193 | 23-01483 | 12752577 | 05/24/2023 07:00 | 05/24/2023 15:00 | BELL: 500KV REACTOR 1 INCLUDING PCB 4559 | BELL: 500KV REACTOR 1, BELL: 500KV REACTOR 1 INCLUDING PCB 4559, BELL: PCB 4559 | MT-NW, WOH
194 | 23-05630 | 13171108 | 05/24/2023 07:00 | 05/24/2023 12:00 | MORROW FLAT: PCB B-2214 | MORROW FLAT: PCB B-2214 | WOM
195 | 23-04301 | 13099285 | 05/24/2023 07:30 | 05/24/2023 16:00 | BELLINGHAM: 230KV MAIN BUS | BELLINGHAM: 230KV MAIN BUS, BELLINGHAM: 230/115KV TRANSFORMER 1, BELLINGHAM: 230/115KV TRANSFORMER 2, BELLINGHAM-CUSTER NO 1 230KV LINE, SEDRO WOOLLEY-BELLINGHAM NO 1 230KV LINE, BELLINGHAM: 230KV MAIN BUS, BELLINGHAM: 230KV AUX BUS | LOAD, NOEL, SOC
196 | 23-00682 | 12752642 | 05/24/2023 08:00 | 05/24/2023 15:00 | MAPLE VALLEY: 230KV CAP GROUP 1 SECT 1, 2, 3, 4 INCL LBDs A-1101, A-1102, A-1103, & A-1104 | MAPLE VALLEY: 230KV CAP GROUP 1 SECT 1, 2, 3, 4 INCL LBDs A-1101, A-1102, A-1103, & A-1104, MAPLE VALLEY: LBD A-1101, MAPLE VALLEY: LBD A-1102, MAPLE VALLEY: LBD A-1103, MAPLE VALLEY: LBD A-1104, MAPLE VALLEY: PCB A-1146, MAPLE VALLEY: 230KV CAP GROUP 1 SECTION 1, MAPLE VALLEY: 230KV CAP GROUP 1 SECTION 2, MAPLE VALLEY: 230KV CAP GROUP 1 SECTION 3, MAPLE VALLEY: 230KV CAP GROUP 1 SECTION 4 | NOEL, SOC, WOCN, NI
197 | 23-05631 | 13171051 | 05/24/2023 11:00 | 05/24/2023 16:00 | MORROW FLAT: PCB B-2227 | MORROW FLAT: PCB B-2227
198 | 23-01926 | 12810116 | 05/25/2023 07:00 | 05/25/2023 08:00 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 | GEN, NOH, WOCN
199 | 23-01523 | 12667380 | 05/25/2023 07:00 | 05/25/2023 15:00 | PORT ANGELES: 115KV CAP GROUP 1 INCLUDING PCB B-648 & LBD'S B-1883 & B-645 | PORT ANGELES: 115KV CAP GROUP 1 INCLUDING PCB B-648 & LBD'S B-1883 & B-645, PORT ANGELES: PCB B-648, PORT ANGELES: 115KV CAP GROUP 1 SECTION 1, PORT ANGELES: 115KV CAP GROUP 1 SECTION 2 | WOCN
200 | 23-05632 | 13171298 | 05/25/2023 07:00 | 05/25/2023 12:00 | MORROW FLAT: PCB A-1877 | MORROW FLAT: PCB A-1877 | WOM
201 | 23-00684 | 12752713 | 05/25/2023 07:30 | 05/25/2023 12:00 | Raver: PCBs 4914 and 4921 including 500kV Cap Group 1 Sections 1, 2, 3 and 500kV Reactive Bus | RAVER: PCB 4914, Raver: PCBs 4914 and 4921 including 500kV Cap Group 1 Sections 1, 2, 3 and 500kV Reactive Bus, RAVER: PCB 4917, RAVER: PCB 4919, RAVER: PCB 4722, RAVER: PCB 4921, RAVER: 500KV CAP GROUP 1 SECTION 1, RAVER: 500KV CAP GROUP 1 SECTION 2, RAVER: 500KV CAP GROUP 1 SECTION 3 | NOEL, RP, SOC, IROL, WOCN
202 | 23-01927 | 12810138 | 05/25/2023 08:00 | 05/25/2023 09:00 | GRAND COULEE: PCB 2092, GRAND COULEE: PCB 2096 | GRAND COULEE: PCB 2092, GRAND COULEE: PCB 2096 | GEN, NOH, WOCN
203 | 23-04473 | 13060216 | 05/25/2023 08:00 | 05/25/2023 15:00 | SIFTON: PCB B-1509 | SIFTON: PCB B-1509, SIFTON: 115KV AUX BUS
204 | 23-01928 | 12810144 | 05/25/2023 09:00 | 05/25/2023 10:00 | GRAND COULEE: PCB 2292, GRAND COULEE: PCB 2296 | GRAND COULEE: PCB 2292, GRAND COULEE: PCB 2296 | GEN, NOH, WOCN
205 | 23-01929 | 12810148 | 05/25/2023 10:00 | 05/25/2023 11:00 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 | GEN, NOH, WOCN
206 | 23-05575 | 13202868 | 05/25/2023 10:00 | 05/25/2023 12:00 | KEELER: PCB 4322 | KEELER: PCB 4322 | SOA
207 | 23-01930 | 12810154 | 05/25/2023 11:00 | 05/25/2023 12:00 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 | GEN, NOH, WOCN
208 | 23-05634 | 13171370 | 05/25/2023 11:00 | 05/25/2023 16:00 | MORROW FLAT: PCB A-1871 | MORROW FLAT: PCB A-1871
209 | 23-05586 | 13191242 | 05/26/2023 08:00 | 05/26/2023 12:00 | ECHO LAKE: 500KV CAP GROUP 1 INCLUDING PCB 5125 | ECHO LAKE: PCB 5125, ECHO LAKE: 500KV CAP GROUP 1 INCLUDING PCB 5125, ECHO LAKE: 500KV CAP GROUP 1 | BCHT, BCHW, NOEL, SOC, WOCN, NI, IROL
210 | 23-05588 | 13191217 | 05/26/2023 08:00 | 05/26/2023 12:00 | ECHO LAKE: 500KV CAP GROUP 2 INCLUDING PCB 5127 | ECHO LAKE: PCB 5127, ECHO LAKE: 500KV CAP GROUP 2 INCLUDING PCB 5127, ECHO LAKE: 500KV CAP GROUP 2 | BCHT, NOEL, SOC, WOCN, NI, BCHW, IROL
211 | 23-00128 | 11597829 | 05/26/2023 16:30 | 05/26/2023 17:00 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 | GEN, NOH, WOCN
212 | 23-01706 | 12736687 | 05/29/2023 22:00 | 06/30/2023 19:00 | -USBR- GRAND COULEE: 230/115KV TRANSFORMER KX2A INCLUDING PCB'S 5182 AND 2372 | -USBR- GRAND COULEE: 230/115KV TRANSFORMER KX2A INCLUDING PCB'S 5182 AND 2372, GRAND COULEE: 230/115KV BANK KX2A SWITCHYARD TIE, GRAND COULEE: PCB 2372, GRAND COULEE: PCB 5182 | NOH, OKLA, LOAD, WOCN, COI, NWACI, PDCI
213 | 23-05719 | 13176863 | 05/30/2023 06:00 | 05/31/2023 17:00 | PAC - GRANTS PASS-GLENDALE SECTION OF GRANTS PASS-DIXONVILLE 230KV LINE | PAC - GRANTS PASS-GLENDALE SECTION OF GRANTS PASS-DIXONVILLE 230KV LINE
214 | 23-05532 | 13195255 | 05/30/2023 07:00 | 05/31/2023 16:00 | SHELTON: PCB A-1667 | SHELTON: PCB A-1667 | PA, RP
215 | 23-05361 | 13203143 | 05/30/2023 07:00 | 05/30/2023 16:30 | SNOHOMISH: 230KV MAIN BUS SECTION 4, INCLUDING PCB'S A-197, A-184, A-182, A-181, A-178 AND A-1040 | SNOHOMISH: PCB A-1040, SNOHOMISH: 230KV MAIN BUS SECTION 4, INCLUDING PCB'S A-197, A-184, A-182, A-181, A-178 AND A-1040, SNOHOMISH: PCB A-184, SNOHOMISH: PCB A-181, SNOHOMISH: PCB A-178, SNOHOMISH: PCB A-182, SNOHOMISH: PCB A-197, SNOHOMISH: 230KV AUX BUS SECTION 4, SNOHOMISH: 230/115KV TRANSFORMER 1, SNOHOMISH: 115KV CAP GROUP 2 SECTION 1, SNOHOMISH: 115KV CAP GROUP 2 SECTION 2, MONROE-SNOHOMISH NO 1&2 230KV LINE | NOEL, SOC, WOCN, BCHT, BCHW, LOAD
216 | 23-00130 | 11575566 | 05/30/2023 07:00 | 06/04/2023 17:00 | ASHE-MARION NO 2 500KV LINE | ASHE: 500KV REACTOR 1, ASHE-MARION NO 2 500KV LINE, ASHE: PCB 4907 | NWACI, BCHT, BCHW, NI, SIG, WOCS, WOJD, WOM, FCRPS, NOH
217 | 23-00129 | 11575538 | 05/30/2023 07:00 | 06/04/2023 17:00 | ASHE-SLATT NO 1 500KV LINE | ASHE-SLATT NO 1 500KV LINE | BCHT, BCHW, NI, NOH, SIG, WOM, WOS
218 | 23-04475 | 13048225 | 05/30/2023 07:00 | 06/15/2023 15:00 | SIFTON: NORTH BONNEVILLE - ROSS NO 2 230KV LINE INCLUDING SIFTON TAP LINE RELAYS AND THE 230/115KV XFMR NO.1 RELAYS | SIFTON: 230KV WEST MAIN BUS, SIFTON: NORTH BONNEVILLE - ROSS NO 2 230KV LINE INCLUDING SIFTON TAP LINE RELAYS AND THE 230/115KV XFMR NO.1 RELAYS, NORTH BONNEVILLE-ROSS NO 2 230KV LINE, SIFTON: 230/115KV TRANSFORMER 1, SIFTON TAP TO NORTH BONNEVILLE-ROSS NO 2 230KV LINE, SIFTON: PCB B-1511, ROSS: PCB A-22, NORTH BONNEVILLE: PCB A-14 | SOA, GEN, LOAD, WOCS, FCRPS
219 | 23-01218 | 12685390 | 05/30/2023 07:00 | 06/16/2023 17:00 | CLYMER-MOXEE SECTION OF ELLENSBURG-MOXEE NO 1 115KV LINE | CLYMER-MOXEE SECTION OF ELLENSBURG-MOXEE NO 1 115KV LINE, MOXEE: PCB B-912 | TCLA
220 | 23-05110 | 13109692 | 05/30/2023 07:30 | 06/01/2023 16:00 | ADDY-CHEWELAH SECTION OF ADDY-AVISTA DEVIL'S GAP 1 115KV LINE INCLUDING ADDY: PCB B-1137 AND 115KV AUX BUS | ADDY-AVA DEVILS GAP NO 1 115KV LINE, ADDY-CHEWELAH SECTION OF ADDY-AVISTA DEVIL'S GAP 1 115KV LINE INCLUDING ADDY: PCB B-1137 AND 115KV AUX BUS, ADDY: PCB B-1137, ADDY: 115KV AUX BUS, ADDY: PCB B-1141
221 | 23-00251 | 13065071 | 05/30/2023 08:00 | 06/01/2023 15:00 | LAPINE: PCB A-1498 | LAPINE: 230/115KV TRANSFORMER 2, LAPINE: PCB A-1498, LAPINE: 230KV AUX BUS | COR
222 | 23-00879 | 12484181 | 05/30/2023 08:00 | 06/01/2023 17:00 | BIG EDDY-MCLOUGHLIN NO 1&2 230KV LINE | BIG EDDY-MCLOUGHLIN NO 1&2 230KV LINE | PDCI, SOA, WOJD, BGEDY
223 | 23-06139 | 13226179 | 05/30/2023 08:00 | 05/31/2023 16:00 | BELLINGHAM: 230/115KV TRANSFORMER 2, INCLUDING PCB'S A-487 & B-933 | BELLINGHAM: 230/115KV TRANSFORMER 2, BELLINGHAM: PCB A-487, BELLINGHAM: PCB B-933, INCLUDING PCB'S A-487 & B-933 | LOAD, NOEL, SOC, BCHW
224 | 23-01184 | 12777119 | 05/30/2023 10:00 | 05/30/2023 11:00 | MURRAY: 115KV CAP GROUP 1 SECTIONS 1 & 2 INCLUDING LBD'S B-1755, B-1756 AND 115KV REACTIVE BUS | MURRAY: PCB B-1745, MURRAY: 115KV CAP GROUP 1 SECTIONS 1 & 2 INCLUDING LBD'S B-1755, B-1756 AND 115KV REACTIVE BUS, MURRAY: LBD B-1755, MURRAY: LBD B-1756, MURRAY: 115KV CAP GROUP 1 SECTION 1, MURRAY: 115KV CAP GROUP 1 SECTION 2
225 | 23-03622 | 13042486 | 05/31/2023 07:00 | 05/31/2023 14:00 | DRUMMOND: 115KV AUX BUS INCLUDING 115/46KV TRANSFORMER #3 AND 115KV BUS TIE PCB B-1686 | DRUMMOND: 115KV AUX BUS INCLUDING 115/46KV TRANSFORMER #3 AND 115KV BUS TIE PCB B-1686, DRUMMOND: 115KV AUX BUS, DRUMMOND: 115/46KV TRANSFORMER 3, DRUMMOND: PCB B-1686, DRUMMOND: PCB B-1684 | SEIL
226 | 23-04909 | 13109612 | 05/31/2023 07:00 | 05/31/2023 16:00 | ALVEY: 230KV CENTER MAIN BUS INCLUDING PCBS A-247 AND A-332 | ALVEY: PCB A-247, ALVEY: 230KV CENTER MAIN BUS INCLUDING PCBS A-247 AND A-332, ALVEY: PCB A-332 | SCORC
227 | 23-01740 | 12782517 | 05/31/2023 08:00 | 06/01/2023 18:00 | BIG EDDY: 500/230KV TIE NO 1 500KV LINE RELAYS (FORCES OUT TIE 1, BANK 2 & PCB'S ) | BIG EDDY 500/230KV TIE NO 1 500KV LINE, BIG EDDY: 500/230KV TIE NO 1 500KV LINE RELAYS (FORCES OUT TIE 1, BANK 2 & PCB'S ), BIG EDDY: 500/230KV TRANSFORMER 2, BIG EDDY: PCB 4866, BIG EDDY: PCB 4870, BIG EDDY: 500/230KV TRANSFORMER 2 RELAYS, BIG EDDY: 500/230KV TRANSFORMER 2/TIE LINE 1 RELAYS | GEN, NWACI, PDCI, WOJD, COI, SIG, FCRPS, BGEDY, SOA
228 | 23-03320 | 12971679 | 05/31/2023 08:00 | 06/15/2023 18:00 | NORTH BONNEVILLE-TROUTDALE NO 1 230KV LINE | NORTH BONNEVILLE-TROUTDALE NO 1 230KV LINE | GEN, LOAD, WOCS, FCRPS
229 | 23-05365 | 13202431 | 05/31/2023 08:00 | 05/31/2023 16:00 | SNOHOMISH: PCB A-1040 INCLUDING 230KV REACTIVE BUS | SNOHOMISH: 230KV CAP GROUP 3 SECTION 1, SNOHOMISH: PCB A-1040 INCLUDING 230KV REACTIVE BUS, SNOHOMISH: 230KV CAP GROUP 3 SECTION 2 | NOEL, SOC, WOCN