## Request List
Row | Request# | CAISO# | Start | End | Main Element Impacted | Path Affected
1 | 21-01711 | 9741845 | 02/03/2021 09:00 | 02/28/2030 17:00 | -USBR- GRAND COULEE 287/230KV TRANSFORMER KX-17-A (OLYMPIA-GRAND COULEE NO 1 287KV LINE OPERATING AT 230KV) | NOEL, PA, RP, SOC, WOCN, IROL, NOH, OKLA
2 | 22-06836 | 11597875 | 04/06/2022 12:25 | 05/31/2023 15:00 | OSTRANDER-TROUTDALE 1 500KV LINE INCLUDING TROUTDALE: 500/230KV TRANSFORMER BANK 8 | SIG, SOA, WOCS, SIG, WOCS, SOA
3 | 22-13128 | 12651062 | 08/17/2022 08:00 | 05/31/2023 23:59 | MAPLE VALLEY: 500/230KV TRANSFORMER 2, (DERATED) | IROL, NOEL, SIG, SOC, WOCN
4 | 22-17044 | 12730571 | 11/16/2022 14:00 | 11/16/2023 19:00 | (EWEB) CURRIN: PCB'S 4590 & 4584 | NWACI, PDCI, COI
5 | 23-01684 | 11460660 | 02/03/2023 15:30 | 10/10/2023 09:00 | PG&E - TABLE MOUNTAIN SERIES CAP 1 (ROUND MOUNTAIN-TABLE MOUNTAIN #1 500KV LINE) | COI, NWACI
6 | 23-03222 | 11461724 | 02/10/2023 18:30 | 10/19/2023 09:00 | PG&E- TABLE MOUNTAIN: ROUND MOUNTAIN 500KV LINE SERIES CAP GROUP 2 | NWACI, COI
7 | 23-05354 |  | 03/13/2023 06:00 | 08/18/2023 17:00 | -PACW- PACW KNOTT-PGE NORTHERN SECTION OF THE KNOTT-ST JOHNS 57KV LINE | SOA
8 | 23-04279 | 13037076 | 03/20/2023 15:30 | 05/12/2023 15:00 | JOHN DAY: PCB 4128, INCLUDING MOD 4127 | NWACI, WOJD, WOS
9 | 23-00011 | 11242268 | 03/20/2023 17:30 | 05/11/2023 07:30 | HANFORD: PCB 4095 INCLUDING MODS 4094 & 4096 | NWACI, PDCI, WOLM, COI, NOH, WOM
10 | 23-00462 | 12289653 | 04/04/2023 22:00 | 05/16/2023 19:00 | GRAND COULEE: 500/230KV CSY TIE BANK, INCLUDING 500KV PCB'S 8692,1996 & 230KV PCB 6582 | GEN, NOH, WOCN, PDCI, SIG, COI, FCRPS, NWACI
11 | 23-05041 |  | 04/11/2023 04:00 | 05/14/2023 20:00 | LADWP- ADELANTO-TOLUCA 1 500KV LINE | PDCI
12 | 23-03864 | 13005625 | 04/12/2023 15:00 | 05/02/2023 15:00 | BETTAS ROAD: 230KV EAST BUS INCLUDING PCB'S A-3046 & A-3043, THE COLUMBIA-BETTAS ROAD NO 1 230KV LINE AND THE KITTITAS PUD BETTAS ROAD 230KV LINE TO THE BB1-1 DISCONNECT | NOEL, CI, NOH, SOC, WOCN, IROL
13 | 23-03525 | 12976427 | 04/17/2023 17:01 | 05/04/2023 08:30 | LONGVIEW-ALLSTON #1 230KV LINE INCLUDING LONGVIEW: PCB A-100, A-100 M/B DISC, AND 230KV SOUTH AUX BUS | SOA
14 | 23-01686 | 12735737 | 04/20/2023 06:30 | 05/12/2023 17:00 | GRAND COULEE: PCB 5782 | NOH, WOCN, COI, NWACI, PDCI
15 | 23-05080 | 13126620 | 04/24/2023 07:00 | 05/10/2023 16:00 | LANE: 115KV SOUTH MAIN BUS INCLUDING PCB'S B-1614, B-1612, B-1610 AND B-1608 | LOAD, EWEB, SCORC
16 | 23-00530 | 12570534 | 04/24/2023 08:00 | 05/26/2023 16:00 | HANFORD-WAUTOMA NO 2 500KV LINE | NOH, NWACI, PDCI, SIG, COI
17 | 23-04284 |  | 04/24/2023 08:00 | 05/05/2023 15:00 | -PGE- MURRAYHILL- SHERWOOD NO 1 & 2 230KV LINES | SOA
18 | 23-02735 | 12888833 | 04/24/2023 12:00 | 05/12/2023 11:00 | GARRISON-TAFT NO 2 500KV LINE, INCLUDING GARRISON PCB'S 4360, 4463 | MT-NW, SIG
19 | 22-02103 | 10879173 | 05/01/2023 01:00 | 05/12/2023 20:00 | GRAND COULEE: PCB 2296, PCB 2292 | GEN, NOH, WOCN
20 | 23-01241 | 12734923 | 05/01/2023 06:00 | 05/26/2023 17:00 | ROCK CREEK: 500/230KV TRANSFORMER 1, INCLUDING 500/230 TRANSFORMER SPARE PHASE, PCB'S 5291, 5294, A-1704, A-1711, A-1714 AND PACIFICORP 230KV FEEDER #1 TO IMRIE | GEN, RKCR
21 | 23-01178 | 12695006 | 05/01/2023 07:00 | 05/06/2023 16:00 | MONROE-SNOHOMISH NO 1&2 230KV LINE, INCLUDING HORSE RANCH TAP | NOEL, SOC, BCHT, BCHW, SIG
22 | 23-01171 | 12695240 | 05/01/2023 07:00 | 05/03/2023 16:00 | BELL: PCB 5316 | MT-NW, WOH
23 | 23-01389 | 12694988 | 05/01/2023 07:00 | 05/01/2023 15:30 | CUSTER: PCB 4482 | BCHT, BCHW, NOEL, SOC, NI
24 | 23-00445 | 12182162 | 05/01/2023 08:00 | 05/02/2023 16:00 | JOHN DAY-GRIZZLY NO 1 500KV LINE, INCLUDING GRIZZLY: PCB 4058 | BCHT, BCHW, NI, NWACI, PDCI, SIG, WOJD, COI
25 | 23-00739 | 12690366 | 05/01/2023 08:00 | 05/02/2023 15:00 | BELL: PCB 5307, BFR AND DIFFERENTIAL RELAY | MT-NW, WOH
26 | 23-00784 | 12695352 | 05/01/2023 08:00 | 05/04/2023 16:00 | MARION: PCB 4380 | NWACI, PDCI, COI
27 | 23-01403 | 12695959 | 05/01/2023 08:00 | 05/04/2023 15:00 | CAPTAIN JACK: PCB 4983 | NWACI, PDCI, COI
28 | 23-05407 | 13190799 | 05/01/2023 08:00 | 05/01/2023 15:00 | MURRAY: PCB A-1516 INCLUDING 230KV AUX BUS | BCHT, BCHW, NOEL, SOC
29 | 23-04890 | 13104745 | 05/01/2023 08:00 | 05/04/2023 15:00 | USK-BOUNDARY 1 230KV LINE INCLUDING CUSICK SUBSTATION, ADDY-CUSICK 1 230KV LINE, USK: PCB'S A-953 & A-955, BOUNDARY: PCB A-1235 | SOB
30 | 23-02492 | 12880817 | 05/01/2023 08:00 | 05/02/2023 16:00 | RILEY-STARVATION RIDGE SECTION OF BRASADA-HARNEY NO 1 115KV LINE | ID-NW, JDAY
31 | 23-01558 | 12810676 | 05/01/2023 08:00 | 05/01/2023 09:30 | HARVALUM: 230KV CAP GROUP 1 | WOM
32 | 23-05271 |  | 05/01/2023 08:00 | 05/11/2023 16:00 | DORENA TAP TO THE ALVEY-MARTIN CREEK NO 1 115KV LINE INCLUDING B-1577 DISCONNECT | SCORC
33 | 23-00234 | 12118758 | 05/01/2023 08:30 | 05/02/2023 15:00 | OSTRANDER: PCB 5134 | WOCS
34 | 23-02352 |  | 05/02/2023 07:00 | 05/03/2023 16:00 | MAPLE VALLEY: 500/230KV TRANSFORMER 2 | IROL, NOEL, SIG, SOC, WOCN
35 | 23-01089 | 12622881 | 05/02/2023 07:00 | 05/02/2023 16:00 | ABERDEEN: 230/115KV TRANSFORMER 4 AND THE 115KV AUX BUS | LOAD, PA, SI
36 | 23-04063 | 13029033 | 05/02/2023 07:00 | 05/02/2023 16:30 | LEBANON: AIRPORT-LEBANON SECTION OF ALBANY-LEBANON NO 1 115KV LINE INCLUDING PCB B-848 AND THE 115KV AUX BUS | SLAL
37 | 23-05275 |  | 05/02/2023 07:00 | 05/02/2023 16:00 | SATSOP-ABERDEEN NO 2 230 KV LINE INCLUDING PCBS A-625 AND A-630 | PA, LOAD
38 | 23-01384 | 12695541 | 05/02/2023 07:30 | 05/03/2023 15:00 | MONROE: PCB 5053 | BCHT, BCHW, NOEL, SOC, WOCN, NI
39 | 23-05678 | 13191083 | 05/02/2023 08:00 | 05/03/2023 15:00 | SCHULTZ 500KV REACTOR #1, INCLUDING PCB 5106 | WOCN
40 | 23-01568 | 12873306 | 05/02/2023 08:00 | 05/02/2023 15:00 | DWORSHAK: TAFT 1 500KV LINE SERIES CAP GROUP 1, INCLUDING PCB 4765 | MT-NW, WOH, WOLM, SLAL
41 | 23-03319 | 12969499 | 05/02/2023 08:00 | 05/11/2023 18:00 | NORTH BONNEVILLE-TROUTDALE NO 1 230KV LINE | GEN, LOAD, WOCS, FCRPS
42 | 23-02663 | 12858455 | 05/02/2023 08:00 | 05/25/2023 16:00 | REDMOND: A-262 TERMINAL OF THE REDMOND-PGE ROUND BUTTE 230KV LINE | SIG, COR
43 | 23-04068 | 13032348 | 05/03/2023 07:00 | 05/03/2023 16:30 | LEBANON: 115KV MAIN BUS INCLUDING PCB'S B-848, B-850, B-1950 AND THE 115KV CAP GROUP NO 1 INCLUDING PCB B-1951 | SLAL
44 | 23-00740 | 12690371 | 05/03/2023 08:00 | 05/04/2023 15:00 | BELL: PCB 5310, BFR AND DIFFERENTIAL RELAY | MT-NW, WOH
45 | 23-04934 | 13115048 | 05/03/2023 08:00 | 05/04/2023 16:00 | HOLCOMB: PCB B-440 | PA, RP
46 | 23-01409 | 12690849 | 05/03/2023 16:00 | 06/14/2023 16:00 | GRIZZLY: PCB 4058, GRIZZLY: MOD 4057 | NWACI, WOJD, COI
47 | 23-05402 | 13191146 | 05/04/2023 07:00 | 05/04/2023 16:00 | SNO-KING: PCB A-1205 | BCHT, BCHW, NOEL, SOC
48 | 23-04070 | 13032429 | 05/04/2023 07:00 | 05/04/2023 16:30 | LEBANON: FOSTER TAP-LEBANON SECTION OF GREEN PETER-LEBANON NO 1 115KV LINE INCLUDING PCB B-850 AND THE LEBANON 115KV A/B
49 | 23-04243 | 13038028 | 05/04/2023 08:00 | 05/04/2023 09:30 | LOWER MONUMENTAL: PCB 4599 | WOLM
50 | 23-03532 | 12976505 | 05/04/2023 08:31 | 05/04/2023 17:00 | LONGVIEW: 230KV SOUTH MAIN BUS INCLUDING PCB A-100 | SOA, PA, LOAD
51 | 23-01827 | 12782970 | 05/04/2023 09:00 | 05/04/2023 14:00 | ROSS: PCB A-20 (ROSS-RIVERGATE NO 1 230KV LINE) | SOA, LOAD
52 | 23-04245 | 13038045 | 05/04/2023 10:00 | 05/04/2023 11:30 | LOWER MONUMENTAL: PCB 4263 | WOLM
53 | 23-04248 | 13038057 | 05/04/2023 13:00 | 05/04/2023 14:30 | LOWER MONUMENTAL: PCB 4316 | WOLM
54 | 23-05371 | 13139779 | 05/06/2023 06:00 | 05/07/2023 18:00 | COVINGTON: A-86 TERMINAL OF , COVINGTON-DUWAMISH NO 1 230KV LINE | NOEL, SOC
55 | 23-05372 | 13139807 | 05/06/2023 06:00 | 05/07/2023 18:00 | MAPLE VALLEY: A-1106 TERMINAL OF, MAPLE VALLEY-DUWAMISH NO 1 230KV LINE | NOEL, SOC
56 | 23-03883 | 13004870 | 05/06/2023 07:00 | 05/09/2023 12:00 | ASHE: PCB 4885 | GEN, NWACI, FCRPS
57 | 23-00481 | 12220066 | 05/08/2023 07:00 | 05/10/2023 16:00 | PAUL: PCB 4540 | NWACI, PDCI, COI, WOCS, SOA
58 | 23-03928 | 13011876 | 05/08/2023 07:00 | 05/09/2023 12:00 | ASHE: PCB 4888 BFR and BREAKER DIFFERENTIAL RELAY | GEN, NWACI, FCRPS
59 | 23-01177 | 12695738 | 05/08/2023 07:00 | 05/13/2023 16:00 | SNOHOMISH-BOTHELL NO 1 230KV LINE | NOEL, SOC
60 | 23-01348 | 12695763 | 05/08/2023 07:00 | 05/11/2023 12:00 | BELL: 500/230KV TRANSFORMER 1 | GEN, MT-NW, WOH
61 | 23-04472 | 13060177 | 05/08/2023 07:00 | 05/25/2023 15:00 | SIFTON: 230/115KV TRANSFORMER NO 2 RELAYS | SOA
62 | 23-01614 | 12729060 | 05/08/2023 07:30 | 05/09/2023 15:00 | ECHO LAKE: PCB 5072 | BCHT, BCHW, NOEL, SOC, NI, WOCN
63 | 23-04984 | 13104565 | 05/08/2023 07:30 | 05/12/2023 17:30 | NORTH BONNEVILLE: UNDERWOOD TAP-ALCOA SECTION OF BONNEVILLE PH 1-ALCOA NO 1&2 115KV LINE | SOA, GEN, LOAD
64 | 23-04979 | 13104546 | 05/08/2023 07:30 | 05/12/2023 17:30 | SIFTON-ROSS NO 1 115KV LINE | SOA, WOCS
65 | 23-03488 |  | 05/08/2023 08:00 | 05/11/2023 15:00 | -CPI- BURNT WOODS SUBSTATION | SLAL
66 | 23-01291 | 12695258 | 05/08/2023 08:00 | 05/11/2023 15:00 | MALIN: PCB 4582 | NWACI, PDCI, COI
67 | 23-02416 | 13048431 | 05/08/2023 08:00 | 05/11/2023 15:00 | KEELER: PCB 4394 | SOA
68 | 23-01943 | 12824401 | 05/08/2023 08:00 | 05/11/2023 16:00 | MARION: 500KV REACTOR 1 INCLUDING PCB 4012 | COI, NWACI
69 | 22-13081 | 12264072 | 05/08/2023 08:00 | 05/26/2023 15:00 | DIAMOND LAKE-ALBENI FALLS SECTION OF THE SACHEEN-ALBENI FALLS NO 1 115KV LINE INCLUDING ALBENI FALLS 115KV AUX BUS, AND PCB B-960 | SOB, GEN
70 | 23-05620 | 13195792 | 05/08/2023 08:00 | 05/08/2023 13:00 | WENDSON: 230/115KV TRANSFORMER 1, INCLUDING: THREE-PHASE PRIMARY STATION SERVICE TRANSFORMER 1 AND AUTOMATIC TRANSFER SWITCH | LOAD, SCORC
71 | 23-02165 | 13038451 | 05/08/2023 08:00 | 05/18/2023 15:00 | BENTON CITY-RED MOUNTAIN SECTION OF GRANDVIEW-RED MOUNTAIN NO 1 115KV LINE | GEN, TCLA, LOAD
72 | 23-04600 | 13125767 | 05/08/2023 08:00 | 05/16/2023 16:00 | GRAND COULEE-NILLES CORNER SECTION OF GRAND COULEE-FOSTER CREEK NO 1 115KV LINE INCLUDING B-1236 DISCONNECT | CI
73 | 23-02494 | 12880157 | 05/08/2023 08:00 | 05/12/2023 16:00 | HAMPTON-BEST LANE SECTION OF BRASADA-HARNEY NO 1 115KV LINE | NWACI
74 | 23-05183 | 13110444 | 05/08/2023 09:00 | 05/19/2023 16:30 | SUMMER LAKE: 4951/4952 TERMINALS OF THE HEMINGWAY-SUMMER LAKE NO 1 500KV LINE | ID-NW, NWACI, SIG, COI
75 | 23-01387 | 12736322 | 05/08/2023 11:30 | 05/09/2023 15:00 | MONROE: PCB 4715, MONROE: 500KV CAP GROUP 2 | WOCN, NI, NOEL, SOC, IROL
76 | 23-04306 | 13039399 | 05/09/2023 07:00 | 05/09/2023 14:00 | DRUMMOND-MACKS INN NO 1 115KV LINE INCLUDING MACKS INN PCB B-363 AND THE MACKS INN-MADISON NO 1 115KV LINE | SEIL
77 | 23-03211 | 13027416 | 05/09/2023 07:30 | 05/10/2023 15:30 | ALBANY: 115KV WEST, CENTER, AND EAST MAIN BUS INCLUDING PCB’S: B-512 , B-514 , B-516 , B-518 , B-520 , B-522 , B-524 , B-526 , B-528 , B-1272 | LOAD, SLAL, SCORC
78 | 23-03463 |  | 05/09/2023 07:30 | 05/09/2023 16:00 | HAT ROCK: 230/115KV TRANSFORMER 1 INCLUDING PCB A-1490 AND PCB B-31 | WOM, LOAD
79 | 23-01584 |  | 05/09/2023 08:00 | 05/09/2023 12:00 | BIG EDDY: 230KV CAP GROUP 1 SECTIONS 1&2 INCLUDING LBD'S A-837 AND A-841 | COI, PDCI, NWACI, WOJD
80 | 23-03884 | 13004874 | 05/09/2023 12:00 | 05/12/2023 15:00 | ASHE: PCB 4888 | GEN, NWACI, FCRPS
81 | 23-01585 | 12685834 | 05/09/2023 12:00 | 05/09/2023 15:00 | BIG EDDY: 230KV CAP GROUP 2 SECTION 1 INCLUDING PCB A-818 | COI, PDCI, NWACI, WOJD
82 | 23-03929 | 13043407 | 05/09/2023 13:00 | 05/10/2023 15:00 | ASHE: PCB 4885 BFR | GEN, NWACI, FCRPS
83 | 23-05398 | 13191156 | 05/10/2023 07:00 | 05/10/2023 16:00 | SNO-KING: PCB A-1200 | BCHT, BCHW, NOEL, SOC
84 | 23-01615 | 12736418 | 05/10/2023 07:00 | 05/11/2023 15:00 | RAVER: 500KV CAP GROUP 1 SECTION 2, INCLUDING PCB 4919 | IROL, WOCN, NOEL, RP, SOC
85 | 23-01390 | 12718082 | 05/10/2023 07:00 | 05/10/2023 15:00 | CUSTER: PCB 4486 | BCHT, BCHW, NOEL, SOC, NI
86 | 23-04291 | 13038828 | 05/10/2023 07:00 | 05/10/2023 14:00 | DRUMMOND-MACKS INN NO 1 115KV LINE, INCLUDING MACKS INN 115KV MAIN BUS | SEIL, LOAD
87 | 23-01553 | 12736452 | 05/10/2023 08:00 | 05/10/2023 12:00 | JOHN DAY: 500KV CAP GROUP 1 | COI, NWACI, PDCI, WOJD
88 | 23-01766 | 12761655 | 05/10/2023 12:00 | 05/10/2023 13:30 | JOHN DAY: 230KV CAP GROUP 2 SECTION 1 INCLUDING PCB A-1734 | COI, JDAY, PDCI, WOJD, NWACI
89 | 23-01767 | 12761828 | 05/10/2023 13:00 | 05/10/2023 14:00 | JOHN DAY: 230KV CAP GROUP 2 SECTION 2 INCLUDING PCB A-1735 | COI, JDAY, PDCI, WOJD, NWACI
90 | 23-01769 |  | 05/10/2023 14:00 | 05/10/2023 16:00 | JOHN DAY: 230KV CAP GROUP 2 SECTION 3 INCLUDING PCB A-1736
91 | 23-01768 | 12810475 | 05/10/2023 14:00 | 05/10/2023 15:00 | JOHN DAY: 230KV CAP GROUP 2 SECTION 1 INCLUDING PCB A-1734 | COI, JDAY, PDCI, WOJD, NWACI
92 | 23-04292 | 13042468 | 05/11/2023 07:00 | 05/11/2023 14:00 | DRUMMOND - MACKS INN #1 115KV LINE INCLUDING MACKS INN: 115/46KV TRANSFORMERS #1 AND #2, 115KV MAIN BUS, AND LBD B-1842 | LOAD, SEIL
93 | 23-00012 | 11242303 | 05/11/2023 07:30 | 05/11/2023 15:00 | LOWER MONUMENTAL-HANFORD NO 1 500KV LINE INCLUDING HANFORD: PCB 4095 | NWACI, PDCI, WOLM, COI, NOH, WOM, SIG
94 | 23-05242 | 13126532 | 05/11/2023 08:00 | 05/11/2023 15:00 | LANE: 115KV NORTH MAIN BUS | LOAD, EWEB
95 | 23-01796 | 12782135 | 05/11/2023 08:30 | 05/11/2023 12:00 | BAKEOVEN: JOHN DAY-GRIZZLY 1 500KV LINE SERIES CAP GROUP 1, INCLUDING PCB 5363 | NWACI, PDCI, COI, WOJD
96 | 23-01452 | 12736469 | 05/11/2023 09:00 | 05/11/2023 10:00 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 | GEN, NOH, WOCN
97 | 23-04776 | 13078297 | 05/11/2023 09:00 | 05/11/2023 15:00 | COLVILLE: 115KV CAP GROUP 1 SECTIONS 1, 2, & 3 INCLUDING PCB'S B-1769, B-1771, B-1773, & B-1780
98 | 23-01453 | 12736473 | 05/11/2023 10:00 | 05/11/2023 11:00 | GRAND COULEE: PCB 2092, GRAND COULEE: PCB 2096 | GEN, NOH, WOCN
99 | 23-01454 | 12736479 | 05/11/2023 11:00 | 05/11/2023 12:00 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 | GEN, NOH, WOCN
100 | 23-01816 | 12782062 | 05/11/2023 12:00 | 05/11/2023 15:00 | BAKEOVEN: JOHN DAY-GRIZZLY 2 500KV LINE SERIES CAP GROUP 2, INCLUDING PCB 5367 | NWACI, PDCI, COI, WOJD
101 | 23-01456 | 12736651 | 05/11/2023 13:30 | 05/11/2023 14:30 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 | GEN, NOH, WOCN
102 | 23-01457 | 12736655 | 05/11/2023 14:30 | 05/11/2023 15:30 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 | GEN, NOH, WOCN
103 | 23-00013 | 11242330 | 05/12/2023 07:30 | 05/12/2023 15:00 | HANFORD-WAUTOMA NO 1 500KV LINE, INCLUDING HANFORD: PCB 4095 | NWACI, PDCI, WOLM, COI, NOH, WOM, SIG
104 | 23-04358 | 13039409 | 05/12/2023 08:00 | 05/12/2023 18:00 | COVINGTON: A-86 TERMINAL OF COVINGTON-DUWAMISH 1 230KV LINE | NOEL, SOC
105 | 23-05260 | 13134487 | 05/12/2023 08:00 | 05/12/2023 16:00 | JOHN DAY: 500KV EAST BUS, INCLUDING PCB 4128 | WOJD, NWACI, WOS
106 | 23-05245 | 13139869 | 05/12/2023 08:00 | 05/26/2023 15:00 | DANEBO (EWEB)-LANE #1 115KV LINE INCLUDING LANE: PCB B-1620 AND THE 115KV A/B | EWEB
107 | 23-04127 | 13032973 | 05/14/2023 12:00 | 05/18/2023 16:00 | ASHE: 230KV MAIN BUS INCLUDING PCB A-924 | TCLA, NOH, COI, PDCI, GEN, FCRPS, LOAD
108 | 23-01665 | 12736670 | 05/14/2023 22:00 | 05/19/2023 17:00 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 | GEN, NOH, WOCN
109 | 23-01613 | 12735859 | 05/15/2023 07:00 | 05/16/2023 15:00 | RAVER: PCB 4789 | NOEL, RP, SOC, WOCN
110 | 23-01949 | 12858231 | 05/15/2023 07:00 | 06/23/2023 14:00 | SPAR CANYON: 230KV REACTOR #1 INCLUDING LBD A-151
111 | 23-01704 | 12736212 | 05/15/2023 07:00 | 06/02/2023 17:00 | -USBR- COULMBIA-GRAND COULEE NO 1 230KV LINE INCLUDING GRAND COULEE PCB 5686 | NOH, WOCN, COI, NWACI, PDCI, CI
112 | 23-00695 | 12593780 | 05/15/2023 08:00 | 05/25/2023 16:00 | CENTRAL FERRY: PCB 5432, INCLUDING 500KV REACTOR 1 | WOH, WOLM, SOA
113 | 23-01226 | 13202169 | 05/15/2023 08:00 | 05/25/2023 10:00 | KEELER: PCB 4324 RELAYS | SOA
114 | 23-01288 | 13012752 | 05/15/2023 08:00 | 05/18/2023 15:00 | WARNER: 230/115KV TRANSFORMER 1 | NWACI
115 | 23-04769 | 13077694 | 05/15/2023 08:00 | 05/17/2023 16:00 | REDMOND: A-262 TERMINAL OF REDMOND-PGE ROUND BUTTE NO 1 230KV LINE | COR, SIG
116 | 23-04130 |  | 05/15/2023 08:00 | 05/17/2023 15:00 | ASHE TAP TO MIDWAY-HEW NO 2 230KV LINE INCLUDING ASHE PCB A-401 AND 230KV AUX BUS | GEN, LOAD, NOH, TCLA
117 | 23-04024 | 13059140 | 05/15/2023 08:00 | 05/18/2023 15:00 | SATSOP-SHELTON NO 1 230KV LINE | LOAD, PA, SI
118 | 23-01220 | 12660992 | 05/15/2023 08:30 | 05/19/2023 17:30 | MALIN: 4065/4187/4075/4076 TERMINAL OF, MALIN-ROUND MOUNTAIN NO 1 500KV LINE | BCHT, BCHW, NI, NWACI, COI
119 | 23-00406 |  | 05/15/2023 09:00 | 06/16/2023 15:00 | -IPCO- HINES-WEST JOHN DAY 115KV LINE | ID-NW
120 | 23-02816 | 12888935 | 05/15/2023 12:00 | 06/08/2023 16:00 | GARRISON-TAFT NO 1 500KV LINE, INCLUDING GARRISON PCB'S 4415, 4418 | MT-NW, SIG
121 | 23-02736 | 12888914 | 05/15/2023 12:00 | 06/08/2023 16:00 | BROADVIEW-GARRISON NO 1 500KV LINE, INCLUDING GARRISON PCB'S 4418, 4421 | MT-NW, GEN
122 | 23-01687 |  | 05/16/2023 07:30 | 05/18/2023 17:00 | JONES CANYON: 230KV REACTIVE BUS INCLUDING PCB'S A -1647, A-1682, A-1688, A-1689 AND THE 230KV CAP GROUP #1 SECTION 1 AND 2 | WOCS
123 | 23-03325 | 12985544 | 05/16/2023 08:00 | 05/25/2023 18:00 | NORTH BONNEVILLLE-ROSS NO 1 230KV LINE INCLUDING SIFTON TAP | GEN, LOAD, WOCS, FCRPS, SOA
124 | 23-05868 | 13202383 | 05/17/2023 07:00 | 05/17/2023 15:00 | COVINGTON: REACTIVE GROUP 1 SECTIONS 1, 2, 3, & 230KV REACTOR 1, INCLUDING PCB'S A-999, A-1003, A-1005, A-1007, & REACTIVE GROUP 1 PCB A-1004 | RP, NOEL, SOC, WOCN, LOAD
125 | 23-00742 | 12735472 | 05/18/2023 08:00 | 05/18/2023 15:00 | BELL: 500/230KV TRANSFORMER 1 INCLUDING PCB'S 5307, 5310, A-577, AND A-552 | GEN, MT-NW, WOH
126 | 23-02362 | 12842609 | 05/18/2023 09:00 | 05/18/2023 11:00 | RAVER: PCB 4296 | NOEL, RP, SOC
127 | 23-02363 | 12842610 | 05/18/2023 12:00 | 05/18/2023 14:00 | RAVER: PCB 4293 | NOEL, RP, SOC, WOCN
128 | 23-05450 | 13145446 | 05/19/2023 06:00 | 05/21/2023 18:00 | SNO-KING: A-1198 TERMINAL AND MAPLE VALLEY: A-1138 TERMINAL OF, SNO-KING-MAPLE VALLEY NO 1 230KV LINE | NOEL, SOC, SIG
129 | 23-05452 | 13145446 | 05/19/2023 06:00 | 05/21/2023 18:00 | SNO-KING: A-1417 TERMINAL AND MAPLE VALLEY: A-1124 TERMINAL OF, SNO-KING-MAPLE VALLEY NO 2 230KV LINE | NOEL, SOC, SIG
130 | 23-00127 | 11597819 | 05/21/2023 22:00 | 05/21/2023 22:30 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 | GEN, NOH, WOCN
131 | 23-00520 | 12219187 | 05/22/2023 07:00 | 05/23/2023 18:00 | SCHULTZ-WAUTOMA NO 1 500KV LINE | BCHT, BCHW, IROL, NI, NOH, SIG, WOCN
132 | 23-05422 | 13191175 | 05/22/2023 07:00 | 05/25/2023 16:00 | MARION-LANE NO 1 500KV LINE, (UNGROUNDED AT MARION) | NWACI, SIG, EWEB, SCORC
133 | 23-00681 | 12751723 | 05/22/2023 07:00 | 05/22/2023 11:30 | COVINGTON: 230KV REACTIVE GROUP 1 CAP SECTIONS 1, 2 AND 3 INCLUDING PCB A-999, PCB A-1005, PCB A-1007, PCB A-1003 AND 230KV REACTOR 1 | NOEL, SOC, WOCN, LOAD, RP
134 | 23-04673 | 13077424 | 05/22/2023 07:30 | 06/06/2023 17:00 | LONGVIEW: PCB A-646 INCLUDING LONGVIEW-CHEHALIS 1&3 230KV LINE | LOAD, NOEL, RP, SOA, PA
135 | 23-00239 | 12118767 | 05/22/2023 08:00 | 05/23/2023 15:00 | OSTRANDER: 500KV CAP GROUP 3 INCLUDING PCB 5097 | NWACI, PDCI, WOCS, COI
136 | 23-01944 | 12810652 | 05/22/2023 08:00 | 05/25/2023 16:00 | MARION: 500KV REACTOR 2 INCLUDING PCB 4020 | COI, NWACI, PDCI
137 | 23-04025 | 13042801 | 05/22/2023 08:00 | 05/25/2023 15:00 | SATSOP-SHELTON NO 1 230KV LINE | LOAD, PA, SI
138 | 23-02364 | 13059728 | 05/22/2023 08:00 | 05/26/2023 15:00 | PONDEROSA-PILOT BUTTE NO 1 230KV LINE | COR
139 | 23-01519 | 12782906 | 05/22/2023 08:30 | 05/25/2023 15:00 | CAPTAIN JACK: PCB 4977 | NWACI, PDCI, COI
140 | 23-00482 | 12220068 | 05/23/2023 07:00 | 05/25/2023 16:00 | PAUL: PCB 4542 | GEN, NWACI, PDCI, COI, WOCS, SOA
141 | 23-04233 | 13042417 | 05/23/2023 07:00 | 05/23/2023 14:00 | DRUMMOND - MACKS INN #1 115KV LINE INCLUDING DRUMMOND: 115KV AUX BUS AND PCB B-1502 | SEIL
142 | 23-00680 | 12752594 | 05/23/2023 07:30 | 05/23/2023 12:00 | TACOMA: 230KV CAP GROUP 3 SECTION 1, & 2 INCLUDING LBD A-1078, LBD 1079 | NOEL, RP, SOC, WOCN
143 | 23-04341 | 13048462 | 05/23/2023 07:30 | 05/23/2023 12:00 | SLATT: 230KV CAP GROUP 2 SECTION 2 INCLUDING PCB A -1798 | WOJD, GEN
144 | 23-01483 | 12752577 | 05/24/2023 07:00 | 05/24/2023 15:00 | BELL: 500KV REACTOR 1 INCLUDING PCB 4559 | MT-NW, WOH
145 | 23-04301 | 13099285 | 05/24/2023 07:30 | 05/24/2023 16:00 | BELLINGHAM: 230KV MAIN BUS | LOAD, NOEL, SOC
146 | 23-00682 | 12752642 | 05/24/2023 08:00 | 05/24/2023 15:00 | MAPLE VALLEY: 230KV CAP GROUP 1 SECT 1, 2, 3, 4 INCL LBDs A-1101, A-1102, A-1103, & A-1104 | NOEL, SOC, WOCN, NI
147 | 23-01926 | 12810116 | 05/25/2023 07:00 | 05/25/2023 08:00 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 | GEN, NOH, WOCN
148 | 23-00684 | 12752713 | 05/25/2023 07:30 | 05/25/2023 12:00 | Raver: PCBs 4914 and 4921 including 500kV Cap Group 1 Sections 1, 2, 3 and 500kV Reactive Bus | NOEL, RP, SOC, IROL, WOCN
149 | 23-01927 | 12810138 | 05/25/2023 08:00 | 05/25/2023 09:00 | GRAND COULEE: PCB 2092, GRAND COULEE: PCB 2096 | GEN, NOH, WOCN
150 | 23-01928 | 12810144 | 05/25/2023 09:00 | 05/25/2023 10:00 | GRAND COULEE: PCB 2292, GRAND COULEE: PCB 2296 | GEN, NOH, WOCN
151 | 23-05575 | 13202868 | 05/25/2023 10:00 | 05/25/2023 12:00 | KEELER: PCB 4322 | SOA
152 | 23-01929 | 12810148 | 05/25/2023 10:00 | 05/25/2023 11:00 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 | GEN, NOH, WOCN
153 | 23-01930 | 12810154 | 05/25/2023 11:00 | 05/25/2023 12:00 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 | GEN, NOH, WOCN
154 | 23-05586 | 13191242 | 05/26/2023 08:00 | 05/26/2023 12:00 | ECHO LAKE: 500KV CAP GROUP 1 INCLUDING PCB 5125 | BCHT, BCHW, NOEL, SOC, WOCN, NI, IROL
155 | 23-05588 | 13191217 | 05/26/2023 08:00 | 05/26/2023 12:00 | ECHO LAKE: 500KV CAP GROUP 2 INCLUDING PCB 5127 | BCHT, NOEL, SOC, WOCN, NI, BCHW, IROL
156 | 23-00128 | 11597829 | 05/26/2023 16:30 | 05/26/2023 17:00 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 | GEN, NOH, WOCN
157 | 23-01706 | 12736687 | 05/29/2023 22:00 | 06/30/2023 19:00 | -USBR- GRAND COULEE: 230/115KV TRANSFORMER KX2A INCLUDING PCB'S 5182 AND 2372 | NOH, OKLA, LOAD, WOCN, COI, NWACI, PDCI
158 | 23-05719 | 13176863 | 05/30/2023 06:00 | 05/31/2023 17:00 | PAC - GRANTS PASS-GLENDALE SECTION OF GRANTS PASS-DIXONVILLE 230KV LINE
159 | 23-00130 | 11575566 | 05/30/2023 07:00 | 06/04/2023 17:00 | ASHE-MARION NO 2 500KV LINE | NWACI, BCHT, BCHW, NI, SIG, WOCS, WOJD, WOM, FCRPS, NOH
160 | 23-00129 | 11575538 | 05/30/2023 07:00 | 06/04/2023 17:00 | ASHE-SLATT NO 1 500KV LINE | BCHT, BCHW, NI, NOH, SIG, WOM, WOS
161 | 23-05361 | 13203143 | 05/30/2023 07:00 | 05/30/2023 16:30 | SNOHOMISH: 230KV MAIN BUS SECTION 4, INCLUDING PCB'S A-197, A-184, A-182, A-181, A-178 AND A-1040 | NOEL, SOC, WOCN, BCHT, BCHW
162 | 23-01218 | 12685390 | 05/30/2023 07:00 | 06/16/2023 17:00 | CLYMER-MOXEE SECTION OF ELLENSBURG-MOXEE NO 1 115KV LINE | TCLA
163 | 23-04475 | 13048225 | 05/30/2023 07:00 | 06/15/2023 15:00 | SIFTON: NORTH BONNEVILLE - ROSS NO 2 230KV LINE INCLUDING SIFTON TAP LINE RELAYS AND THE 230/115KV XFMR NO.1 RELAYS | SOA, GEN, LOAD, WOCS, FCRPS
164 | 23-05110 | 13109692 | 05/30/2023 07:30 | 06/01/2023 16:00 | ADDY-CHEWELAH SECTION OF ADDY-AVISTA DEVIL'S GAP 1 115KV LINE INCLUDING ADDY: PCB B-1137 AND 115KV AUX BUS
165 | 23-00879 | 12484181 | 05/30/2023 08:00 | 06/01/2023 17:00 | BIG EDDY-MCLOUGHLIN NO 1&2 230KV LINE | PDCI, SOA, WOJD, BGEDY
166 | 23-01184 | 12777119 | 05/30/2023 10:00 | 05/30/2023 11:00 | MURRAY: 115KV CAP GROUP 1 SECTIONS 1 & 2 INCLUDING LBD'S B-1755, B-1756 AND 115KV REACTIVE BUS
167 | 23-04909 | 13109612 | 05/31/2023 07:00 | 05/31/2023 16:00 | ALVEY: 230KV CENTER MAIN BUS INCLUDING PCBS A-247 AND A-332 | SCORC
168 | 23-01740 | 12782517 | 05/31/2023 08:00 | 06/01/2023 18:00 | BIG EDDY: 500/230KV TIE NO 1 500KV LINE RELAYS (FORCES OUT TIE 1, BANK 2 & PCB'S ) | GEN, NWACI, PDCI, WOJD, COI, SIG, FCRPS, BGEDY, SOA
169 | 23-05365 | 13202431 | 05/31/2023 08:00 | 05/31/2023 16:00 | SNOHOMISH: PCB A-1040 INCLUDING 230KV REACTIVE BUS | NOEL, SOC, WOCN