## Request List
Row | Request# | CAISO# | Start | End | Main Element Impacted | Path Affected
1 | 23-00399 | 12118076 | 08/31/2023 08:00 | 11/23/2023 18:00 | SCL Broad St - SCL Union St Tap 115kV Cable, SCL Union St - SCL Union St Tap 115kV Cable, SCL Massachusetts St - SCL Union St Tap 115kV Cable, SCL Broad St Bank 66B, SCL Broad St Bank 66A, SCL Broad St BKR 120-55, SCL Broad St BKR 120-58, SCL Union St BKR 120-65 | NOEL, SOC
2 | 23-00084 | 11345939 | 10/16/2023 07:00 | 11/09/2023 16:00 | HANFORD-WAUTOMA NO 2 500KV LINE | NOH, NWACI, PDCI, SIG, COI, NOH, NWACI, PDCI, COI, WOM, WOS, NOH, NWACI, PDCI, COI, WOM, WOS, WOCN, NOH, WOCN
3 | 23-00004 | 10955446 | 10/30/2023 03:00 | 11/30/2023 17:00 | -USBR- GRAND COULEE: PCB 5382 | NOH, WOCN, COI, NWACI, PDCI
4 | 23-00049 | 10388102 | 10/31/2023 08:00 | 11/03/2023 18:30 | CANBY TAP TO MALIN-HILLTOP NO 1 230KV LINE (UNGROUNDED) | RATS, RATS, RATS, LOAD
5 | 23-00089 | 11350694 | 11/01/2023 07:30 | 11/01/2023 16:00 | BENTON-FRANKLIN NO 2 115KV LINE INCLUDING GLADE TAP AND TAYLOR FLATS TAP | TCLA, TCLA, LOAD, TCLA, WOM, LOAD
6 | 23-00050 | 10793523 | 11/04/2023 07:00 | 11/06/2023 18:30 | HILLTOP-WARNER NO 1 230KV LINE (UNGROUNDED), WARNER: 230/115KV TRANSFORMER 1 | COI, NWACI, PDCI, RATS, COI, PDCI, RATS, NWACI
7 | 22-01809 | 10633216 | 11/06/2023 09:00 | 11/06/2023 14:00 | BUCKLEY: GRIZZLY BUS SECTION DIFFERENTIAL RELAY (FORCES OUT BUCKLEY-GRIZZLY 1 500KV LINE), BUCKLEY-GRIZZLY NO 1 500KV LINE | NWACI, PDCI, WOJD, WOM, WOS, COI, NWACI, PDCI, WOCS, WOJD, COI, BCHT, BCHW, NI, NWACI, PDCI, SIG, WOJD, COI
8 | 23-00407 | 12252239 | 11/07/2023 08:00 | 11/09/2023 15:00 | MIDWAY-MOXEE NO 1 115KV LINE, INCLUDING MIDWAY PCBS B-146, B-148 AND MOXEE PCBS B-902, B-906 | TCLA
9 | 22-01810 | 10633200 | 11/07/2023 09:00 | 11/07/2023 14:00 | BUCKLEY: MARION BUS SECTION DIFFERENTIAL RELAY (FORCES OUT BUCKLEY-MARION 1 500KV LINE), BUCKLEY-MARION NO 1 500KV LINE | NWACI, PDCI, WOCS, WOJD, COI, NWACI, PDCI, WOCS, WOJD, WOM, WOS, COI, NWACI, PDCI, SIG, WOCS, WOJD, COI
10 | 22-01806 | 10633205 | 11/08/2023 09:00 | 11/08/2023 14:00 | BUCKLEY: SLATT BUS SECTION DIFFERENTIAL RELAY (FORCES OUT SLATT-BUCKLEY 1 500KV LINE), SLATT-BUCKLEY NO 1 500KV LINE | NWACI, PDCI, WOCS, WOJD, WOM, WOS, COI, NWACI, PDCI, WOJD, WOM, WOS, COI, NWACI, PDCI, SIG, WOJD, WOM, WOS, COI
11 | 23-00085 | 11345942 | 11/13/2023 07:00 | 12/01/2023 16:00 | HANFORD-WAUTOMA NO 1 500KV LINE | NOH, NWACI, PDCI, SIG, COI, NOH, NWACI, PDCI, COI, WOM, WOS, GEN, NWACI, PDCI, WOLM, COI, NOH, WOM, WOS, WOCN, WOCN
12 | 23-00055 | 10154630 | 11/20/2023 06:00 | 12/01/2023 21:00 | GRAND COULEE: PCB 2296, PCB 2292 | GEN, NOH, WOCN