## Request List
0 | Request# | Start | End | Main Element Impacted | Elements Involved | CAISO# | Path Affected
1 | 20-00283 | 12/31/2020 15:00 | 12/15/2031 23:59 | PAUL: 4569 TERMINAL OF PAUL-CENTRALIA THERMAL PH NO 1 500KV LINE | PAUL: 4569 TERMINAL OF PAUL-CENTRALIA THERMAL PH NO 1 500KV LINE | 11219795 | GEN, PA
2 | 23-04125 | 01/28/2023 17:00 | 07/07/2025 07:00 | ROCKY REACH-MAPLE VALLEY NO 1 345kV LINE OPERATING AT 230KV | ROCKY REACH: 345/230KV TRANSFORMER 1, MAPLE VALLEY: 345/230KV TRANSFORMER 1 | 13016840 | WOCN, SOC/NOEL, CI, GEN, IROL, NOEL, NOH, SOC
3 | 23-16749 | 10/26/2023 07:00 | 06/01/2028 16:00 | VALHALLA: B-280 TERMINAL OF THE VALHALLA-CHELAN CO PUD 115KV FEEDER T1 | VALHALLA: CHELAN CO PUD 115KV FEEDER T1 |  | CI
4 | 23-18445 | 12/14/2023 06:40 | 12/31/2025 16:00 | BCH - CHAPMAN: 5CX1 | BCH - CHAPMAN: 5CX1 | 14853282 | NI
5 | 24-16579 | 10/16/2024 08:00 | 10/31/2025 15:00 | BOUNDARY: PCB A-1230 |  | 17543676 | SOB
6 | 25-05571 | 02/24/2025 12:00 | 12/31/2025 23:00 | GARRISON-ANACONDA NO 1 230KV LINE (DERATED) |  | 17476640 | MT-NW
7 | 25-00087 | 02/24/2025 18:00 | 08/20/2025 16:30 | PONDEROSA: A-1811 TO A-1840 SECTION OF THE 230KV NORTH MAIN BUS INCLUDING A-1840 DISCONNECT | PONDEROSA: 230KV NORTH NON-GIS BUS SECTION |  | LOAD, COR, NWACI
8 | 25-01365 | 04/01/2025 07:30 | 06/13/2025 16:00 | ALCOA: B-230 TERMINAL OF PIONEER-ALCOA NO 1 115KV LINE | FELIDA-SW48 SECTION OF PIONEER-ALCOA NO 1 115KV LINE, SW48-ALCOA SECTION OF PIONEER-ALCOA NO 1 115KV LINE | 17030311 | LOAD
9 | 25-07342 | 04/01/2025 15:00 | 07/01/2025 17:00 | PAUL: 4812 TERMINAL OF THE PAUL-CENTRALIA PH NO 2 500KV LINE | PAUL-CENTRALIA THERMAL PH NO 2 500KV LINE | 17677355 | GEN, RP, SOA, NOPE
10 | 25-07665 | 04/07/2025 10:30 | 10/31/2025 15:00 | SATSOP PARK-COSMOPOLIS NO 1 115KV LINE (DERATED) |  | 17719104 | LOAD, SOA, NOPE
11 | 25-03624 | 04/21/2025 08:00 | 10/06/2025 11:00 | CARDWELL: B-1540 TERMINAL OF CARDWELL-MEEKER 115KV LINE | CARDWELL-MEEKER 115KV LINE, CARDWELL: PCB B-1540 | 17293824 | LOAD, SOA, NOPE
12 | 25-06129 | 05/05/2025 07:00 | 06/06/2025 17:00 | MIDPOINT (IPC)-HEMINGWAY 500KV LINE |  |  | ID-NW, NWACI
13 | 25-00606 | 05/19/2025 06:00 | 06/20/2025 16:00 | -OTEC- HINES-WEST JOHN DAY 138KV LINE |  |  | LOAD
14 | 25-07358 | 05/19/2025 08:00 | 06/05/2025 18:00 | MAPLE VALLEY: A-1116 TERMINAL OF MAPLE VALLEY-EAST PINE 1 230KV LINE | MAPLE VALLEY-EAST PINE NO 1 230KV LINE | 17678518 | NOEL, SOC
15 | 25-04561 | 05/19/2025 12:00 | 07/17/2025 10:00 | MIDWAY-HEW NO 2 230kV LINE INCLUDING MIDWAY: PCB A-114 AND A-114 AUX BUS DISC | MIDWAY: PCB A-114, MIDWAY: A-114 AUX BUS DISC, MIDWAY-HEW NO 2 230KV LINE | 17583210 | WOM, GEN, TCLA, LOAD
16 | 25-03902 | 05/22/2025 08:00 | 06/01/2025 16:00 | REDMOND: A-262 TERMINAL OF REDMOND-PGE ROUND BUTTE NO 1 230KV LINE | REDMOND-PGE ROUND BUTTE NO 1 230KV LINE | 17304188 | SIG, COR, NWACI
17 | 25-01370 | 05/26/2025 08:00 | 06/13/2025 15:00 | -PGE- SHERWOOD: 230KV BUS V63 |  |  | SOA, NOPE, LOAD
18 | 25-02092 | 05/27/2025 08:00 | 06/01/2025 15:00 | CHEHALIS-OLYMPIA NO 1 230KV LINE | CHEHALIS: PCB A-228, OLYMPIA: PCB A-220 | 17133685 | RP, LOAD, SI, NOEL, SOC, WOCN
19 | 25-00205 | 05/28/2025 08:00 | 07/28/2025 15:00 | KNAPPA-FERN HILL SECTION OF DRISCOLL-ASTORIA NO 1 115KV LINE |  | 17095338 | SOA
20 | 25-02222 | 05/29/2025 10:00 | 07/01/2025 15:00 | NOTI CREEK TAP: B-971 AND B-972 TERMINALS OF NOTI CREEK TAP TO LANE-WENDSON NO 1 115KV LINE | FERN RIDGE-NOTI CREEK SECTION OF LANE-WENDSON NO 1 115KV LINE, NOTI CREEK-WALTON SECTION OF LANE-WENDSON NO 1 115KV LINE, NOTI CREEK TAP TO LANE-WENDSON NO 1 115KV LINE | 17182100 | LOAD, SCORC
21 | 25-00285 | 06/01/2025 22:00 | 06/05/2025 17:00 | GRAND COULEE: 2193 DSC, GRAND COULEE: 2197 DSC, GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 |  |  | GEN, NOH, WOCN
22 | 25-01491 | 06/02/2025 06:00 | 06/05/2025 15:00 | PALISADES PH: 762 TERMINAL OF THE PALISADES PH-SNAKE RIVER 115KV LINE | PALISADES PH: PCB 762, PALISADES PH: LOWER VALLEY ENG 115KV FEEDER 1 BY USBR GENERAL |  | GEN, LOAD, SEIL
23 | 25-02597 | 06/02/2025 06:00 | 06/05/2025 15:00 | PALISADES PH-SNAKE RIVER 115KV LINE | PALISADES PH: LOWER VALLEY ENG 115KV FEEDER 1 BY USBR GENERAL | 17208082 | GEN, LOAD, SEIL
24 | 25-02778 | 06/02/2025 07:00 | 06/02/2025 09:00 | MONROE: 500KV CAP GROUP 4, INCLUDING PCB 4508 | MONROE: PCB 4508 | 17294313 | IROL, NI, NOEL, SOC, WOCN, STCON
25 | 25-00940 | 06/02/2025 07:00 | 06/13/2025 15:00 | LANE: 500/230KV TRANSFORMER 3 | MARION-LANE NO 1 500KV LINE | 16840136 | SIG, NWACI, EWEB
26 | 25-06261 | 06/02/2025 07:00 | 06/03/2025 16:00 | LANCASTER-NOXON NO 1 230KV LINE | LANCASTER: PCB A-1184, LANCASTER: PCB A-1186 | 17557287 | MT-NW, WOH, FLAT
27 | 25-00103 | 06/02/2025 07:00 | 06/15/2025 15:00 | PAUL-OLYMPIA NO 1 500KV LINE INCLUDING OLYMPIA 500/230KV BANK NO 5 | PAUL-OLYMPIA NO 1 500KV LINE, OLYMPIA: 500/230KV TRANSFORMER 5 | 16778049 | LOAD, RP, SIG, NOEL, IROL, SI
28 | 25-02193 | 06/02/2025 07:00 | 06/11/2025 16:00 | GRAND COULEE-SCHULTZ NO 2 500KV LINE | COLUMBIA: GRAND COULEE-SCHULTZ 2 500KV LINE SERIES CAP GROUP 2, SCHULTZ: PCB 5148, SCHULTZ: PCB 5151, GRAND COULEE: PCB 9192, GRAND COULEE: PCB 2296, COLUMBIA: PCB 4693 | 17181316 | IROL, NOEL, NOH, SOC, WOCN, GEN, FCRPS, SIG
29 | 25-05882 | 06/02/2025 07:00 | 06/05/2025 17:00 | THE DALLES PH: 115/13.2KV BANK 2 | THE DALLES PH-BIG EDDY NO 2 115KV LINE | 17536441 | GEN, FCRPS
30 | 25-04244 | 06/02/2025 07:30 | 06/03/2025 16:00 | JONES CANYON: 230KV REACTOR #1 INCLUDING PCB A-1673 | JONES CANYON: 230KV REACTOR 1, JONES CANYON: PCB A-1673 | 17333405 | WOM
31 | 25-00455 | 06/02/2025 07:30 | 06/03/2025 15:30 | CAPTAIN JACK: PCB 4983 |  | 17080343 | NWACI, COI
32 | 25-01373 | 06/02/2025 08:00 | 06/04/2025 16:30 | SCHULTZ: PCB 5160 |  | 17159231 | WOCN, NOEL
33 | 25-02091 | 06/02/2025 08:00 | 06/13/2025 15:00 | T3BA'DAS-FAIRMOUNT SECTION OF SHELTON-FAIRMOUNT NO 2 115KV LINE |  | 17268467 | PA
34 | 25-06919 | 06/02/2025 08:00 | 06/15/2025 15:00 | WAUTOMA: SCHULTZ 1 500KV LINE SERIES CAP GROUP NO 1 INCLUDING PCBS 5513 AND 5514 | WAUTOMA: PCB 5514, WAUTOMA: PCB 5513, WAUTOMA: SCHULTZ 1 500KV LINE SERIES CAP GROUP NO 1 |  | NOH, WOCN
35 | 25-04315 | 06/02/2025 08:00 | 06/02/2025 15:00 | SNO-KING: 230KV CAP GROUP 1 SECTIONS 1 & 2 INCLUDING LBDS A-1197, A-1199 AND 230KV REACTIVE BUS | SNO-KING: PCB A-1434, SNO-KING: LBD A-1197, SNO-KING: LBD A-1199, SNO-KING: 230KV CAP GROUP 1 SECTION 1, SNO-KING: 230KV CAP GROUP 1 SECTION 2 | 17338012 | NOEL, SOC, WOCN
36 | 25-02196 | 06/02/2025 08:00 | 06/20/2025 12:00 | COLUMBIA: GRAND COULEE-SCHULTZ NO 2 500KV LINE SERIES CAP GROUP 2 INCLUDING PCB 4693 | COLUMBIA: PCB 4693, COLUMBIA: GRAND COULEE-SCHULTZ 2 500KV LINE SERIES CAP GROUP 2 | 17191320 | NOH, WOCN, IROL, NOEL, SOC
37 | 25-00526 | 06/02/2025 08:00 | 06/05/2025 16:30 | BIG EDDY-CHEMAWA NO 1 230KV LINE |  | 17109271 | PDCI, WOCS, WOJD, NWACI
38 | 25-03593 | 06/02/2025 08:00 | 06/06/2025 16:00 | -PGE- PELTON-ROUND BUTTE 230KV LINE |  |  | COR, NWACI
39 | 25-06917 | 06/02/2025 08:00 | 10/30/2025 16:00 | -CPUD- 7TH AVE-EAST KELSO 115KV LINE | 7TH AVE-EAST KELSO 115KV LINE | 17616764 | LOAD
40 | 25-03489 | 06/02/2025 08:00 | 06/06/2025 15:00 | ST JOHNS-KEELER NO 2 115KV LINE INCLUDING KEELER: PCB B-1072 | ST JOHNS: PCB B-42, KEELER: PCB B-1072, ST JOHNS-KEELER NO 2 115KV LINE | 17287068 | LOAD, SOA, NOPE
41 | 25-06453 | 06/02/2025 08:30 | 06/05/2025 16:00 | HOLDEN CREEK (EWEB) - THURSTON NO 1 115KV LINE | THURSTON: PCB 2360, HOLDEN CREEK: PCB 7150, HOLDEN CREEK: PCB 7190, HOLDEN CREEK-THURSTON NO 1 115KV LINE | 17663913 | GEN, EWEB
42 | 25-02776 | 06/02/2025 09:00 | 06/02/2025 11:00 | MONROE: 500KV CAP GROUP 2, INCLUDING PCB 4715 | MONROE: PCB 4715 | 17294326 | IROL, NI, NOEL, SOC, WOCN
43 | 25-06152 | 06/02/2025 10:30 | 06/02/2025 12:30 | CHIEF JOSEPH: BRAKING RESISTOR | CHIEF JOSEPH: PCB A-594 | 17535895 | NOH, SIG, NWACI, WOCN
44 | 25-02775 | 06/02/2025 11:00 | 06/02/2025 12:00 | MONROE: 500KV CAP GROUP 3, INCLUDING PCB 5047 | MONROE: PCB 5047 | 17294320 | IROL, NOEL, SOC, WOCN, NI
45 | 25-04881 | 06/02/2025 12:00 | 06/02/2025 17:00 | COLUMBIA: 115KV SOUTH MAIN BUS INCLUDING PCB B-398 AND (NEW) B-398 M/B AND A/B DISCs | COLUMBIA: 115KV SOUTH MAIN BUS, COLUMBIA: 230/115KV TRANSFORMER 1, COLUMBIA-B408 SECTION OF COLUMBIA-ELLENSBURG NO 1 115KV LINE, COLUMBIA-ROCKY FORD NO 1 115KV LINE | 17407115 | TCLA, CI, NOH, LOAD, WOCN
46 | 25-02779 | 06/02/2025 12:00 | 06/02/2025 14:00 | MONROE: 230KV REACTIVE GROUP 1 CAP SECTION 1 INCLUDING PCB A-1433 | MONROE: PCB A-1433, MONROE: 230KV REACTIVE GROUP 1 CAP SECTION 1 | 17298042 | WOCN, NOEL, SIG, SOC
47 | 25-00906 | 06/03/2025 07:30 | 06/03/2025 07:45 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 |  | 16822111 | GEN, NOH, WOCN
48 | 25-04190 | 06/03/2025 08:00 | 06/03/2025 12:00 | ADDY: 230KV CAP GROUP 1 INCLUDING PCB A-147 | ADDY: PCB A-147, ADDY: 230KV CAP GROUP 1 | 17332913 | SOB
49 | 25-01349 | 06/03/2025 08:00 | 06/04/2025 15:00 | MONROE: PCB 4522 | MONROE: PCB 5502 | 17049777 | BCHT, BCHW, NOEL, SOC, NI, WOCN
50 | 25-01265 | 06/03/2025 08:00 | 06/03/2025 16:00 | CENTRAL FERRY: PCB 5432, INCLUDING 500KV REACTOR 1 | CENTRAL FERRY: PCB 5432, CENTRAL FERRY: 500KV REACTOR 1 | 16978079 | WOH, WOLM
51 | 25-02258 | 06/03/2025 08:00 | 06/04/2025 15:00 | CUSTER: PCB A-1246 |  | 17160287 | BCHT, BCHW, NOEL, SOC, NI
52 | 25-07061 | 06/03/2025 10:00 | 06/03/2025 21:00 | CELILO: PACIFIC HVDC PROBING SIGNAL TEST | CHIEF JOSEPH: BRAKING RESISTOR | 17642430 | NOH, SIG, NWACI
53 | 25-00907 | 06/03/2025 11:15 | 06/03/2025 11:30 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 |  | 16822070 | GEN, NOH, WOCN
54 | 25-00457 | 06/04/2025 07:30 | 06/05/2025 15:30 | CAPTAIN JACK: PCB 4990 |  | 17080347 | NWACI, COI
55 | 25-06889 | 06/04/2025 10:30 | 06/04/2025 12:30 | HOLCOMB: PCB B-440 | HOLCOMB-OXBOW SECTION OF HOLCOMB-NASELLE NO 1 115KV LINE | 17617808 | RP
56 | 25-02259 | 06/05/2025 08:00 | 06/05/2025 15:00 | CUSTER: PCB A-1242 |  | 17160292 | BCHT, BCHW, NOEL, SOC, NI
57 | 25-02162 | 06/05/2025 08:00 | 06/05/2025 12:00 | SCHULTZ: PCB 5157 |  | 17145808 | WOCN, NOEL
58 | 25-05787 | 06/05/2025 08:00 | 06/11/2025 16:00 | MARION-LANE NO 1 500KV LINE |  | 17490714 | NWACI, SIG, EWEB
59 | 25-02164 | 06/05/2025 12:00 | 06/05/2025 16:00 | SCHULTZ: PCB 5160 |  | 17145810 | WOCN, NOEL
60 | 25-01361 | 06/06/2025 08:00 | 06/12/2025 15:00 | SALEM-GRAND RONDE NO 1 115KV LINE | SALEM: PCB B-56 | 17095274 | LOAD, SOA, SLAL, NOPE
61 | 25-04502 | 06/06/2025 09:00 | 06/20/2025 16:00 | DIXONVILLE: ALVEY 1 500KV LINE SERIES CAP |  |  | NWACI, PDCI
62 | 25-01314 | 06/06/2025 22:30 | 06/06/2025 23:00 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 |  | 17003901 | GEN, NOH, WOCN
63 | 25-02176 | 06/07/2025 08:00 | 06/07/2025 15:00 | ASHE: CGS 1 500KV LINE RELAY SET 1, & 2 AND 500KV LOSS OF BUS SCHEME SET 1 & 2 O.A.T. | ASHE: PCB 4885, ASHE: PCB 4888 |  | GEN, NWACI, FCRPS
64 | 25-03604 | 06/07/2025 08:00 | 06/08/2025 16:00 | GRIZZLY: 4053/5039 TERMINALS OF GRIZZLY-ROUND BUTTE 500KV LINE | GRIZZLY: PCB 5040, GRIZZLY: PCB 4052, GRIZZLY-PGE ROUND BUTTE NO 1 500KV LINE | 17293189 | NWACI, WOJD, SIG
65 | 25-00486 | 06/07/2025 23:00 | 06/08/2025 09:00 | HOOD RIVER: 115KV M/B INCLUDING PCB'S B-1678, B-1679, B-1680, 115KV M/B PT'S AND B-1690 M/B DISCONNECT | HOOD RIVER: PCB B-1678, HOOD RIVER: PCB B-1680, CASCADE LOCKS-HOOD RIVER SECTION OF BONNEVILLE PH 1-HOOD RIVER NO 1 115KV LINE, HOOD RIVER-THE DALLES NO 1 115KV LINE, HOOD RIVER: PCB B-1679, HOOD RIVER: 115KV MAIN BUS, HOOD RIVER: HOOD RIVER ELEC 115KV FEEDER 1, HOOD RIVER: PACIFICORP (PACW) 115KV FEEDER 1, HOOD RIVER-COOP SERVICE NO 1 115KV LINE | 17373639 | GEN, WOCS, FCRPS, LOAD
66 | 25-00287 | 06/08/2025 22:00 | 06/27/2025 23:00 | GRAND COULEE: PCB 2292, GRAND COULEE: PCB 2296 |  |  | GEN, NOH, WOCN
67 | 25-07753 | 06/09/2025 07:00 | 09/04/2025 18:00 | SCL - BOTHELL: 230/115KV TRANSFORMER 61 | BOTHELL: 230/115KV TRANSFORMER 61 |  | LOAD, NOEL, SOC
68 | 25-00973 | 06/09/2025 07:00 | 06/12/2025 15:00 | OSTRANDER: PCB 4448 |  | 16929824 | WOCS
69 | 25-05884 | 06/09/2025 07:00 | 06/09/2025 07:30 | BIG EDDY: PCB A-812 OF THE DALLES PH-BIG EDDY NO 3 230KV LINE | THE DALLES PH-BIG EDDY NO 3 230KV LINE |  | GEN, FCRPS
70 | 25-04803 | 06/09/2025 07:30 | 06/12/2025 15:30 | ROSS: 230/115KV TRANSFORMER 2 RELAYS | ROSS: 230/115KV TRANSFORMER 2, ROSS: PCB A-28, ROSS: PCB B-4 | 17380715 | LOAD, SOA, NOPE
71 | 25-04059 | 06/09/2025 08:00 | 07/09/2025 15:00 | KEELER: PCB A-873 INCLUDING 230KV REACTIVE GROUP 2 REACTOR 1 | KEELER: PCB A-873, KEELER: 230KV REACTIVE GROUP 2 REACTOR 1 | 17320365 | SOA, NOPE
72 | 25-01079 | 06/09/2025 08:00 | 06/12/2025 16:00 | ALVEY: 230KV REACTOR 1, INCLUDING PCB A-241 |  | 17080834 | EWEB, NWACI, SLAL
73 | 25-05967 | 06/09/2025 08:00 | 06/12/2025 15:30 | GREEN VALLEY: 230/69KV TRANSFORMER 1 | DRAIN: DOUGLAS ELEC COOP 69KV FEEDER 1 TO OAKLAND, GREEN VALLEY: DOUGLAS ELEC COOP 69KV FEEDER 1, GREEN VALLEY: 230/69KV TRANSFORMER 1, GREEN VALLEY: 69KV PCB L-431, GREEN VALLEY: PCB A-507 | 17529529 | SCORC, SWORE, LOAD
74 | 25-01307 | 06/09/2025 08:00 | 06/10/2025 15:00 | KEELER: PCB 4763 INCLUDING 500KV CAP GROUP 3 | KEELER: 500KV CAP GROUP 3, KEELER: PCB 4763 | 17004753 | SOA, WOCS, NOPE
75 | 25-07236 | 06/09/2025 08:00 | 06/26/2025 15:30 | BIG EDDY: PCB 4866 BFR | BIG EDDY: PCB 4866 | 17657453 | GEN, PDCI, WOJD, BGEDY
76 | 25-06748 | 06/09/2025 08:00 | 06/11/2025 15:00 | MONROE: 230KV REACTOR 1 INCLUDING PCB A-1431 | MONROE: PCB A-1431, MONROE: 230KV REACTIVE GROUP 1 REACTOR 1 | 17611238 | NOEL, SOC, WOCN
77 | 25-01375 | 06/09/2025 08:00 | 06/09/2025 16:30 | SCHULTZ: PCB 5148 |  | 17180938 | WOCN, NOEL
78 | 25-00527 | 06/09/2025 08:00 | 06/12/2025 15:30 | BIG EDDY-CHEMAWA NO 1 230KV LINE |  | 17115999 | PDCI, WOCS, WOJD, NWACI
79 | 25-05403 | 06/09/2025 08:00 | 06/13/2025 18:00 | SCL - NORTH: 120KV BUS 7 INCLUDING BANK 56 AND PCB'S 120-80 & -81 |  |  | SOC/NOEL
80 | 25-02759 | 06/09/2025 12:00 | 06/18/2025 16:00 | ALVEY: 115KV NORTH MAIN BUS, INCLUDING PCBs: B-584, B-586, B-588, B-590, B-594, B-1660, AND B-1662 | ALVEY: PCB B-586, ALVEY: PCB B-588, ALVEY: PCB B-590, ALVEY: PCB B-594, ALVEY: PCB B-1660, ALVEY: PCB B-1662, ALVEY: PCB B-584, ALVEY PACW-GOSHEN SECTION OF ALVEY-MARTIN CREEK NO 1 115KV LINE, ALVEY: EWEB (EUGENE OR) 115KV FEEDER 1 TO CURRIN, PLEASANT HILL-ALVEY SECTION OF LOOKOUT POINT-ALVEY NO 1 115KV LINE, ALVEY: 115KV CAP GROUP 1 SECTION 1, ALVEY: 115KV CAP GROUP 1 SECTION 2, ALVEY: 230/115KV TRANSFORMER 4, ALVEY: SPRNGFLD UTIL BRD 115KV FEEDER 1 TO 10TH STREET, ALVEY: 115KV AUX BUS | 17339709 | LOAD, EWEB, NWACI, GEN, SCORC
81 | 25-07147 | 06/10/2025 07:00 | 06/11/2025 16:00 | COLUMBIA: A-344 TERMINAL OF COLUMBIA-WANAPUM NO 2 230KV LINE | COLUMBIA-ANCIENT LAKE SECTION OF COLUMBIA-WANAPUM NO 2 230KV LINE | 17649664 | CI
82 | 25-07711 | 06/10/2025 07:00 | 06/10/2025 15:00 | GOSHEN: PCB B-1346 | CATTLE CREEK-GOSHEN NO 1 115KV LINE, GOSHEN: 161/115KV TRANSFORMER 1, GOSHEN: 161/115KV TRANSFORMER 2 | 17725459 | SEIL, GEN
83 | 25-00884 | 06/10/2025 07:30 | 06/10/2025 07:45 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 |  | 16841117 | GEN, NOH, WOCN
84 | 25-01381 | 06/10/2025 08:00 | 06/12/2025 16:30 | SCHULTZ: PCB 5151 |  | 17175423 | WOCN, NOEL
85 | 25-07063 | 06/10/2025 10:00 | 06/10/2025 21:00 | CELILO: PACIFIC HVDC PROBING SIGNAL TEST, (ALTERNATE DATE) | CHIEF JOSEPH: BRAKING RESISTOR | 17642451 | NOH, SIG, NWACI
86 | 25-00885 | 06/10/2025 11:15 | 06/10/2025 11:30 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 |  | 16841123 | GEN, NOH, WOCN
87 | 25-02117 | 06/11/2025 08:00 | 06/12/2025 16:00 | CENTRAL FERRY: PCB 5432 INCLUDING 500KV REACTOR 1 | CENTRAL FERRY: PCB 5432, CENTRAL FERRY: 500KV REACTOR 1 | 17127835 | WOH, WOLM
88 | 25-06027 | 06/12/2025 07:00 | 06/12/2025 11:00 | CUSTER: PCB A-1250 |  | 17596724 | BCHT, BCHW, NOEL, SOC, NI
89 | 25-01654 | 06/12/2025 07:00 | 06/12/2025 11:00 | RAVER: PCB 4308 |  | 17094302 | NOEL, RP, SOC, WOCN
90 | 25-01656 | 06/12/2025 11:00 | 06/12/2025 15:00 | RAVER: PCB 4311 |  | 17094294 | NOEL, RP, SOC, WOCN
91 | 25-06623 | 06/12/2025 11:30 | 06/12/2025 15:00 | CUSTER: PCB A-1540 |  | 17596731 | BCHT, BCHW, NOEL, SOC, NI
92 | 25-05885 | 06/12/2025 16:30 | 06/12/2025 17:00 | BIG EDDY: PCB A-812 OF THE DALLES PH-BIG EDDY NO 3 230KV LINE | THE DALLES PH-BIG EDDY NO 3 230KV LINE |  | GEN, FCRPS
93 | 25-00939 | 06/16/2025 07:00 | 06/29/2025 16:00 | SNOHOMISH-BOTHELL NO 1 230KV LINE |  | 16841149 | NOEL, SOC
94 | 25-07633 | 06/16/2025 07:00 | 10/31/2025 16:00 | -CPUD- MEEKER-NORTH WOODLAND 115KV LINE | MEEKER-NORTH WOODLAND 115KV LINE | 17718483 | LOAD, SOA, NOPE
95 | 25-01179 | 06/16/2025 07:00 | 06/16/2025 15:00 | GRAND COULEE-BELL NO 3 230KV LINE INCLUDING BELL: 230KV AUX BUS SECTION 5 AND PCB A-558 | GRAND COULEE-BELL NO 3 230KV LINE, BELL: 230KV AUX BUS SECTION 5, BELL: PCB A-558, BELL: PCB A-552 | 17191219 | NOH, WOH, MT-NW
96 | 25-05888 | 06/16/2025 07:00 | 06/16/2025 07:30 | THE DALLES PH-BIG EDDY NO 3 230KV LINE | THE DALLES PH: 230/13.8KV TRANSFORMER T3, THE DALLES PH: 230/13.8KV TRANSFORMER T4 |  | GEN, FCRPS
97 | 25-01080 | 06/16/2025 08:00 | 06/26/2025 15:00 | ALVEY: 230KV REACTIVE GROUP 2, CAP SECTIONS 1, 2, AND 3 INCLUDING: PCBs A-476, A-235, A-237, AND A-239 | ALVEY: 230KV REACTIVE GROUP 2 CAP SECTION 1, ALVEY: 230KV REACTIVE GROUP 2 CAP SECTION 2, ALVEY: 230KV REACTIVE GROUP 2 CAP SECTION 3, ALVEY: PCB A-476, ALVEY: PCB A-235, ALVEY: PCB A-237, ALVEY: PCB A-239 | 17122618 | EWEB, NWACI
98 | 25-02087 | 06/16/2025 08:00 | 06/18/2025 15:00 | FAIRMOUNT-HAPPY VALLEY SECTION OF FAIRMOUNT-PORT ANGELES NO 2 230KV LINE |  | 17208207 | SOA, RP, NOPE
99 | 25-01248 | 06/16/2025 08:00 | 06/17/2025 16:00 | GLASGOW-SUMNER SECTION OF REEDSPORT-FAIRVIEW NO 1 115KV LINE |  | 17075964 | LOAD, SCORC
100 | 25-01204 | 06/16/2025 08:00 | 06/16/2025 16:00 | CARLTON: PCB A-315 | CARLTON-TILLAMOOK NO 1 230KV LINE, TILLAMOOK: 230/115KV TRANSFORMER 2 | 17036887 | LOAD, SOA, NOPE, NWACI
101 | 25-04252 | 06/16/2025 08:00 | 06/17/2025 15:00 | COLUMBIA-VALHALLA NO 2 115KV LINE |  | 17339570 | CI, NOH
102 | 25-04291 | 06/16/2025 08:00 | 07/02/2025 15:00 | ROSS: 230/115KV TRANSFORMER 1 | ROSS: PCB A-26, ROSS: PCB B-2, ROSS: 13.2KV PCB L-25 | 17337016 | LOAD, SOA, NOPE
103 | 25-02086 | 06/16/2025 08:00 | 06/22/2025 15:00 | T3BA'DAS-FAIRMOUNT SECTION OF SHELTON-FAIRMOUNT NO 2 115KV LINE |  | 17268975 | PA
104 | 25-06751 | 06/16/2025 08:00 | 06/16/2025 16:00 | OLYMPIA: 230/115KV TRANSFORMER 1 | OLYMPIA: PCB A-218, OLYMPIA: PCB B-682 | 17643935 | NOEL, RP, WOCN, SOC
105 | 25-01378 | 06/16/2025 08:00 | 06/18/2025 16:30 | SCHULTZ: RAVER 1 500KV LINE SERIES CAP GROUP 1 INCLUDING PCB 5163 | SCHULTZ: PCB 5163, SCHULTZ: RAVER 1 500KV LINE SERIES CAP GROUP 1 | 17299613 | WOCN, NOEL, IROL, SOC, SIG
106 | 25-05405 | 06/16/2025 08:00 | 06/21/2025 18:00 | SCL - BOTHELL-NORTH 120KV LINE INCLUDING NORTH: 120KV BUS 1 AND PCB'S 120-75 & -81 |  |  | SOC/NOEL
107 | 25-06811 | 06/16/2025 08:00 | 06/25/2025 15:30 | PACE: THEIR THREE MILE KNOLL 121A TERMINAL | HOOPER SPRINGS-THREE MILE KNOLL NO 1 138KV LINE, HOOPER SPRINGS: 138/115KV BANK 1 |  | ID-NW
108 | 25-01360 | 06/16/2025 08:00 | 06/17/2025 15:00 | KEELER-FOREST GROVE NO 2 115KV LINE |  | 17298724 | LOAD, SOA, NOPE
109 | 25-01180 | 06/17/2025 07:00 | 06/17/2025 15:00 | GRAND COULEE-BELL NO 5 230KV LINE INCLUDING BELL: 230KV AUX BUS SECTION 3 AND PCB A-382 | GRAND COULEE-BELL NO 5 230KV LINE, BELL: 230KV AUX BUS SECTION 3, BELL: PCB A-382, BELL: PCB A-372, GRAND COULEE: PCB 7286 | 17191638 | NOH, WOH, MT-NW, WOCN
110 | 25-05256 | 06/17/2025 07:30 | 06/17/2025 16:00 | ABERDEEN: 230/115KV TRANSFORMER 5 | SATSOP-ABERDEEN NO 3 230KV LINE, ABERDEEN: PCB B-807, SATSOP: PCB A-619, SATSOP: PCB A-616 | 17490879 | LOAD, SI, GEN
111 | 25-00908 | 06/17/2025 07:30 | 06/17/2025 07:45 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 |  | 16821985 | GEN, NOH, WOCN
112 | 25-00459 | 06/17/2025 08:00 | 06/18/2025 15:00 | HILLTOP: PCB A-1525 |  | 17116209 | RATS, NWACI
113 | 25-00462 | 06/17/2025 08:00 | 06/17/2025 17:00 | GOBLE-RAINIER SECTION OF ST HELENS-ALLSTON NO 1 115KV LINE |  | 16842562 | SOA, NOPE
114 | 25-00909 | 06/17/2025 11:15 | 06/17/2025 11:30 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 |  | 16821976 | GEN, NOH, WOCN
115 | 25-05637 | 06/18/2025 07:00 | 06/18/2025 16:00 | SHELTON: PCB A-971 |  | 17518950 | RP
116 | 25-01181 | 06/18/2025 07:00 | 06/18/2025 15:00 | BELL-USK NO 1 230KV LINE INCLUDING BELL: 230KV AUX BUS SECTION 3 AND PCB A-394 | BELL-USK NO 1 230KV LINE, BELL: 230KV AUX BUS SECTION 3, BELL: PCB A-372, BELL: PCB A-394, USK: PCB A-955, USK: PCB A-958 | 17191535 | SOB, GEN, WOH, MT-NW
117 | 25-03625 | 06/18/2025 08:00 | 07/02/2025 16:00 | GRIZZLY: 4047/4049 TERMINALS AND MALIN: 4071/4073/4341 TERMINALS OF GRIZZLY-MALIN 2 500KV LINE | GRIZZLY-MALIN PGE NO 2 500KV LINE, SAND SPRINGS: GRIZZLY-MALIN 2 500KV LINE SERIES CAP GROUP 2, FORT ROCK: GRIZZLY-MALIN 2 500KV LINE SERIES CAP GROUP 2, SYCAN: GRIZZLY-MALIN 2 500KV LINE SERIES CAP GROUP 2 | 17293918 | BCHT, BCHW, NI, NWACI, SIG
118 | 25-00463 | 06/18/2025 08:00 | 06/18/2025 17:00 | RAINIER-ALLSTON SECTION OF ST HELENS-ALLSTON NO 1 115KV LINE | ALLSTON: PCB B-1901 | 16842566 | SOA, NOPE
119 | 25-05259 | 06/18/2025 08:00 | 06/18/2025 15:00 | KEELER-FOREST GROVE NO 1 115KV LINE | KEELER: PCB B-1086, FOREST GROVE: PCB B-650 | 17569733 | LOAD, SOA, NOPE
120 | 25-02088 | 06/19/2025 08:00 | 06/23/2025 15:00 | FAIRMOUNT-PORT ANGELES NO 1 230KV LINE |  | 17208676 | RP
121 | 25-05889 | 06/19/2025 16:30 | 06/19/2025 17:00 | THE DALLES PH-BIG EDDY NO 3 230KV LINE | THE DALLES PH: 230/13.8KV TRANSFORMER T3, THE DALLES PH: 230/13.8KV TRANSFORMER T4 |  | GEN, FCRPS
122 | 25-02204 | 06/20/2025 12:30 | 06/20/2025 17:00 | COLUMBIA: GRAND COULEE-SCHULTZ NO 1 500KV SERIES CAP GROUP 1 INCLUDING PCB 4694 | COLUMBIA: PCB 4694, COLUMBIA: GRAND COULEE-SCHULTZ 1 500KV LINE SERIES CAP GROUP 1 |  | NOH, WOCN, IROL, NOEL, SOC
123 | 25-04414 | 06/21/2025 03:00 | 06/22/2025 20:00 | CELILO: 9085 TERMINAL OF CELILO-SYLMAR POLE 3 AND 9084 TERMINAL OF CELILO-SYLMAR POLE 4 1000KV LINE, CELILO: 9054/9092 TERMINAL OF RICE FLATS ELECTRODE, BIG EDDY: 4214 TERMINAL OF BIG EDDY-CELILO #1 500KV LINE, BIG EDDY: 4207 TERMINAL OF BIG EDDY-CELILO #2 500KV LINE | BIG EDDY-CELILO NO 1 500KV LINE, BIG EDDY-CELILO NO 2 500KV LINE, CELILO-SYLMAR POLE NO 3 1000KV LINE, CELILO-SYLMAR POLE NO 4 1000KV LINE, CELILO: POLE 3 540/240/240KV TRANSFORMER, CELILO: POLE 3 CONVERTER 1, CELILO: POLE 4 540/240/240KV TRANSFORMER, CELILO: POLE 4 CONVERTER 2, CELILO: PCB 4741, CELILO: PCB 4740 | 17360986 | PDCI, SIG, BGEDY, NWACI, GEN
124 | 25-04415 | 06/21/2025 03:00 | 06/22/2025 20:00 | CELILO: 9085 TERMINAL OF CELILO-SYLMAR POLE 3 AND 9084 TERMINAL OF CELILO-SYLMAR POLE 4 1000KV LINE (GROUNDED) |  |  | PDCI
125 | 25-05894 | 06/23/2025 07:00 | 06/23/2025 07:30 | BIG EDDY: PCB A-824 OF THE DALLES PH-BIG EDDY NO 4 230KV LINE | THE DALLES PH-BIG EDDY NO 4 230KV LINE |  | GEN, FCRPS
126 | 25-03605 | 06/23/2025 07:00 | 07/02/2025 15:00 | KELLER-NESPELEM SECTION OF GRAND COULEE-OKANOGAN NO 2 115KV LINE |  | 17299738 | LOAD
127 | 25-03132 | 06/23/2025 07:00 | 06/23/2025 14:00 | TARGHEE: PCB B-1422 | TARGHEE-DRUMMOND NO 1 115KV LINE | 17269033 | SEIL, GEN
128 | 25-00394 | 06/23/2025 07:00 | 06/26/2025 16:30 | ROCKY REACH-MAPLE VALLEY NO 1 345KV LINE INCLUDING ROCKY REACH: 345/230KV TRANSFORMER 1 | MAPLE VALLEY: 345/230KV TRANSFORMER 1, ROCKY REACH: 345/230KV TRANSFORMER 1, ROCKY REACH-MAPLE VALLEY NO 1 345KV LINE | 16425606 | NOEL, SOC, WOCN, IROL, GEN, NOH, CI
129 | 24-02160 | 06/23/2025 07:00 | 06/23/2025 16:30 | GARRISON: 4428/4436/4437 TERMINAL OF BROADVIEW-GARRISON 1 500KV LINE | GARRISON: 4428/4436/4437 TERMINAL OF BROADVIEW-GARRISON 1 500KV LINE, BROADVIEW-GARRISON NO 1 500KV LINE | 14854315 | MT-NW, GEN
130 | 25-01254 | 06/23/2025 08:00 | 06/24/2025 16:00 | GLASGOW-SUMNER SECTION OF REEDSPORT-FAIRVIEW NO 1 115KV LINE |  | 17087091 | LOAD, SCORC
131 | 25-00661 | 06/23/2025 08:00 | 06/24/2025 15:00 | LOWER MONUMENTAL: PCB 4676 |  | 16841107 | WOLM
132 | 25-00913 | 06/23/2025 08:00 | 06/26/2025 15:00 | TAFT: PCB 4119, BFR |  | 17087584 | MT-NW, WOH
133 | 25-01518 | 06/23/2025 08:00 | 06/23/2025 16:00 | LOWER GRANITE: PCB 4775 |  | 17080315 | MT-NW, WOH, WOLM, GEN
134 | 25-02307 | 06/23/2025 08:00 | 06/26/2025 16:30 | HOOD RIVER-THE DALLES NO 1 115KV LINE |  | 17209101 | WOCS, FCRPS, GEN
135 | 25-03595 | 06/23/2025 08:00 | 06/23/2025 15:00 | PEARL: A-1165 TERMINAL OF THE PEARL TAP TO PGE MCLOUGHLIN SHERWOOD NO.1 230KV LINE | MCLOUGHLIN-PEARL SECTION OF MCLOUGHLIN-SHERWOOD NO 1 230KV LINE |  | SOA, WOCS, NOPE
136 | 25-00464 | 06/23/2025 08:00 | 06/28/2025 17:00 | ST HELENS-DEER ISLAND SECTION OF ST HELENS-ALLSTON NO 1 115KV LINE |  | 16842576 | SOA, LOAD
137 | 25-04065 | 06/23/2025 08:00 | 06/24/2025 15:00 | REDMOND: 69KV PCB L-214 | REDMOND: PACIFICORP (PACW) 69KV FEEDER 1 |  | COR
138 | 25-01379 | 06/23/2025 08:00 | 06/23/2025 12:00 | SCHULTZ: PCB 5132 |  | 17175351 | WOCN, NOEL
139 | 25-06210 | 06/23/2025 09:00 | 06/27/2025 15:00 | REDMOND: A-252 TERMINAL OF REDMOND-PACW PILOT BUTTE NO 1 230KV LINE | REDMOND-PILOT BUTTE PACW NO 1 230KV LINE | 17542325 | LOAD, COR, NWACI
140 | 25-01380 | 06/23/2025 12:30 | 06/23/2025 16:30 | SCHULTZ: PCB 5129 |  | 17175403 | WOCN, NOEL
141 | 25-06368 | 06/24/2025 07:00 | 06/24/2025 16:00 | COLUMBIA FALLS-KALISPELL NO 1 115KV LINE |  | 17570340 | GEN, LOAD, MT-NW, FLAT
142 | 25-00890 | 06/24/2025 07:30 | 06/24/2025 07:45 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 |  | 16842232 | GEN, NOH, WOCN
143 | 25-00044 | 06/24/2025 08:00 | 06/24/2025 15:00 | KEELER: 230/115KV TRANSFORMER 1 | KEELER: 230/115KV TRANSFORMER 1, KEELER: PCB A-860, KEELER: PCB B-1066, KEELER: 13.8KV PCB 1W STATION SERVICE 1, KEELER: 13.8KV SVC SS #1 | 13333778 | SOA, LOAD
144 | 25-01256 | 06/24/2025 08:00 | 06/24/2025 16:00 | CENTRAL FERRY: PCB 5391 | CENTRAL FERRY: PCB 5391 | 16978112 | GEN, WOLM
145 | 25-01377 | 06/24/2025 08:00 | 06/26/2025 16:00 | SCHULTZ: ECHO LAKE 1 500KV LINE SERIES CAP GROUP 1 INCLUDING PCB 5142 | SCHULTZ: PCB 5142, SCHULTZ: ECHO LAKE 1 500KV LINE SERIES CAP GROUP 1 | 17299573 | WOCN, NOEL, IROL, SOC
146 | 25-00891 | 06/24/2025 11:15 | 06/24/2025 11:30 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 |  | 16842244 | GEN, NOH, WOCN
147 | 25-06600 | 06/25/2025 07:00 | 06/25/2025 15:00 | BELL: 230KV MAIN BUS SECTION 1 | DAY MT SPOKANE-BELL SECTION OF SACHEEN-BELL NO 1 230KV LINE, BELL: 230KV CAP GROUP 10 SECTION 1, BELL: 230KV CAP GROUP 10 SECTION 2, BELL: PCB A-366, BELL: PCB A-368, BELL: PCB A-374, BELL: PCB A-370, BELL: PCB A-375, BELL: LBD A-925, BELL: LBD A-926, BELL: 230KV AUX BUS SECTION 1, BELL: 230KV AUX BUS SECTION 2 | 17604158 | MT-NW, WOH, SOB
148 | 25-00663 | 06/25/2025 08:00 | 06/25/2025 15:00 | LOWER MONUMENTAL: PCB 4290 |  | 17318986 | WOLM
149 | 25-00483 | 06/25/2025 22:00 | 06/25/2025 22:30 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 |  | 16463596 | GEN, NOH, WOCN
150 | 25-03360 | 06/26/2025 07:30 | 06/26/2025 15:00 | LOWER MONUMENTAL: PCB 4624 |  | 17319826 | WOLM
151 | 25-01339 | 06/26/2025 08:00 | 06/26/2025 15:00 | SLATT-JOHN DAY NO 1 500KV LINE INCLUDING SLATT PCB'S 5018 AND 5021 AND JOHN DAY PCB'S 4128 AND 4131 | SLATT: PCB 5018, SLATT: PCB 5021, JOHN DAY: PCB 4131, JOHN DAY: PCB 4128 | 17009965 | WOJD, NWACI, WOS, PDCI
152 | 25-02268 | 06/26/2025 08:30 | 06/26/2025 17:00 | LAPINE: PCB A-1552 | LAPINE: 230/115KV TRANSFORMER 2 | 17269178 | COR, NWACI, GRZN
153 | 25-07279 | 06/26/2025 12:00 | 06/26/2025 13:00 | BIG EDDY: PCB 4870 |  | 17676830 | GEN, PDCI, WOJD, BGEDY, SOA, NOPE
154 | 25-06096 | 06/26/2025 16:00 | 11/14/2025 08:00 | ROCKY REACH: 345/230KV TRANSFORMER 1 INCLUDING MODS A-3017, A-3016 AND THE A-1001 DISCONNECTS | ROCKY REACH: 345/230KV TRANSFORMER 1 | 17530014 | GEN, IROL, NOEL, NOH, SOC, WOCN
155 | 25-05895 | 06/26/2025 16:30 | 06/26/2025 17:00 | BIG EDDY: PCB A-824 OF THE DALLES PH-BIG EDDY NO 4 230KV LINE | THE DALLES PH-BIG EDDY NO 4 230KV LINE |  | GEN, FCRPS
156 | 25-06511 | 06/27/2025 08:00 | 06/30/2025 15:00 | ALVEY: PCB 5087, MODS 5086, 5088, 5089 CONTROL AND ALARM CIRCUITS | ALVEY: 500KV SOUTH BUS, ALVEY: PCB 5087 | 17576986 | NWACI, EWEB
157 | 25-00484 | 06/27/2025 22:30 | 06/27/2025 23:00 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 |  | 16463602 | GEN, NOH, WOCN
158 | 25-06557 | 06/28/2025 06:00 | 06/28/2025 17:00 | -IPC- HELLS CANYON-HURRICANE 230KV LINE | HELLS CANYON (IPC)-HURRICANE 230KV LINE |  | ID-NW, WOH
159 | 25-02007 | 06/29/2025 22:00 | 06/29/2025 22:15 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 |  | 17115714 | GEN, NOH, WOCN
160 | 25-00310 | 06/30/2025 06:30 | 07/02/2025 17:00 | OLYMPIA: A-206 TERMINAL OF OLYMPIA-GRAND COULEE NO 1 230KV LINE | OLYMPIA: PCB A-206, GRAND COULEE: PCB 6886, OLYMPIA-GRAND COULEE NO 1 230KV LINE | 17116530 | NOEL, RP, SOC, WOCN, NOH, IROL
161 | 25-05897 | 06/30/2025 07:00 | 06/30/2025 07:30 | BIG EDDY: PCB A-824 OF THE DALLES PH-BIG EDDY NO 4 230KV LINE | THE DALLES PH-BIG EDDY NO 4 230KV LINE |  | GEN, FCRPS
162 | 25-05139 | 06/30/2025 07:30 | 07/01/2025 17:00 | LOOKOUT POINT-MT. VERNON SECTION OF LOOKOUT POINT-ALVEY NO 2 115KV LINE |  |  | GEN
163 | 25-00849 | 06/30/2025 08:00 | 08/08/2025 15:00 | MARTIN CREEK: 230/115KV TRANSFORMER 1 INCLUDING PCB A-443 | MARTIN CREEK: 230/115KV TRANSFORMER 1, MARTIN CREEK: PCB A-443, MARTIN CREEK TAP TO ALVEY-FAIRVIEW NO 1 230KV LINE | 17326275 | SCORC, LOAD
164 | 25-00956 | 06/30/2025 08:00 | 07/01/2025 16:00 | JOHN DAY: PCB 4170 (108E) BFR and PCB DIFF | JOHN DAY: PCB 4170 | 17005005 | NWACI, WOCS, WOJD, PDCI
165 | 25-05945 | 06/30/2025 08:00 | 07/22/2025 15:00 | CARLTON-TILLAMOOK NO 1 230KV LINE INCLUDING PCB A-315 AND 230KV AUX BUS | CARLTON-TILLAMOOK NO 1 230KV LINE, TILLAMOOK: 230/115KV TRANSFORMER 2 | 17503965 | LOAD, SOA, NOPE, NWACI
166 | 25-01382 | 06/30/2025 08:00 | 06/30/2025 15:00 | SCHULTZ: PCB 5154 |  | 17175502 | WOCN, NOEL
167 | 25-04079 | 06/30/2025 08:30 | 06/30/2025 16:00 | LAPINE: PCB A-1494 INCLUDING 230/115KV TRANSFORMER 1 | LAPINE: 230/115KV TRANSFORMER 1, LAPINE: PCB A-1494, LAPINE: 230/115KV TRANSFORMER 2 | 17333427 | COR, GRZN, NWACI