## Primary Application
TP-GO Implementation Plan
Entity Name: | Bonneville Power Administration
Details for the Proposed Implemenation Plan:
Identify and describe the action plan, including specific tasks and actions that your organization is proposing to undertake:
Bonneville Power Administration (BPA) is working with registered Generator Owners (GO) within it's Planning Coordinator (PC) area to complete implemenation of Transmission Planner (TP) standards. There are several generation facilities within BPA's PC area where the registered GO/GOP is also a TP. BPA will meet with these entities and finalize TP responsibilities by 12/31/2018. BPA expects to be fully compliant as the TP for GOs by 5/1/2019.
Provide the timetable for completion of the Implementation Plan, including completion date by which the plan will be fully implemented:
Proposed Completion Date (Milestones should not be more than 3 months apart) | Milestone Activity
Status | DATE | Responsible Party | Standard | Action
In Progress | 2018-11-05 | BPA | NA | Validate BES generation mapped to BPA as the TP
Future | 2018-12-31 | BPA | NA | Validate with other TPs who is responsible for Facility model validation
Future | 2019-01-30 | BPA/TPCR | MOD-026/027 | Develop internal processes for handling model validation submissions
Future | 2019-01-30 | BPA | NA | Determine appropriate contract vehicle
Future | 2019-02-28 | BPA/TPMG | MOD-026/027 | Finalize 10 year schedule for GO model validation testing
Future | 2019-01-30 | BPA | NA | Ensure all BES generation is in applicable models
Future | 2019-04-01 | BPA | TPL-001-4, R1.1.2 | Data request to GO entity for communication of known outages > 6 months within the planning horizon
Future | 2019-05-01 | BPA | NA | Execute applicable contract with GO entities
Future | 2019-05-01 | BPA | All | Full Compliance
Reliability Risk:
While the plan is being implemented, the reliability of the Bulk Power System (BPS) may remain at higher risk or be otherwise negatively impacted until the plan is successfully completed. To the extent they are known or anticipated: (i) Identify any such risks or impacts, and: (ii) discuss any actions planned or proposed to address these risks or impacts:
BPA Response:
The risk resulting from the lack of an identified Transmission Planner would be limited to the identified generators. There is a minimal immediate (< 1 year) risk to reliability because they would only impact their local area system and not the overall reliability of the BPS within the Northwest. However, there is a longer term risk to reliability if generators are not coordinating model validation reports with an identified TP throughout the planning horizon (> 1 year to 10 years). BPA has identified two processes that need to be assessed and modified to ensure full coverage of model validation.
Implementation Plan(s) Submittted:
Yes | TPL-001-4 | R1.1.2. | Known outage(s) of generation or Transmission Facility(ies) with a duration of at least six months.
Yes | MOD-026-1 | R1. | Each Transmission Planner shall provide the following requested information to the Generator Owner within 90 calendar days of receiving a written request : • Instructions on how to obtain the list of excitation control system or plant volt/var control function models that are acceptable to the Transmission Planner for use in dynamic simulation, • Instructions on how to obtain the dynamic excitation control system or plant volt/var control function model library block diagrams and/or data sheets for models that are acceptable to the Transmission Planner, or • Model data for any of the Generator Owner’s existing applicable unit specific excitation control system or plant volt/var control function contained in the Transmission Planner’s dynamic database from the current (in-use) models, including generator MVA base.
Yes | MOD-026-1 | R6. | Each Transmission Planner shall provide a written response to the Generator Owner within 90 calendar days of receiving the verified excitation control system or plant volt/var control function model information in accordance with Requirement R2 that the model is usable (meets the criteria specified in Parts 6.1 through 6.3) or is not usable. 6.1. The excitation control system or plant volt/var control function model initializes to compute modeling data without error, 6.2. A no-disturbance simulation results in negligible transients, and 6.3. For an otherwise stable simulation, a disturbance simulation results in the excitation control and plant volt/var control function model exhibiting positive damping. If the model is not usable, the Transmission Planner shall provide a technical description of why the model is not usable.
Yes | MOD-027-1 | R1. | Each Transmission Planner shall provide the following requested information to the Generator Owner within 90 calendar days of receiving a written request: • Instructions on how to obtain the list of turbine/governor and load control or active power/frequency control system models that are acceptable to the Transmission Planner for use in dynamic simulation, • Instructions on how to obtain the dynamic turbine/governor and load control or active power/frequency control function model library block diagrams and/or data sheets for models that are acceptable to the Transmission Planner, or • Model data for any of the Generator Owner’s existing applicable unit specific turbine/governor and load control or active power/frequency control system contained in the Transmission Planner’s dynamic database from the current (in-use) models.
Yes | MOD-027-1 | R5. | Each Transmission Planner shall provide a written response to the Generator Owner within 90 calendar days of receiving the turbine/governor and load control or active power/frequency control system verified model information in accordance with Requirement R2 that the model is usable (meets the criteria specified in Parts 5.1 through 5.3) or is not usable. 5.1. The turbine/governor and load control or active power/frequency control function model initializes to compute modeling data without error, 5.2. A no-disturbance simulation results in negligible transients, and 5.3. For an otherwise stable simulation, a disturbance simulation results in the turbine/governor and load control or active power/frequency control model exhibiting positive damping. If the model is not usable, the Transmission Planner shall provide a technical description of why the model is not usable.

## MOD-026-1
TP-GO Implementation Plan
Entity Name: | Bonneville Power Administration
Standard: | MOD-026-1
Requirement(s): | R1. / R6.
Details for the Proposed Implemenation Plan:
Identify and describe the action plan for each specific requirement, including specific tasks and actions that your organization is proposing to undertake:
Provide the timetable for completion of the Implementation Plan, including completion date by which the plan will be fully implemented. Milestones should not be more than 3 months apart.
Proposed Completion Date | Milestone Activity
2019-01-30 | Develop internal processes for handling model validation submissions
2019-02-28 | Finalize 10 year schedule for GO model validation testing
Reliability Risk:
While the plan is being implemented, the reliablity of the Bulk Power System (BPS) may remain at higher risk or be otherwise negatively impacted until the plan is sucessfully completed. To the extent they are know or anticipated: (i) Identify any such risks or impacts, and: (ii) discuss any actions planned or propsed to address these risks or impacts:
Implementation Plan(s) Submittted:
Yes | MOD-026-1 | R1. | Each Transmission Planner shall provide the following requested information to the Generator Owner within 90 calendar days of receiving a written request : • Instructions on how to obtain the list of excitation control system or plant volt/var control function models that are acceptable to the Transmission Planner for use in dynamic simulation, • Instructions on how to obtain the dynamic excitation control system or plant volt/var control function model library block diagrams and/or data sheets for models that are acceptable to the Transmission Planner, or • Model data for any of the Generator Owner’s existing applicable unit specific excitation control system or plant volt/var control function contained in the Transmission Planner’s dynamic database from the current (in-use) models, including generator MVA base.
Yes | MOD-026-1 | R6. | Each Transmission Planner shall provide a written response to the Generator Owner within 90 calendar days of receiving the verified excitation control system or plant volt/var control function model information in accordance with Requirement R2 that the model is usable (meets the criteria specified in Parts 6.1 through 6.3) or is not usable. 6.1. The excitation control system or plant volt/var control function model initializes to compute modeling data without error, 6.2. A no-disturbance simulation results in negligible transients, and 6.3. For an otherwise stable simulation, a disturbance simulation results in the excitation control and plant volt/var control function model exhibiting positive damping. If the model is not usable, the Transmission Planner shall provide a technical description of why the model is not usable.

## MOD-027-1
TP-GO Implementation Plan
Entity Name: | Bonneville Power Administration
Standard: | MOD-027-1
Requirement(s): | R1. / R5.
Details for the Proposed Implemenation Plan:
Identify and describe the action plan for each specific requirement, including specific tasks and actions that your organization is proposing to undertake:
BPA is developing internal processes, schedules and controls for implementing MOD-027-1 as the Transmission Planner.
Provide the timetable for completion of the Implementation Plan, including completion date by which the plan will be fully implemented. Milestones should not be more than 3 months apart.
Proposed Completion Date | Milestone Activity
2019-01-30 | Develop internal processes for handling model validation submissions
2019-02-28 | Finalize 10 year schedule for GO model validation testing
Reliability Risk:
While the plan is being implemented, the reliablity of the Bulk Power System (BPS) may remain at higher risk or be otherwise negatively impacted until the plan is sucessfully completed. To the extent they are know or anticipated: (i) Identify any such risks or impacts, and: (ii) discuss any actions planned or propsed to address these risks or impacts:
Implementation Plan(s) Submittted:
Yes | MOD-027-1 | R1. | Each Transmission Planner shall provide the following requested information to the Generator Owner within 90 calendar days of receiving a written request: • Instructions on how to obtain the list of turbine/governor and load control or active power/frequency control system models that are acceptable to the Transmission Planner for use in dynamic simulation, • Instructions on how to obtain the dynamic turbine/governor and load control or active power/frequency control function model library block diagrams and/or data sheets for models that are acceptable to the Transmission Planner, or • Model data for any of the Generator Owner’s existing applicable unit specific turbine/governor and load control or active power/frequency control system contained in the Transmission Planner’s dynamic database from the current (in-use) models.
Yes | MOD-027-1 | R5. | Each Transmission Planner shall provide a written response to the Generator Owner within 90 calendar days of receiving the turbine/governor and load control or active power/frequency control system verified model information in accordance with Requirement R2 that the model is usable (meets the criteria specified in Parts 5.1 through 5.3) or is not usable. 5.1. The turbine/governor and load control or active power/frequency control function model initializes to compute modeling data without error, 5.2. A no-disturbance simulation results in negligible transients, and 5.3. For an otherwise stable simulation, a disturbance simulation results in the turbine/governor and load control or active power/frequency control model exhibiting positive damping. If the model is not usable, the Transmission Planner shall provide a technical description of why the model is not usable.

## TPL-001-4
TP-GO Implementation Plan
Entity Name: | Bonneville Power Administration
Standard: | TPL-001-4
Requirement(s): | R1.1.2.
Details for the Proposed Implemenation Plan:
Identify and describe the action plan for each specific requirement, including specific tasks and actions that your organization is proposing to undertake:
Provide the timetable for completion of the Implementation Plan, including completion date by which the plan will be fully implemented. Milestones should not be more than 3 months apart.
Proposed Completion Date | Milestone Activity
2019-04-01 | Data request to GO entities for communication of known outages > 6 months within the planning horizon
Reliability Risk:
While the plan is being implemented, the reliablity of the Bulk Power System (BPS) may remain at higher risk or be otherwise negatively impacted until the plan is sucessfully completed. To the extent they are know or anticipated: (i) Identify any such risks or impacts, and: (ii) discuss any actions planned or propsed to address these risks or impacts:
Implementation Plan(s) Submittted:
Yes | TPL-001-4 | R1.1.2 | 1.1.2. Known outage(s) of generation or Transmission Facility(ies) with a duration of at least six months.